**Problem Deliverables:**

* Vendor selection
  + This will include the analysis of multiple vendor quotes to determine the most complete and cost effective option.
    - Light Fixtures
    - Design Build Lighting Control
    - Switchgear
* Man loaded schedule
  + Include weekly and peak manpower projections based off of the General Contractors schedule.
  + Note all electrical milestones.
  + Include quotable item estimated delivery/ installation dates if required.
* Updated final estimate
  + Includes final vendor selections.
  + Fire Alarm modifications as (if) required.
  + Impacts to gross margin.
  + Etc.
* Provide log with all the estimate changes including associated costs. ROM costs (rough orders of magnitude) are acceptable.
* Detailed light fixture submittal with all accessories identified.
* Bulletin #1 estimate and scope letter.
* Change order log.
* Panel relocation narrative and/or sketch.
* Schedule of values