## RFI Form
[6 empty] | Transmitted to: | General Constructions Inc
REQUEST FOR INFORMATION
PROJECT: | SPKR |  |  |  | CEI JOB NO.: |  | 14.1.14
TO: | General Construction Inc |  |  |  | RFI NO.: |  | 1
| 3100 Van Ness |  |  |  | REQUEST: |  | 2ND | 3RD
| San Francisco, CA |  |  | DRAWING LOCATION: |  |  | 5EP-.2.2
SPEC. PAGE/SECTION:
TITLE OR SECTION OF WORK: |  |  | Floor penetrations
COST EFFECT: |  |  | Yes | ISSUED BY: |  |  | CEI
SCHEDULE IMPACT: |  |  | No |  | DATE REQUIRED: |  | 2014-02-06
DATE:
WRITTEN DESCRIPTION OF PROBLEM:
On drawing 5EP-2.2 within Conference Rooms 5006, 5007, 5008, 5009, and 5010 power, data and AV is shown at the conference tables. Symbology indicates these tables will be fed via the cellular floor system. Upon receipt of the furniture drawings it appears that the required table feed locations shown do not land on cell, therefore a feed via the cell system is not possible within these rooms.
PROPOSED SOLUTION:
DISTRIBUTION: |  | CEI Project Manager |  |  | CEI Foreman |  |  | C.M.
|  | General Contractor |  |  | Owner |  |  | Architect
|  | EE |  |  | CEI RFI Binder |  |  | CEI Engineering