## Takt Plan
Phase | Date |  | 2020-01-06 |  |  |  |  | 2020-01-13 |  |  |  |  | 2020-01-20 |  |  |  |  | 2020-01-27 |  |  |  |  | 2020-02-03 |  |  |  |  | 2020-02-10 |  |  |  |  | 2020-02-17 |  |  |  |  | 2020-02-24 |  |  |  |  | 2020-03-02 |  |  |  |  | 2020-03-09 |  |  |  |  | 2020-03-16 |  |  |  |  | 2020-03-23 |  |  |  |  | 2020-03-30 |  |  |  |  | 2020-04-06 |  |  |  |  | 2020-04-13 |  |  |  |  | 2020-04-20 |  |  |  |  | 2020-04-27 |  |  |  |  | 2020-05-04 |  |  |  |  | 2020-05-11 |  |  |  |  | 2020-05-18 |  |  |  |  | 2020-05-25 |  |  |  |  | 2020-06-01 |  |  |  |  | 2020-06-08 |  |  |  |  | 2020-06-15 |  |  |  |  | 2020-06-22 |  |  |  |  | 2020-06-29 |  |  |  |  | 2020-07-06 |  |  |  |  | 2020-07-13 |  |  |  |  | 2020-07-20 |  |  |  |  | 2020-07-27 |  |  |  |  | 2020-08-03 |  |  |  |  | 2020-08-10 |  |  |  |  | 2020-08-17 |  |  |  |  | 2020-08-24 |  |  |  |  | 2020-08-31 |  |  |  |  | 2020-09-07 |  |  |  |  | 2020-09-14 |  |  |  |  | 2020-09-21 |  |  |  |  | 2020-09-28 |  |  |  |  | 2020-10-05 |  |  |  |  | 2020-10-12 |  |  |  |  | 2020-10-19 |  |  |  |  | 2020-10-26 |  |  |  |  | 2020-11-02 |  |  |  |  | 2020-11-09 |  |  |  |  | 2020-11-16 |  |  |  |  | 2020-11-23 |  |  |  |  | 2020-11-30 |  |  |  |  | 2020-12-07 |  |  |  |  | 2020-12-14 |  |  |  |  | 2020-12-21 |  |  |  |  | 2020-12-28 |  |  |  |  | 2021-01-04 |  |  |  |  | 2021-01-11 |  |  |  |  | 2021-01-18 |  |  |  |  | 2021-01-25 |  |  |  |  | 2021-02-01 |  |  |  |  | 2021-02-08 |  |  |  |  | 2021-02-15
| Week # | Area | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 8 |  |  |  |  | 9 |  |  |  |  | 10 |  |  |  |  | 11 |  |  |  |  | 12 |  |  |  |  | 13 |  |  |  |  | 14 |  |  |  |  | 15 |  |  |  |  | 16 |  |  |  |  | 17 |  |  |  |  | 18 |  |  |  |  | 19 |  |  |  |  | 20 |  |  |  |  | 21 |  |  |  |  | 22 |  |  |  |  | 23 |  |  |  |  | 24 |  |  |  |  | 25 |  |  |  |  | 26 |  |  |  |  | 27 |  |  |  |  | 28 |  |  |  |  | 29 |  |  |  |  | 30 |  |  |  |  | 31 |  |  |  |  | 32 |  |  |  |  | 33 |  |  |  |  | 34 |  |  |  |  | 35 |  |  |  |  | 36 |  |  |  |  | 37 |  |  |  |  | 38 |  |  |  |  | 39 |  |  |  |  | 40 |  |  |  |  | 41 |  |  |  |  | 42 |  |  |  |  | 43 |  |  |  |  | 44 |  |  |  |  | 45 |  |  |  |  | 46 |  |  |  |  | 47 |  |  |  |  | 48 |  |  |  |  | 49 |  |  |  |  | 50 |  |  |  |  | 51 |  |  |  |  | 52 |  |  |  |  | 53 |  |  |  |  | 54 |  |  |  |  | 55 |  |  |  |  | 56 |  |  |  |  | 57 |  |  |  |  | 58 |  |  |  |  | 59
 | time axis 2020-01-06 to 2021-02-23
 | time axis 2020-01-06 to 2021-02-23
TI Permit Received
PERIMETER WALLS | Floor 4 | A | 2020-06-29: Rough-in for Core and Shell Walls
|  | B | 2020-06-29: In-Wall Inspections
| Floor 5 | A | 2020-06-29: Install Drywall
|  | B | 2020-06-29: Tape, Paint & Finish
| Floor 6 | A | bar: 2020-04-29 to 2020-05-18
B | bar: 2020-05-06 to 2020-05-25
| Floor 7 | A | bar: 2020-04-06 to 2020-04-23
B | bar: 2020-04-13 to 2020-04-30
| Floor 3 | A | bar: 2020-04-20 to 2020-05-07
B | bar: 2020-04-27 to 2020-05-14
| Floor 2 | A | bar: 2020-05-04 to 2020-05-21
B | bar: 2020-05-11 to 2020-05-28
|  |  | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 8 |  |  |  |  | 9 |  |  |  |  | 10 |  |  |  |  | 11 |  |  |  |  | 12 |  |  |  |  | 13 |  |  |  |  | 14 |  |  |  |  | 15 |  |  |  |  | 16 |  |  |  |  | 17 |  |  |  |  | 18 |  |  |  |  | 19 |  |  |  |  | 20 |  |  |  |  | 21 |  |  |  |  | 22 |  |  |  |  | 23 |  |  |  |  | 24 |  |  |  |  | 25 |  |  |  |  | 26 |  |  |  |  | 27 |  |  |  |  | 28 |  |  |  |  | 29 |  |  |  |  | 30 |  |  |  |  | 31 |  |  |  |  | 32 |  |  |  |  | 33 |  |  |  |  | 34 |  |  |  |  | 35 |  |  |  |  | 36 |  |  |  |  | 37 |  |  |  |  | 38 |  |  |  |  | 39 |  |  |  |  | 40 |  |  |  |  | 41 |  |  |  |  | 42 |  |  |  |  | 43 |  |  |  |  | 44 |  |  |  |  | 45 |  |  |  |  | 46 |  |  |  |  | 47 |  |  |  |  | 48 |  |  |  |  | 49 |  |  |  |  | 50 |  |  |  |  | 51 |  |  |  |  | 52 |  |  |  |  | 53 |  |  |  |  | 54 |  |  |  |  | 55 |  |  |  |  | 56 |  |  |  |  | 57 |  |  |  |  | 58 |  |  |  |  | 59
OH SYSTEMS/DISTRIBUTION | Floor 4 | A | bar: 2020-03-03 to 2020-04-17
B | bar: 2020-03-10 to 2020-04-24
| Floor 5 | A | 2020-08-05: LAYOUT OH DISTRIBUTION
|  | B | 2020-08-05: INSTALL OH DISTRIBUTION
| Floor 6 | A | bar: 2020-03-31 to 2020-05-15
B | bar: 2020-04-07 to 2020-05-22
| Floor 7 | A | bar: 2020-04-15 to 2020-06-01
B | bar: 2020-04-21 to 2020-06-05
| Floor 3 | A | bar: 2020-02-14; 2020-04-29 to 2020-06-15
B | bar: 2020-05-05 to 2020-06-19
| Floor 2 | A | bar: 2020-05-12 to 2020-06-26
B | bar: 2020-05-19 to 2020-07-03
|  |  | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 8 |  |  |  |  | 9 |  |  |  |  | 10 |  |  |  |  | 11 |  |  |  |  | 12 |  |  |  |  | 13 |  |  |  |  | 14 |  |  |  |  | 15 |  |  |  |  | 16 |  |  |  |  | 17 |  |  |  |  | 18 |  |  |  |  | 19 |  |  |  |  | 20 |  |  |  |  | 21 |  |  |  |  | 22 |  |  |  |  | 23 |  |  |  |  | 24 |  |  |  |  | 25 |  |  |  |  | 26 |  |  |  |  | 27 |  |  |  |  | 28 |  |  |  |  | 29 |  |  |  |  | 30 |  |  |  |  | 31 |  |  |  |  | 32 |  |  |  |  | 33 |  |  |  |  | 34 |  |  |  |  | 35 |  |  |  |  | 36 |  |  |  |  | 37 |  |  |  |  | 38 |  |  |  |  | 39 |  |  |  |  | 40 |  |  |  |  | 41 |  |  |  |  | 42 |  |  |  |  | 43 |  |  |  |  | 44 |  |  |  |  | 45 |  |  |  |  | 46 |  |  |  |  | 47 |  |  |  |  | 48 |  |  |  |  | 49 |  |  |  |  | 50 |  |  |  |  | 51 |  |  |  |  | 52 |  |  |  |  | 53 |  |  |  |  | 54 |  |  |  |  | 55 |  |  |  |  | 56 |  |  |  |  | 57 |  |  |  |  | 58 |  |  |  |  | 59
PRE-MODULAR WALL | Floor 4 | A | bar: 2020-04-20 to 2020-05-08
B | bar: 2020-05-04 to 2020-05-15
C | bar: 2020-05-11 to 2020-05-22
| Floor 5 | A | 2020-09-14: FLOOR PREP & BOTTOM TRACK
|  | B | 2020-09-14: 3rd Pass Layout Bottom Track & Anchor
C | bar: 2020-06-01 to 2020-06-12
| Floor 6 | A | bar: 2020-06-08 to 2020-06-19
B | bar: 2020-06-15 to 2020-06-26
C | bar: 2020-06-22 to 2020-07-03
| Floor 7 | A | bar: 2020-06-29 to 2020-07-10
B | bar: 2020-07-06 to 2020-07-17
C | bar: 2020-07-13 to 2020-07-24
| Floor 3 | A | bar: 2020-07-20 to 2020-07-31
B | bar: 2020-07-27 to 2020-08-07
C | bar: 2020-08-03 to 2020-08-14
| Floor 2 | A | bar: 2020-08-10 to 2020-08-21
B | bar: 2020-08-17 to 2020-08-28
|  |  | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 8 |  |  |  |  | 9 |  |  |  |  | 10 |  |  |  |  | 11 |  |  |  |  | 12 |  |  |  |  | 13 |  |  |  |  | 14 |  |  |  |  | 15 |  |  |  |  | 16 |  |  |  |  | 17 |  |  |  |  | 18 |  |  |  |  | 19 |  |  |  |  | 20 |  |  |  |  | 21 |  |  |  |  | 22 |  |  |  |  | 23 |  |  |  |  | 24 |  |  |  |  | 25 |  |  |  |  | 26 |  |  |  |  | 27 |  |  |  |  | 28 |  |  |  |  | 29 |  |  |  |  | 30 |  |  |  |  | 31 |  |  |  |  | 32 |  |  |  |  | 33 |  |  |  |  | 34 |  |  |  |  | 35 |  |  |  |  | 36 |  |  |  |  | 37 |  |  |  |  | 38 |  |  |  |  | 39 |  |  |  |  | 40 |  |  |  |  | 41 |  |  |  |  | 42 |  |  |  |  | 43 |  |  |  |  | 44 |  |  |  |  | 45 |  |  |  |  | 46 |  |  |  |  | 47 |  |  |  |  | 48 |  |  |  |  | 49 |  |  |  |  | 50 |  |  |  |  | 51 |  |  |  |  | 52 |  |  |  |  | 53 |  |  |  |  | 54 |  |  |  |  | 55 |  |  |  |  | 56 |  |  |  |  | 57 |  |  |  |  | 58 |  |  |  |  | 59
MODULAR WALL | Floor 4 | A | bar: 2020-01-28 to 2020-06-04
|  | B | 2020-12-02: MODULAR InWall Coordination with design team
|  | C | 2020-12-02: MODULAR Final InWall Coordination
|  | D | 2020-12-02: MODULAR Model Walk to Release PRODUCT
|  | E | 2020-12-02: MODULAR Shop Drawing release FOR CONSTRUCTION
|  | F | 2020-12-02: MODULAR Shop drawing review/approval
| Floor 5 | A | 2020-12-02: MODULAR FAB ORDER
|  | B | 2020-12-02: PRE-FAB BUFFER (SITE CONTROLLED)
|  | C | 2020-12-02: MODULAR FAB Lead Time (10 Days + 5 DAY TRANSPORT)
|  | D | 2020-12-02: SITE PREP FOR MASS DELIVERY
|  | E | 2020-12-02: Deliver MODULAR Material
|  | F | 2020-12-02: Stand Frames
| Floor 6 | A | 2020-12-02: All Modular Systems INSTALL
|  | B | 2020-12-02: T-bar Grids, Wires, Above ceiling Devices
|  | C | 2020-12-02: Floor Installation
D | bar: 2020-07-13 to 2020-07-14; 2020-07-22 to 2020-08-06
E | bar: 2020-07-15 to 2020-07-16; 2020-07-27 to 2020-08-11
F | bar: 2020-07-17 to 2020-07-20; 2020-07-30 to 2020-08-14
| Floor 7 | A | bar: 2020-03-24 to 2020-07-22; 2020-08-04 to 2020-08-19
B | bar: 2020-07-23 to 2020-07-24; 2020-08-07 to 2020-11-09
C | bar: 2020-07-27 to 2020-07-28; 2020-08-12 to 2020-11-09
D | bar: 2020-07-29 to 2020-07-30; 2020-08-17 to 2020-11-09
E | bar: 2020-07-31 to 2020-08-03; 2020-08-20 to 2020-11-09
F | bar: 2020-08-04 to 2020-08-05; 2020-08-25 to 2020-11-09
| Floor 3 | A | bar: 2020-04-07 to 2020-08-07; 2020-08-28 to 2020-09-14
B | bar: 2020-08-10 to 2020-08-11; 2020-09-02 to 2020-09-17
C | bar: 2020-08-12 to 2020-08-13; 2020-09-07 to 2020-09-22
D | bar: 2020-08-14 to 2020-08-17; 2020-09-10 to 2020-09-25
E | bar: 2020-08-18 to 2020-08-19; 2020-09-15 to 2020-09-30
F | bar: 2020-08-20 to 2020-08-21; 2020-09-18 to 2020-10-05
| Floor 2 | A | bar: 2020-05-06 to 2020-10-08
B | bar: 2020-09-24 to 2020-10-13
C | bar: 2020-09-29 to 2020-10-16
D | bar: 2020-10-02 to 2020-10-21
|  |  | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 8 |  |  |  |  | 9 |  |  |  |  | 10 |  |  |  |  | 11 |  |  |  |  | 12 |  |  |  |  | 13 |  |  |  |  | 14 |  |  |  |  | 15 |  |  |  |  | 16 |  |  |  |  | 17 |  |  |  |  | 18 |  |  |  |  | 19 |  |  |  |  | 20 |  |  |  |  | 21 |  |  |  |  | 22 |  |  |  |  | 23 |  |  |  |  | 24 |  |  |  |  | 25 |  |  |  |  | 26 |  |  |  |  | 27 |  |  |  |  | 28 |  |  |  |  | 29 |  |  |  |  | 30 |  |  |  |  | 31 |  |  |  |  | 32 |  |  |  |  | 33 |  |  |  |  | 34 |  |  |  |  | 35 |  |  |  |  | 36 |  |  |  |  | 37 |  |  |  |  | 38 |  |  |  |  | 39 |  |  |  |  | 40 |  |  |  |  | 41 |  |  |  |  | 42 |  |  |  |  | 43 |  |  |  |  | 44 |  |  |  |  | 45 |  |  |  |  | 46 |  |  |  |  | 47 |  |  |  |  | 48 |  |  |  |  | 49 |  |  |  |  | 50 |  |  |  |  | 51 |  |  |  |  | 52 |  |  |  |  | 53 |  |  |  |  | 54 |  |  |  |  | 55 |  |  |  |  | 56 |  |  |  |  | 57 |  |  |  |  | 58 |  |  |  |  | 59
POST-MODULAR INSTALL | Floor 4 | A | bar: 2020-06-05 to 2020-08-11
|  | B | 2020-12-22: Float
|  | C | 2020-12-22: Ceiling Rough-In/Install
| Floor 5 | A | 2020-12-22: Inspections
|  | B | 2020-12-22: Ceiling Tiles
|  | C | 2020-12-22: Doors/Door hardware
| Floor 6 | A | 2020-12-22: Millwork
|  | B | 2020-12-22: Base flooring, counter tops, electrical trim
C | bar: 2020-08-21 to 2020-10-06
| Floor 7 | A | bar: 2020-08-28 to 2020-10-13
B | bar: 2020-09-04 to 2020-10-20
C | bar: 2020-09-11 to 2020-10-27
| Floor 3 | A | bar: 2020-09-18 to 2020-11-03
B | bar: 2020-09-25 to 2020-11-10
C | bar: 2020-10-02 to 2020-11-17
| Floor 2 | A | bar: 2020-10-09 to 2020-11-24
B | bar: 2020-10-16 to 2020-12-01
Air/Water Balancing | bar: 2020-11-17 to 2020-12-07
FA Pre-Test | bar: 2020-11-24 to 2020-12-14
Final Testing and Inspections (City Sign off) | bar: 2020-12-01 to 2020-12-30
Cx | bar: 2020-12-01 to 2020-12-30
Move In & Staff/Stock | bar: 2020-12-17 to 2021-01-14
End Construction | bar: 2021-01-21
First Patient 2/10/21 | bar: 2021-02-07
First Patient 2/10/21