Date: February 16, 2022  
Subject: Value Statement  
Project: Clark Arena Project  
Prepared by: Clark Construction in conjunction with Owner Team   
\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

The following items need to be included in your Site Logistics plan:

* Gates – vehicular and personnel
* Trucking Haul Routes
* Five (5) Tower Cranes –locations, radii, Heights above ground level (AGL)
* Material Storage / Laydown Area
* Dewatering Tank
* Trailers

Logistics items to resolve with the neighborhood

* Nearby hospital with roof helipad – how will you ensure cranes and equipment will not affect operation?
* Student Housing – how will you communicate with students such that early morning and late night noise cause by construction will not create issues?
* Adjacent construction sites – How will you ensure their tower cranes and construction operations do not impact your own?
* Nearby Baseball stadium – Afternoon games during the season will impact traffic around the neighborhood. What will you do to ensure this is properly communicated and coordinated?