**Date:** 1/22/23

**Job:** NER Dock 10/11 Project

**Quote #** 412

**Price:** See below

Hank’s Directional Drilling is pleased to provide pricing for your upcoming project:

Provide all labor, material, equipment, and tooling to complete the horizontal directional drill scope per contract documents: approx. 2,733 LF of drilling for a 12-inch pipeline

Pricing Breakdown

 Drill and install approximately 2,733 12” pipeline $400/ft

 Mobilization/Demobilization $25,000 ea.

Schedule based upon working a 6x10’s schedule Monday – Saturday. Estimated days to complete from start of mobilization is 40 days. Pull-back duration is 2 days.

Quotation Terms:

1. Proposal includes:
	1. All submittals per requirements of contract documents
	2. Drilling rig(s), drill cab(s) and power unit(s)
	3. Mud pumping units
	4. Vacuum and dump trucks
	5. Tool Containers
	6. Gyro steering tool system & tracer wire.
	7. Provide all in-hole tooling required to complete the project
	8. Provide pipe rollers and rolling cradles for pull back
	9. Provide and install surface casing
	10. Provide all labor required for drill operations
	11. Provide pull head
2. Proposal excludes:
	1. All permitting
	2. Locating of entry and exit locations
	3. Potholing existing utilities
	4. Permanent pipeline, welding, and test of the pipe
	5. Equipment and manpower to handle the pipeline during pullback
	6. All traffic control measures
	7. All SWPPP plan engineering, execution and maintenance
3. All work stoppages that arise through no fault to Hank’s Directional Drilling, will be billed at $25,000 per calendar day (no crew onsite).