## Sub Bid Evaluation Sheet
DPR Sub Bid Evaluation Sheet
Item No. | Scope of Work | Subcontractor Company Name | Risk Identification | Risk Mitigation Plan
EXAMPLE #1 | Roofing | Jim's Roofing Company | Roofer has excluded hoisting material to the roof. | We have added money into DPR's Site Requirements for DPR labor and equipment to Hoist Roofing material to roof.
EXAMPLE #2 | Rebar | BNW Rebar | In BNW's clarifications, they claim they will only handle material 1 time ie. they will place rebar in a location at the time of delivery, then will pick up the rebar when the job is complete. We think that BNW will need to move material multiple times for logistical purposes. We think this material will obstruct other subcontractors from getting equipment and material into the building. | We have added additional money in the "Cost to Complete" budget so that DPR can pay BNW via change order each time DPR needs BNW to relocate material.