ASC 2018 – Project Management

Instructions and Timeline

Introduction – 2/8/18

Your team will act as members of DPR Construction; determining if you will take the deal set forth by your client.  You are empowered to make key contractual, business and logistical decisions.  The decisions your team makes will have significant consequences and will impact the success of your project.  The strategy that you choose will map the road ahead, but may also expose you to possible roadblocks.  You are expected to adapt to situations, engineer solutions, demonstrate DPR’s Core Values, and deliver a project decision while maintaining raving fans.

DPR is responding to a Request for Proposal for the University of Southern California Norris Healthcare Center Project.  DPR is still determining if the project is one in which we want to pursue.  Your selection on whether or not to take the project is based upon your team decision about the client’s contract, schedule and budget requirements; while maintaining a great relationship.

USC been a great client of DPR in the past. We have built several projects for them over the past few decades and would like to continue the relationship as long as the deal is fair, equitable, and profitable.

USC believes in delivering healthcare centers that impact their community but also represent their image as a leading private research university.  USC’s Health Sciences campus houses renowned specialized care and research in cancer, stem cell and regenerative medicine, orthopedics and sports medicine.  USC is looking to expand their healthcare facilities and in doing so they are asking DPR to help with construction of the new USC NHC facility.

List of Project Modules:

The final team score will be a composite of the following:

| 20 Points | Contract Risk Assessment Module |
| --- | --- |
| 20 Points | Logistics + Schedule Modules |
| 20 Points | MEP Equipment Module |
| 30 Points | General Conditions (GC’s) + Schedule of Values (SOV) Module + Self-Perform Work |
| 20 Points | All Scenarios + Red-Zone “Go/No-Go” + Mini Presentation |
| 30 Points | Final Presentation |
| 140 Points | Total Points |

Schedule:

THURSDAY, 2/8/18

| Time | Activity | Activity is DUE |
| --- | --- | --- |
| 6:00 AM | Initial Presentation at Redwood 2 Room. |  |
| 7:00 AM | Students Receive INITIAL PROJECT INFORMATION. |  |
| 10:00 AM | GC’s, SPW, and SOV Module Explanation – Only (2) Students per Team come down to Redwood 2 Room for Presentation. Students should bring questions about these modules and DPR execs can answer. |  |
| 2:00 PM – 4:00 PM | Mini-Presentations - Information for this activity will be provided to you by email sometime during the day. |  |
| 5:00 PM |  | Contract Risk Assessment Module is DUE. |
| 5:00 PM | Logistics Module - Only (2) Students per Team come down to Redwood 2 Room for Logistics Module Presentation. This will be a new module which students did not receive at 7 AM. |  |
| 8:00 PM |  | - GC Module is DUE. - SPW Module is DUE. - SOV Module is DUE. - Schedule Module is DUE. - MEP Equipment Module is DUE. |
| 10:00 PM |  | - Logistics Module is DUE - Red Zone “Go/No-Go” is DUE. |

FRIDAY, 2/9/18

| 7:00 AM | Presentation Times will be posted at Redwood 2 Room. | All Presentation Materials are DUE to Redwood 2 Room. |
| --- | --- | --- |
| 8:00 AM – 4:00 PM | Team Presentations at Redwood 2 Room |  |
| 5:00 PM | Problem Recap at Redwood 2 Room |  |
| 6:00 PM – 7:00 PM | Student Info Session – Hang out and talk to DPR at Redwood 2 Room. |  |

- Contract Risk Assessment Module

During this module, your team will evaluate the (2) contract documents provided.  Use the Owner Contract Evaluation Tool Form as a tool to dive deep into each contract and learn the positives and negatives of each.  Then Fill out the Contract Comparison document to finalize your analysis and help lead you toward your contract selection.  You can find detailed instructions in the module section of your binder and usb.

Deliverable:

Your Team will turn in the following items for this module by usb to DPR’s hotel room.

- (2) Completed Owner Contract Evaluation Tool Forms

- (1) Completed Contract Comparison Document

- Logistics Module

It is crucial that all parties who are traveling through and nearby a construction project clearly understand how to travel safely.  If this information is unclear, this could put people at risk of injury or worse.

During this module, your team will provide multiple logistics-related deliverables.  You will receive a detailed logistics module instruction sheet which will explain in detail what you will need to do.

This module is NOT provided in your initial package.  This module will be provided to you later in the day as per the schedule on page 2 of this document.

Deliverable:

This information will be explained to you when you receive the module.

Your Team will turn in this module by usb to DPR’s hotel room.

- Schedule Module

Project schedules are like the backbone of a project.  They explain how a project will flow and detail the sequence of the work.  A schedule is also used to help the construction management team prioritize their management activities.  By understanding when activities are taking place, and what activities are predecessors and successors, a project engineer can prioritize their workload to make sure the field team receives the information they need before the work starts.

During this module, your team will create a Line Item schedule in Smartsheet.  Your team has been provided milestones and activities.  Use what is given to you but also add additional milestones and

activities to create the complete schedule.  You can find detailed instructions in the module section of your binder and usb.

Deliverable:

Your Team will turn in the following items for this module by usb to DPR’s hotel room.

- (1) Smartsheet schedule as a pdf document.

- (1) Questionnaire filled out

- MEP Equipment Module

As a construction manager, we need to understand what the design is and if we think it works.  When we receive design documents, it is our job to review and validate the design before the work starts.  We do constructability reviews to help guide our owners and designers to create understandable and achievable construction documents.

During this module, your team will confirm if the design documents accurately depict the required MEP systems which are required for each piece of equipment.

Follow the “How to..” document to help you determine if all systems have been included in the design.

Deliverable:

Your Team will turn in the following items for this module by usb to DPR’s hotel room.

- (1) MEP Equipment Constructability Review

- General Conditions (GC’s)

General Conditions are the costs to manage the project.  This includes but is not limited to management staffing labor, field offices, equipment, safety, internet, vehicles, food/water, power, printers, etc.  It is important for project managers to compile the costs for these items before a project starts so that you can get them into your budget.  Imagine if your owner approved your costs for the job but you forgot to include a superintendent, or you forgot internet!  Then your fee would have to cover those items!

In this module you will create your GC’s for the project.  Think hard about what you will need or don’t need!  You need to make sure you have everything you project requires and nothing more.  You don’t want to forget anything, but you also don’t want to be the person who prices yourself out of a job!

(Deliverable info on next page)

Deliverable:

Your Team will turn in the following items for this module by usb to DPR’s hotel room.

- (1) GC document in both pdf and excel formats.

- Self-Performed Work (SPW) Module

Self-Performed Work provides a lot of benefits to both us and our owners.  In this module you will review plans and specs, complete a take-off, and provide a cost of a self-performed work item.

Deliverable:

Your Team will turn in the following items for this module by usb to DPR’s hotel room.

- (1) Concrete Estimate

- (1) Critical Thinking

- Schedule of Values (SOV) Module

Schedule of Values is where you will buy out your subcontractors.  It is DPRs job to scrutinize the scope and the pricing of all our subcontractors.

Deliverable:

Your Team will turn in the following items for this module by usb to DPR’s hotel room.

- All Completed bid tallies in pdf and excel formats.

- (1) Completed SOV in both pdf and excel formats.

- Scenarios

The construction industry is a fast-paced and exciting industry.  Generally, we construction managers are juggling many items at the same time.  During the day your team will be sent emails with instructions for deliverables which will be due the same day.  Make sure you respond to these emails in a professional and clear way.  Your DPR executives expect you to perform at a high level and provide timely responses!

Deliverable:

Your Team will turn in your responses to Scenarios by email.

- Red-Zone “Go/No-Go”

Ah, the most exciting question of the day.  After you have built the many modules of the day, you have a great understanding of the risks that the project creates.  So should DPR take the job or not?  Read through the instructions in detail to provide a detailed response for this answer.

Deliverable:

Your Team will turn in the following items for this module by usb to DPR’s hotel room.

- (1) Response to the RedZone “Go/No-Go” email.

- Mini Presentation

Sometimes email or phone communications are restrictive.  It is hard to ask questions back-and-forth in a timely manner over email and phone calls don’t allow you to read people’s body language.  Even Facetime can’t beat a face-to-face meeting.  Sometime during the day we will ask members of your team to come down to Redwood 2 room and present to your DPR executives.  The content that you will present will be explained to you sometime during the day.

- Final Presentation

The presentation will be structured as an internal DPR meeting held to discuss the risks of the project.  Every member of your team must present.  Teams will present their final risk assessments, budget and schedule for the project with a brief recap of how they arrived at those results.  The presentation should cover your overall strategy including how the team was structured to accomplish the decision on whether or not to pursue this project.  This meeting will also be a forum to present and review risk allowing us an opportunity to share how we might improve for future projects.

Typical Presentation Outline:

- Setup - 5 minutes

- Team Presentation - 20 minutes

- Question and Answer - 10 minutes

- Breakdown - 5 minute

7:00 am:  All presentation materials are due.  Any handouts or electronic files produced after this time cannot be utilized during the presentation.  Please also return all specifications, drawings and USB Modems at this time.

7:00 am:  Presentation times will be posted in Redwood 2.

8:00 am – 4:00 pm:  Team Presentations

- Problem Requirements

Information can be directed to your team in numerous ways.  Any questions from your team to the problem sponsor’s team should be transmitted via email.

Physical copies will only be provided for a limited number of the project documents, and if the internet isn’t working.  All documents will be provided in electronic format.  Most deliverables are submitted via usb to DPR’s hotel room.  Don’t be late!   Give yourself enough time to get from your room to DPR’s hotel room!  If you are late to submit, even by a few seconds, you will be given 0 points for that module.

Email Address

During the course of the competition you will be communicating with the sponsor’s team through this email address:

| DPR Executive Team; dpr.asc2018@gmail.com. |  |  |  |
| --- | --- | --- | --- |

Problem Material

Upon completion of the Initial Presentation your team will be provided with the following materials:

- Project Turnover Binder

- USB

- Room Signs

- DPR Survival Kit

Project Information

A real project was utilized to create this problem; however the problem’s components are fictitious.  The architect, client, and all parties associated to the project have generously granted us permission to utilize the project for the benefit of this educational experience.  We insist that their generosity not be taken for granted.  Under no circumstances should your team make contact with the client, architect or any representatives of the project.

During the course of the problem if any instructional questions arise please address them to the email above.