**Build a Schedule**

**Instructions:**

* Start date is Monday, October 8, 2018
* Owner wants to be 100% moved in & operational by end of Summer, 2021
* Sequence and include the below milestones in your schedule – Add any other milestones you see necessary
* Schedules need to be at least 200 different line items (I.E. L2 overhead MEP & L3 overhead MEP are not 2 different line items, so they count as 1).
* We are grading based on *quality* not *quantity* of line items in your schedule
* This schedule should be built using the information found on the plans provided. Understand the type of structure this is and what elements go into the building to develop a *project specific* schedule.
* **Please turn in your schedule by printing to PDF!**
  + Use “Smartsheet” to build your schedule, see the attached instructions for how to access and use the program.
  + The following columns are to be shown in your PDF:
    - Activity Names
    - Durations
    - Start & Finish Dates
    - Activity Bars

Milestones:

* Steam System Tie In Complete
* Remove Manhoist
* Skin System Complete
* Start TI’s
* Basement Walls Complete
* TI Permit
* Set Roof Mechanical Equipment
* Structural Steel Material Release
* Commissioning Starts
* Complete Shoring
* Elevator Fabrication Released
* Complete SOMD Pours
* Substantial Completion
* Install Manhoist
* Elevator Inspections
* TAB Report
* Start Curtainwall System
* Erect Structural Steel
* Release AHUs
* Pneumatic Tube Deferred Submittal Approved
* Tunnel to Adjacent Building Complete
* Core & Shell Permit
* Steel Topping Out
* Utility Tie In Complete