## Instructions
1. Only edit GREEN cells (few exceptions, see below)
Manpower/General Conditions
1. Type in the hourly rate value and the percentage they will be on the job.
2. If an employee is on the job for less than the whole project, you may delete the formulas of the cells that do not apply to when they are on the job.
3. Labor burden is the cost, above and beyond the salary of the employee, to employ that person. This covers things like insurance, overhead, taxes, etc.
4. The default duration is for the employee to be on the job the duration of the project.
5. Ask questions if you have them. There are not supposed to be any traps in this spreadsheet.
General Requirements
1. Fill in any item costs you wish to use and type the value in the cell when you want to apply the cost.
2. Type the cost per month in the corresponding column for every month that applies to the item.
Exterior Masonry Estimate
1. Break out the line items and use your best judgement for cost.
2. Cost is an insignificant criteria. Quantities will carry the bulk of the points.
3. Be detailed and thorough
4. If you include a waste factor, please list the percentage (%).
Bid Tabs
1. Fill out the scope and the values that correspond.
2. Type the selected bidder and their value in the summary page on the corresponding cells.

## Summary
| Trade | Selected Subcontractor | Cost
03.0000 | Turnkey Concrete | Layton Construction | 0 | Cost auto fills from Self-perform tab
03.3700 | Polished/Stained Concrete Finishes | Subcontractor | 14829
04.0000 | Masonry & Stone | TYPE SELECTED SUB HERE | 0 | Type total value here
05.0000 | Steel | TYPE SELECTED SUB HERE | 0 | Type total value here
05.7000 | Ornamental Metals Fabrication | Subcontractor | 95048
05.8000 | Fireproofing | Subcontractor | 83983
06.4000 | Millwork | Subcontractor | 1788914
07.1000 | Waterproofing & Joint Sealants | Subcontractor | 93711.03
07.2000 | Insulation | TYPE SELECTED SUB HERE | 0 | Type total value here
07.4200 | Metal Panels | Subcontractor | 711105
07.4600 | Wood Panels/Siding | Subcontractor | 363871
07.5000 | Roofing | Subcontractor | 499110.11
08.1000 | Frames, Doors, Hardware | Subcontractor | 1412983
08.3300 | Coiling & Overhead Doors | Subcontractor | 23108
08.4000 | Glass | Subcontractor | 1879315
09.0000 | Interior Finishes | Subcontractor | 174477
09.2200 | Drywall | Subcontractor | 2252335
09.2300 | Plastering | Subcontractor | 671231
09.2500 | Specialty Plastering | Not In Contract | 0
09.3000 | Tile | Subcontractor | 1699918
09.5000 | Ceilings | Subcontractor | 9800
09.6000 | Flooring | Subcontractor | 848955.5
09.6600 | Terrazzo | Not In Contract | 0
09.6700 | Fluid-Applied Flooring | Cubcontractor | 10684
09.9000 | Painting & Wall Coverings | Subcontractor | 227660
10.0000 | Specialties | Developer Finish Selection Allowance | 224285
10.1400 | Signage | Developer Sign Allowance | 20362
10.3000 | Fireplaces | Custom Spec. | 349360
11.3000 | Residential Appliances | Developer Finish Selection Allowance | 432896
11.4000 | Food Service Equipment | Not In Contract | 0
12.0000 | Furnishings | Not In Contract | 0
12.2000 | Window Treatments | Subcontractor | 80000
12.9300 | Site Furnishings | Not In Contract | 0
13.1100 | Swimming Pools | Not In Contract | 0
13.1200 | Water Features | Not In Contract | 0
14.1000 | Dumbwaiter Systems | Not In Contract | 0
14.2000 | Elevators | Subcontractor | 633586.2
14.4200 | Wheelchair Lifts | Not In Contract | 0
14.9100 | Chute Systems | Subcontractor | 31657
21.0000 | Fire Suppression Systems | Subcontractor | 260000
22.0000 | Plumbing | Subcontractor | 4026881
23.0000 | HVAC | Subcontractor | 0
26.0000 | Electrical | Subcontractor | 2198473
27.4000 | Audio-Video Systems | Not In Contract | 0
28.0000 | Security Systems | Allowance | 87239
31.1000 | Earthwork | Subcontractor | 254818.91
32.1300 | Site Concrete | Subcontractor | 52242
32.1400 | Pavers | Not In Contract | 0
32.1700 | Striping & Signing | Subcontractor | 35500
32.3100 | Fence & Gates | Not In Contract | 0
32.3700 | Site Structures | Not In Contract | 0
32.8000 | Landscaping & Irrigation | Subcontractor | 18750
33.0000 | Site Utilities | Subcontractor | 295663
| SubTotal |  | 21862750.75
| General Conditions/Manpower | 0.1698% | 37192.5 | Autofill from Manpower-GC's tab
| General Requirements | 0.001027% | 225 | Autofill from GR tab
|  |  | 0 | Fill out this row if you need it
|  |  | 0 | Fill out this row if you need it
|  |  | 0 | Fill out this row if you need it
|  |  | 0 | Fill out this row if you need it
|  |  | 0 | Fill out this row if you need it
|  |  | 0 | Fill out this row if you need it
| Grand Total |  | 21900168.25

## Manpower-GC's
Please be prepared to talk about your selection and duration reasoning. | [5 empty] | 1.00 is none | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Project Team Name | [5 empty] | 2.00 is double | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | TOTAL
General Conditions |  |  | % | Onsite | HOURLY | BURDEN | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | COST
| ITEM |  | Assigned | Y/N | RATE | RATE | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | FORECAST
| PROJECT STAFF | NAME
EXAMPLE | Chief Boss Person | Tyran Rex | 75% |  | 10 | 1.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 37192.5
| STAFF TITLE HERE |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STAFF TITLE HERE |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STAFF TITLE HERE |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STAFF TITLE HERE |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STAFF TITLE HERE |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STAFF TITLE HERE |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STAFF TITLE HERE |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STAFF TITLE HERE |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STAFF TITLE HERE |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STAFF TITLE HERE |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STAFF TITLE HERE |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STAFF TITLE HERE |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STAFF TITLE HERE |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STAFF TITLE HERE |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STAFF TITLE HERE |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STAFF TITLE HERE |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STAFF TITLE HERE |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STAFF TITLE HERE |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STAFF TITLE HERE |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STAFF TITLE HERE |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STAFF TITLE HERE |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STAFF TITLE HERE |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PROJECT STAFF | [5 empty] | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 1957.5 | 37192.5

## GR's
|  |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Project Team Name |  |  | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | COST IN | TOTAL
General Requirements |  | HOURLY | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | COST
| ITEM | RATE | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | FORECAST
TEMPORARY FACILITIES
| EXAMPLE -- Fax Machine -- |  | 0 | 0 | 0 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 225
| Mobilization | [20 empty] | 0
| Demobilization | [20 empty] | 0
| Tool Trailer | [20 empty] | 0
| Job Site Office | [20 empty] | 0
| Office Equipment / Furniture | [20 empty] | 0
| Computer / Phone / Ipad / Technology | [20 empty] | 0
| Office Supplies | [20 empty] | 0
| Plans & Specs | [20 empty] | 0
| Drinking Water | [20 empty] | 0
| Postage | [20 empty] | 0
| Temporary Power | [20 empty] | 0
| Temp. Internet Infrastructure Setup | [20 empty] | 0
| Temp. Data Wiring Setup | [20 empty] | 0
| Trailer Water | [20 empty] | 0
| Temp. Water Setup | [20 empty] | 0
| Temporary Toilets | [20 empty] | 0
| Fuel, Oil, Maintenance | [20 empty] | 0
| Stair Towers / Access | [20 empty] | 0
| Water Truck | [20 empty] | 0
| Forklift / Water Truck | [20 empty] | 0
| Radios | [20 empty] | 0
| Misc Tool | [20 empty] | 0
| Project Sign | [20 empty] | 0
| Security Services | [20 empty] | 0
| Temporary Fencing (Materials / Labor) | [20 empty] | 0
| Traffic Control - Personel | [20 empty] | 0
| Vector Mapping (Cost of Work) | [20 empty] | 0
| Periodic Cleanup | [20 empty] | 0
| Dumpster Fees | [20 empty] | 0
| Travel | [20 empty] | 0
| Relocation | [20 empty] | 0
| Subsistence | [20 empty] | 0
| Employee Parking / Bus | [20 empty] | 0
| Weather Protection / Temporary Heat | [20 empty] | 0
| Safety Materials & Labor | [20 empty] | 0
| Edge Protection | [20 empty] | 0
| Gravel Sidewalks | [20 empty] | 0
| Vehicle | [20 empty] | 0
| Vehicle Fuel | [20 empty] | 0
| Vehicle maintenance | [20 empty] | 0
| Lunch room / Gathering | [20 empty] | 0
| Subcontractor Appreciation | [20 empty] | 0
| Utility Vehicle | [20 empty] | 0
| Accounting | [20 empty] | 0
Preconstruction
| TEMPORARY FACILITIES |  | 0 | 0 | 0 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 225

## Exterior Masonry Takeoff
Line Items | Qty | Unit | Cost | Total
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Grand Total |  |  | 0

## 04.00 Masonry
Scope Items | Sub 1 | Sub 2 | Sub 3 | Sub 4 | Sub 5 | Sub 6
Total Cost | 0 | 0 | 0 | 0 | 0 | 0

## 05.10 Steel
Scope Items | Sub 1 | Sub 2 | Sub 3 | Sub 4 | Sub 5 | Sub 6
Total | 0 | 0 | 0 | 0 | 0 | 0

## 07.20 Insulation
Scope Items | Sub 1 | Sub 2 | Sub 3 | Sub 4 | Sub 5 | Sub 6
Total | 0 | 0 | 0 | 0 | 0 | 0

## Sheet1 (hidden)
GOTCHA!!!