## STAFFING SOLUTION
UCI IRVINE BREN HALL
STAFFING MATRIX
NTP
| 2007 | 2007-02-18 | [11 empty] | 2008 | [11 empty] | 2009
Position | JAN | FEB |  | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY |  | JUN | JUL | Total
|  | 1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 |  | 29 | 30 | Months
Project Manager |  |  | 1 | [27 empty] | . |  |  | 27 | bar: MAR 2 to 2009 APR 27
Estimator (Desgin & Subcontracting) | [33 empty] | 8 | bar: MAY 4 to DEC 11
Project Superintendent |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | [7 empty] | 24
Area Superintendent | [33 empty] | 18 | bar: OCT 9 to 2009 MAR 26
Project Engineer |  |  | 1 | [30 empty] | 27 | bar: MAR 2 to 2009 APR 27
Office Engineer #1 |  |  | 1 | [30 empty] | 27 | bar: MAR 2 to 2009 APR 27
Office Engineer #2 | [33 empty] | 24 | bar: MAY 4 to 2009 APR 27
Field Engineer #1 | [33 empty] | 23 | bar: APR 3 to 2009 FEB 25
Field Engineer #2 | [33 empty] | 18 | bar: NOV 10 to 2009 APR 27
Intern | [33 empty] | 6 | bar: JUN 5 to AUG 7; 2008 JUN 17 to 2008 AUG 19
Secretary | [33 empty] | 26 | bar: MAR 2 to 2009 APR 27
228

## GC SOLUTION
LastCol
GENERAL CONDITIONS
| ITEM |  | QTY | UNIT | MATERIAL |  | EQUIP./SUBS. |  | LABOR |  | TOTAL
[5 empty] | $/UNIT | AMOUNT | $/UNIT | AMOUNT | $/UNIT | AMOUNT
SUPERVISION & ADMINISTRATION
|  | PROJECT MANAGER | 27 | MO | -- | 0 | -- | 0 | 12000 | 324000 | 324000
|  | PROJECT SUPERINTENDENT | 24 | MO | -- | 0 | -- | 0 | 12000 | 288000 | 288000
|  | PROJECT ENGINEER | 27 | MO | -- | 0 | -- | 0 | 10000 | 270000 | 270000
|  | OFFICE ENGINEER #1 | 27 | MO | -- | 0 | -- | 0 | 8500 | 229500 | 229500
|  | OFFICE ENGINEER #2 | 24 | MO | -- | 0 | -- | 0 | 8500 | 204000 | 204000
|  | SECRETARY | 26 | MO | -- | 0 | -- | 0 | 5500 | 143000 | 143000
|  | PROJECT ESTIMATOR | 8 | MO | -- | 0 | -- | 0 | 11000 | 88000 | 88000
|  | TRAVEL & MEALS | 20 | MO | 475 | 9500 | -- | 0 | -- | 0 | 9500
|  | SALARY MEDICAL (HEALTH INSURANCE) | 228 | MO | -- | 0 | 850 | 193800 | -- | 0 | 193800
|  | TOTAL SUPERVISION & ADMINISTRATION |  |  |  | 9500 |  | 193800 |  | 1546500 | 1749800 | GOOD
ENGINEERING & SURVEY WORK
|  | AREA SUPERINTENDENT #1 | 18 | MO | -- | 0 | -- | 0 | 11000 | 198000 | 198000
| C | AREA SUPERINTENDENT #2 (IN CONCRETE) |  |  | -- | 0 | -- | 0 | -- | 0 | 0
|  | FIELD ENGINEER #1 | 23 | MO | -- | 0 | -- | 0 | 7500 | 172500 | 172500
|  | FIELD ENGINEER #2 | 18 | MO | -- | 0 | -- | 0 | 7500 | 135000 | 135000
| C | FIELD ENGINEER #3 (IN CONCRETE) |  |  | -- | 0 | -- | 0 | -- | 0 | 0
|  | INTERN ENGINEER | 6 | MO | -- | 0 | -- | 0 | 3200 | 19200 | 19200
|  | INTERN ENGINEER HOUSING | 6 | MO | 1000 | 6000 | -- | 0 | -- | 0 | 6000
| C | FIELD ENGINEERING EQUIPMENT (IN CONCRETE) |  |  | -- | 0 | -- | 0 | -- | 0 | 0
| C | SURVEY RODMAN |  |  | -- | 0 | -- | 0 | -- | 0 | 0
|  | PROFESSIONAL SURVEYOR | 1 | LSUM | -- | 0 | 10000 | 10000 | -- | 0 | 10000
|  | DRAFTSMAN - DETAILERS | 1 | LSUM | -- | 0 | 2300 | 2300 | -- | 0 | 2300
|  | ADDITIONAL PLANS | 350 | SET | 200 | 70000 | -- | 0 | -- | 0 | 70000
|  | CONSTRUCTION DRAWING PRINTING | 1 | LSUM | 10000 | 10000 | -- | 0 | -- | 0 | 10000
|  | AS-BUILT PRINTING | 10 | SET | -- | 0 | -- | 0 | -- | 0 | 0
|  | O & M MANUALS | 10 | SET | 250 | 2500 | -- | 0 | -- | 0 | 2500
|  | TOTAL ENGINEERING & SURVEY WORK |  |  |  | 86000 |  | 12300 |  | 524700 | 623000 | GOOD
SAFETY & FIRST AID
|  | PRE-EMPLOYMENT SCREENING (DRUG TESTING) | 12 | EACH | 175 | 2100 | -- | 0 | -- | 0 | 2100
|  | FIRST AID SUPPLIES | 1 | LSUM | 5000 | 5000 | -- | 0 | -- | 0 | 5000
|  | FIRE PROTECTION | 1 | LSUM | 5000 | 5000 | -- | 0 | -- | 0 | 5000
|  | BACK RAILS | 3600 | LF | 1.5 | 5400 | -- | 0 | 1.5 | 5400 | 10800
|  | HORIZONTAL OPENING PROTECTION | 2500 | SF | 1.5 | 3750 | -- | 0 | 2 | 5000 | 8750
|  | TOTAL SAFETY & FIRST AID |  |  |  | 21250 |  | 0 |  | 10400 | 31650 | GOOD
TEMPORARY FACILITIES
|  | OFFICE TRAILER 24'x60' | 26 | MO | -- | 0 | 2000 | 52000 | -- | 0 | 52000
|  | OFFICE TRAILER 12'x60' | 26 | MO | -- | 0 | 1500 | 39000 | -- | 0 | 39000
| C | FIELD TRAILER 10'x30' (IN CONCRETE) |  |  | -- | 0 | -- | 0 | -- | 0 | 0
|  | OWNER / ENGINEER TRAILER 10'x30' | 26 | MO | -- | 0 | 500 | 13000 | -- | 0 | 13000
|  | SETUP & REMOVE TRAILERS | 4 | EACH | -- | 0 | 3500 | 14000 | -- | 0 | 14000
|  | CONEX | 18 | MO | -- | 0 | 250 | 4500 | -- | 0 | 4500
| C | CONEX |  |  | -- | 0 | -- | 0 | -- | 0 | 0
|  | TEMPORARY TOILETS | 432 | WK | -- | 0 | 75 | 32400 | -- | 0 | 32400
|  | WASH STATIONS | 216 | WK | -- | 0 | 50 | 10800 | -- | 0 | 10800
|  | PROFESSIONAL PHOTOGRAPHS | 1 | LSUM | -- | 0 | 1200 | 1200 | -- | 0 | 1200
|  | DIGITAL CAMERA/SOFTWARE | 1 | LSUM | 750 | 750 | -- | 0 | -- | 0 | 750
|  | PRECONSTRUCTION PHOTO SURVEY | 1 | LSUM | 3000 | 3000 | -- | 0 | -- | 0 | 3000
|  | BULLETIN BOARDS | 1 | EACH | 1000 | 1000 | -- | 0 | -- | 0 | 1000
|  | PROJECT SIGN | 1 | EACH | 1000 | 1000 | -- | 0 | -- | 0 | 1000
|  | OFFICE SUPPLIES | 26 | MO | 750 | 19500 | -- | 0 | -- | 0 | 19500
|  | COPY MACHINE | 26 | MO | -- | 0 | 650 | 16900 | -- | 0 | 16900
|  | FAX MACHINE | 1 | EACH | 1500 | 1500 | -- | 0 | -- | 0 | 1500
|  | COMPUTERS | 3 | EACH | 2500 | 7500 | -- | 0 | -- | 0 | 7500
|  | PRINTERS | 1 | EACH | 1500 | 1500 | -- | 0 | -- | 0 | 1500
|  | OFFICE NETWORK EXPENSE | 1 | LSUM | 750 | 750 | 750 | 750 | -- | 0 | 1500
|  | ADDITIONAL SOFTWARE | 1 | LSUM | 2000 | 2000 | -- | 0 | -- | 0 | 2000
|  | PRIMAVERA SOFTWARE | 1 | LSUM | 2000 | 2000 | -- | 0 | -- | 0 | 2000
|  | PROLOG SOFTWARE | 1 | EACH | 2500 | 2500 | 25 | 25 | -- | 0 | 2525
|  | OFFICE SUPPLIES - O/A/E | 1 | LSUM | 2500 | 2500 | -- | 0 | -- | 0 | 2500
|  | POSTAGE & SHIPPING | 26 | MO | 500 | 13000 | -- | 0 | -- | 0 | 13000
|  | TELEPHONE SERVICE | 26 | MO | 1200 | 31200 | -- | 0 | -- | 0 | 31200
|  | TELEPHONE EQUIPMENT RENTAL | 1 | LSUM | -- | 0 | 2500 | 2500 | -- | 0 | 2500
|  | CELLULAR PHONE CHARGES | 96 | MO | 350 | 33600 | -- | 0 | -- | 0 | 33600
|  | TEMPORARY FENCING | 1 | LSUM | 10000 | 10000 | -- | 0 | -- | 0 | 10000
|  | DRINKING WATER/COFFEE | 26 | MO | 100 | 2600 | -- | 0 | -- | 0 | 2600
|  | TEMP. WATER USAGE | 26 | MO | 200 | 5200 | -- | 0 | -- | 0 | 5200
|  | TEMP. POWER USAGE FOR OFFICE TRAILER | 26 | MO | 350 | 9100 | -- | 0 | -- | 0 | 9100
|  | TEMP. POWER USAGE | 22 | MO | 1600 | 35200 | -- | 0 | -- | 0 | 35200
|  | STREET SWEEPER | 27 | MO | -- | 0 | 2000 | 54000 | -- | 0 | 54000
| C | FIELD WATER/ICE/CUPS |  |  | -- | 0 | -- | 0 | -- | 0 | 0
|  | FIELD WATER/ICE/CUPS | 26 | MO | 150 | 3900 | -- | 0 | -- | 0 | 3900
|  | TOTAL TEMPORARY FACILITIES |  |  |  | 189300 |  | 241075 |  | 0 | 430375 | GOOD
BUILDING SERVICES & CLEAN-UP
|  | WEEKLY CLEAN-UP | 80 | WEEK | 35 | 2800 | -- | 0 | 500 | 40000 | 42800
|  | DUMPSTER RENTAL | 100 | DUMP | -- | 0 | 400 | 40000 | -- | 0 | 40000
|  | JANITORIAL SERVICES | 104 | WEEK | -- | 0 | 50 | 5200 | -- | 0 | 5200
|  | FINAL CLEAN-UP BLDG | 125000 | SQ. FT | -- | 0 | 0.25 | 31250 | -- | 0 | 31250
|  | TOTAL BUILDING SERVICES & CLEAN-UP |  |  |  | 2800 |  | 76450 |  | 40000 | 119250 | GOOD
EQUIPMENT & TRANSPORTATION
|  | **FORKLIFTS** |  |  | -- | 0 | -- | 0 | -- | 0 | 0
|  | FORKLIFT | 14 | MO | 2700 | 37800 | -- | 0 | -- | 0 | 37800
| C | FORKLIFT (WHAREHOUSE) |  |  | -- | 0 | -- | 0 | -- | 0 | 0
|  | **AUTOMOBILES & PICKUPS** |  |  | -- | 0 | -- | 0 | -- | 0 | 0
|  | PICKUP | 42 | MO | 350 | 14700 | 550 | 23100 | -- | 0 | 37800
|  | SEDAN | 27 | MO | 250 | 6750 | 650 | 17550 | -- | 0 | 24300
|  | **CRANES** |  |  | -- | 0 | -- | 0 | -- | 0 | 0
| C | CRANE |  |  | -- | 0 | -- | 0 | -- | 0 | 0
|  | **GENERATORS & COMPRESSORS** |  |  | -- | 0 | -- | 0 | -- | 0 | 0
| C | COMPRESSOR (IN CONCRETE) |  |  | -- | 0 | -- | 0 | -- | 0 | 0
|  | **MISC. EQUIPMENT** |  |  | -- | 0 | -- | 0 | -- | 0 | 0
|  | RADIOS & BASE STATION | 1 | LSUM | 2500 | 2500 | -- | 0 | -- | 0 | 2500
| C | SMALL TOOLS (SMALL TOOLS) |  |  | -- | 0 | -- | 0 | -- | 0 | 0
|  | TOTAL EQUIPMENT & TRANSPORTATION |  |  |  | 61750 |  | 40650 |  | 0 | 102400 | GOOD
SUMMARY
|  | SUPERVISION & ADMINISTRATION | --- | LS | --- | 9500 | --- | 193800 | --- | 1546500 | 1749800
|  | ENGINEERING & SURVEY WORK | --- | LS | --- | 86000 | --- | 12300 | --- | 524700 | 623000
|  | SAFETY & FIRST AID | --- | LS | --- | 21250 | --- | 0 | --- | 10400 | 31650
|  | TEMPORARY FACILITIES | --- | LS | --- | 189300 | --- | 241075 | --- | 0 | 430375
|  | BUILDING SERVICES & CLEAN-UP | --- | LS | --- | 2800 | --- | 76450 | --- | 40000 | 119250
|  | EQUIPMENT & TRANSPORTATION | --- | LS | --- | 61750 | --- | 40650 | --- | 0 | 102400
|  | TOTAL GENERAL CONDITIONS |  |  |  | 370600 |  | 564275 |  | 2121600 | 3056475 | GOOD

## EARLY TURNOVER SOLUTION
EARLY TURNOVER ANALYSIS
[6 empty] | 2008-11-01 |  | Saturday's |  | 2008-12-01 |  | Saturday's |  | 2009-01-01 |  | Saturday's
Company: | Trade: | Man Count | Rate: | OT | Delta | 18 | MH's | 4 | MH's | 22 | MH's | 4 | MH's | 21 | MH's | 5 | MH's
Hensel Phelps Cons. Co. | Superintendant | 1 |  |  |  | 11000 |  |  |  | 11000 |  |  |  | 11000
Electrical | Electrician | 16 | 48.97 | 66.07 | 17.1 | 9849.6 | 14400 | 547.2 | 512 | 12038.4 | 14400 | 547.2 | 512 | 11491.2 | 14400 | 684 | 512
Plumbing | Plumbing | 4 | 44.44 | 59.85 | 15.41 | 2219.04 | 3600 | 493.12 | 128 | 2712.16 | 3600 | 493.12 | 128 | 2588.88 | 3600 | 616.4 | 128
Drywall/Framing | Metal Framing/Drywall | 8 | 40.7 | 56.56 | 15.86 | 4567.68 | 7200 | 507.52 | 256 | 5582.72 | 7200 | 507.52 | 256 | 5328.96 | 7200 | 634.4 | 256
Structural Steel | Structural/Misc. Steel | 5 | 47.67 | 61.98 | 14.31 | 2575.8 | 4500 | 457.92 | 160 | 3148.2 | 4500 | 457.92 | 160 | 3005.1 | 4500 | 572.4 | 160
HVAC | HVAC | 7 | 48.06 | 64.95 | 16.89 | 4256.28 | 6300 | 540.48 | 224 | 5202.12 | 6300 | 540.48 | 224 | 4965.66 | 6300 | 675.6 | 224
Masonry | Masonry | 1 | 40.45 | 52.95 | 12.5 | 450 | 900 | 400 | 32 | 550 | 900 | 400 | 32 | 525 | 900 | 500 | 32
Glazing | Exterior Glazing | 6 | 43.29 | 58.89 | 15.6 | 3369.6 | 5400 | 499.2 | 192 | 4118.4 | 5400 | 499.2 | 192 | 3931.2 | 5400 | 624 | 192
Acoustical Ceiling | Acoustical Ceiling | 5 | 52.49 | 73.9 | 21.41 | 3853.8 | 4500 | 685.12 | 160 | 4710.2 | 4500 | 685.12 | 160 | 4496.1 | 4500 | 856.4 | 160
Flooring | Flooring | 4 | 28.41 | 39.17 | 10.76 | 1549.44 | 3600 | 344.32 | 128 | 1893.76 | 3600 | 344.32 | 128 | 1807.68 | 3600 | 430.4 | 128
Painting | Paint | 8 | 34.58 | 47.92 | 13.34 | 3841.92 | 7200 | 426.88 | 256 | 4695.68 | 7200 | 426.88 | 256 | 4482.24 | 7200 | 533.6 | 256
Doors & Hardware | Doors & Hardware | 5 | 49.54 | 74.32 | 24.78 | 4460.4 | 4500 | 792.96 | 160 | 5451.6 | 4500 | 792.96 | 160 | 5203.8 | 4500 | 991.2 | 160
Casework | Millwork | 3 | 40.97 | 57.08 | 16.11 | 1739.88 | 2700 | 515.52 | 96 | 2126.52 | 2700 | 515.52 | 96 | 2029.86 | 2700 | 644.4 | 96
[5 empty] | TOTALS: | 53733.44 |  | 6210.24 |  | 63229.76 |  | 6210.24 |  | 60855.68 |  | 7762.8
[5 empty] | TOTAL MH'S: |  | 64800 |  | 2304 |  | 64800 |  | 2304 |  | 64800 |  | 2304
[5 empty] | TOTAL COST SUBS: |  | 198002.16 |  | AVG. RATE: | 43.2975
[5 empty] | TOTAL MH'S ACCRUED: |  |  | 201312 | AVG. PRODUCTION EFFICIENCY: | 75%
[5 empty] | FEE 5%: |  | 9900.108 |  | MH'S LOST DUE TO OT: | 50328
[5 empty] | TOTAL COST SUBS: |  | 207902.268 |  | ADDITIONAL COST: | 2179076.58
[9 empty] | ADDITIONAL FEE (5%): | 108953.829
[9 empty] | TOTAL COST SUBS: | 2288030.409
SUPERVISION & ADMINISTRATION
PROJECT MANAGER | 3 | MO | -- | 0 | -- | 0 | 12000 | 36000 | 36000
PROJECT ENGINEER | 3 | MO | -- | 0 | -- | 0 | 10000 | 30000 | 30000
OFFICE ENGINEER #1 | 3 | MO | -- | 0 | -- | 0 | 8500 | 25500 | 25500
OFFICE ENGINEER #2 | 3 | MO | -- | 0 | -- | 0 | 8500 | 25500 | 25500
SECRETARY | 3 | MO | -- | 0 | -- | 0 | 5500 | 16500 | 16500
SALARY MEDICAL (HEALTH INSURANCE) | 22 | MO | -- | 0 | 850 | 18700 | -- | 0 | 18700
TOTAL SUPERVISION & ADMINISTRATION |  |  |  | 0 |  | 18700 |  | 133500 | 152200 | GOOD
ENGINEERING & SURVEY WORK
AREA SUPERINTENDENT #1 | 3 | MO | -- | 0 | -- | 0 | 11000 | 33000 | 33000
FIELD ENGINEER #1 | 3 | MO | -- | 0 | -- | 0 | 7500 | 22500 | 22500
FIELD ENGINEER #2 | 1 | MO | -- | 0 | -- | 0 | 7500 | 7500 | 7500
TOTAL ENGINEERING & SURVEY WORK |  |  |  | 0 |  | 0 |  | 63000 | 63000 | GOOD
TEMPORARY FACILITIES
OFFICE TRAILER 24'x60' | 3 | MO | -- | 0 | 2000 | 6000 | -- | 0 | 6000
OFFICE TRAILER 12'x60' | 3 | MO | -- | 0 | 1500 | 4500 | -- | 0 | 4500
OWNER / ENGINEER TRAILER 10'x30' | 3 | MO | -- | 0 | 500 | 1500 | -- | 0 | 1500
TEMPORARY TOILETS | 240 | MO | -- | 0 | 130 | 31200 | -- | 0 | 31200
WASH STATIONS | 120 | MO | -- | 0 | 100 | 12000 | -- | 0 | 12000
OFFICE SUPPLIES | 3 | MO | 750 | 2250 | -- | 0 | -- | 0 | 2250
COPY MACHINE | 3 | MO | -- | 0 | 650 | 1950 | -- | 0 | 1950
POSTAGE & SHIPPING | 3 | MO | 500 | 1500 | -- | 0 | -- | 0 | 1500
TELEPHONE SERVICE | 3 | MO | 1200 | 3600 | -- | 0 | -- | 0 | 3600
CELLULAR PHONE CHARGES | 9 | MO | 350 | 3150 | -- | 0 | -- | 0 | 3150
DRINKING WATER/COFFEE | 3 | MO | 100 | 300 | -- | 0 | -- | 0 | 300
TEMP. WATER USAGE | 3 | MO | 200 | 600 | -- | 0 | -- | 0 | 600
TEMP. POWER USAGE FOR OFFICE TRAILER | 3 | MO | 350 | 1050 | -- | 0 | -- | 0 | 1050
TEMP. POWER USAGE | 3 | MO | 1600 | 4800 | -- | 0 | -- | 0 | 4800
STREET SWEEPER | 3 | MO | -- | 0 | 2000 | 6000 | -- | 0 | 6000
FIELD WATER/ICE/CUPS | 3 | MO | 150 | 450 | -- | 0 | -- | 0 | 450
TOTAL TEMPORARY FACILITIES |  |  |  | 17700 |  | 63150 |  | 0 | 80850 | GOOD
BUILDING SERVICES & CLEAN-UP
JANITORIAL SERVICES | 12 | WEEK | -- | 0 | 50 | 600 | -- | 0 | 600
TOTAL BUILDING SERVICES & CLEAN-UP |  |  |  | 0 |  | 600 |  | 0 | 600 | GOOD
SUMMARY
EQUIPMENT & TRANSPORTATION
**AUTOMOBILES & PICKUPS** |  |  | -- | 0 | -- | 0 | -- | 0 | 0 |  | GC's savings |  |  | -302050
PICKUP | 3 | MO | 350 | 1050 | 550 | 1650 | -- | 0 | 2700 |  | Subcontractor Overtime |  |  | 207902.268
SEDAN | 3 | MO | 250 | 750 | 650 | 1950 | -- | 0 | 2700 |  | Subcontractor Efficiency |  |  | 2288030.409
TOTAL EQUIPMENT & TRANSPORTATION |  |  |  | 1800 |  | 3600 |  | 0 | 5400 | GOOD | Subtotal |  |  | 2193882.677
[11 empty] | Contractor Fee |  |  | 109694.1338
SUMMARY | [10 empty] | Total |  |  | 2303576.8109
SUPERVISION & ADMINISTRATION | --- | LS | --- | 0 | --- | 18700 | --- | 133500 | 152200
ENGINEERING & SURVEY WORK | --- | LS | --- | 0 | --- | 0 | --- | 63000 | 63000
TEMPORARY FACILITIES | --- | LS | --- | 17700 | --- | 63150 | --- | 0 | 80850
BUILDING SERVICES & CLEAN-UP | --- | LS | --- | 0 | --- | 600 | --- | 0 | 600
EQUIPMENT & TRANSPORTATION | --- | LS | --- | 1800 | --- | 3600 | --- | 0 | 5400
TOTAL GENERAL CONDITIONS |  |  |  | 19500 |  | 86050 |  | 196500 | 302050 | GOOD
CREDIT