Memo

UC Irvine, Bren Hall

Irvine, CA  92612

| to: | pROJECT ESTIMATOR |
| --- | --- |
| from: | rICHARD mCBRAYER, pROJECT SUPERINTENDANT |
| subject: | CREW SIZES |
| date: | 10/17/08 |
| cc: |  |

Estimating department:

I discussed the 3 month early turnover with the University, and they have confirmed that we can work 2 hours extra during the workweek, and 8 hours on Saturday’s to achieve the early completion.  Those hours will be billed as overtime hours.  That being said, I am providing you with the manpower of the project as of today.  These crew sizes will remain the same for the remaining of the project; however, beginning October 24, 2008, we will begin longer workdays and implement Saturday work to complete the project by January 31, 2009.  I also recommend one additional superintendent be allocated to assist with multiple floor construction activities, longer hours, and Saturday’s to manage this accelerated schedule.  I have also attached historical production efficiency rates related to acceleration of schedule, i.e. working OT and Saturday’s.  Hope this helps.

Crew:

Electricians		16			Glazier’s	6

Plumbers		4			Acc. Ceiling	5

Framers/Drywall	8			Floor Layers	4

Iron Workers		5			Painters	8

HVAC			7			Door Guys	5

Mason’s		1			Millwork	3

Let me know if you have any questions.

Richard