| SUPERVISION & ADMINISTRATION |  |  |  |
| --- | --- | --- | --- |
| Project Manager | $12,000 | / | Month |
| Project Superintendent | $12,000 | / | Month |
| Project Estimator | $9,000 | / | Month |
| Project Engineer | $10,000 | / | Month |
| Office Engineer | $8,500 | / | Month |
| Office Manager | $5,500 | / | Month |
| Travel Expenses | $700 | / | Month |
| Health Insurance for Salary Staff* | $900 | / | Month / person |
| Moving & Relocation | $5,000 | / | Each |
| ENGINEERING & SURVEY |  |  |  |
| Field Engineer | $7,500 | / | Month |
| Intern Engineer* | $4,800 | / | Month |
| Intern Housing | $1,500 | / | Month |
| FE Equipment** | $350 | / | Month |
| Professional Surveyor | $30,000 |  | Lump sum |
| Sub Bid Packages | $300 | / | Each |
| Plans for owner | $300 | / | Each |
| Additional plans | $500 | / | Set |
| Construction drawing printing | $10,000 |  | Lump sum |
| As-built printing | $10,000 |  | Lump sum |
| O&M Manuals | $500 | / | Set |
| SAFETY |  |  |  |
| Drug testing | $200 | / | Each |
| Safety Incentives | $250 | / | Each |
| Employee training | $100 | / | Each |
| First Aid supplies | $200 | / | Each |
| Fire Extinguishers (1 per 5k SF) | $55 | / | Each |
| TEMPORARY FACILITIES |  |  |  |
| Office Trailer 24x60 | $850 | / | Month |
| Office Trailer 12x60 | $475 | / | Month |
| Setup & Remove Trailer | $1,500 | / | Each |
| Temp toilets | $95 | / | Month |
| Wash Stations | $90 | / | Month |
| Photos | $600 | / | Month |
| Digital Camera/Software | $2,000 | / | Lump sum |
| Preconstruction photo survey | $1,000 | / | Lump sum |
| Bulletin Boards | $400 | / | Each |
| Project Sign** | $1,000 | / | Lump sum |

| TEMPORARY FACILITIES (cont.) |  |  |  |
| --- | --- | --- | --- |
| Office Supplies | $925 | / | Month |
| Copy machine (w/ service contract)** | $700 | / | Month |
| Fax machine | $1,000 | / | Each |
| Computers | $2,300 | / | Each |
| Printers | $500 | / | Each |
| Office Network** | $3,750 | / | Lump sum |
| Office software | $925 | / | Each |
| Primavera Software/Maintenance | $25,000 | / | Lump sum |
| Prolog Software | $8,500 | / | Lump sum |
| Postage & Shipping | $400 | / | Month |
| Telephone Service | $2,000 | / | Lump service |
| Telephone equipment rental | $1,050 | / | Month |
| Cell phone charges | $150 | / | Month / phone |
| Temp fencing | $10 | / | Linear foot |
| Drinking water/Coffee | $200 | / | Month |
| Temp water usage | $200 | / | Month |
| Temp power – Office usage** | $350 | / | Month |
| Temp power – Jobsite usage** | $9,500 | / | Month |
| Street sweeper | $1,000 | / | Each sweep |
| Field Water/Ice/Cups** | $400 | / | Month |
| BUILDING SERVICES |  |  |  |
| Weekly Cleanup (2mandays/week)** | $1,280 | / | Week |
| Dumpster rental | $450 | / | Pull |
| Final Building cleaning (int & ext) | $0.45 | / | SF |
| EQUIPMENT & TRANSPORTATION |  |  |  |
| Forklift Rental** | $3,200 | / | Month |
| Super’s Pickup | $900 | / | Month |
| PM’s Sedan | $900 | / | Month |
| Crane usage | $5,000 | / | Month |
| Compressor** | $1,010 | / | Month |
| Radios | $750 | / | Each |
| Small Tools | $1,200 | / | Month |
| *Health Insurance does not apply to Interns. |  |  |  |
| ** These items have a flat unit price which is comprised of any combination of labor, materials and/or Equipment / Subcontracted items. As described in the problem statement, use all available resources, experience & judgement to determine how this unit price should break-down and reflect this accordingly on your General conditions budget. |  |  |  |