## EXAMPLE
11
PROPOSAL
|  |  | SUMMARY |  | STONE |  | (EXAMPLE)
PROJECT | ***SAMPLE PROJECT*** |  |  |  | Lorton |  | Espina |  | Atlantic Refinish |  | Boatman |  | PCC |  | AFCO Steel |  | Schuff Steel Company
|  |  |  | SCOPE | LORTON VA |  | FAIRFAX VA |  |  |  | CAPITOL HTS MD |  | Gaithersburg, MD |  | Little Rock, Arkansas |  | Phoenix, Arizona
|  |  |  | DESIRED | 703-550-9755 |  | 703-560-1018 |  | 301-843-8331 |  | 301-336-7700 |  | 301-417-1020 |  | 501.340.6300 |  | 602.252.7787
[5 empty] | MANUEL SEARA |  | FERNANDO |  | ALEX |  | GLEN ROBERTS |  | CHARLIE OCONNER |  | Ira Stone |  | Harold Strojan
SEC. | DESCRIPTION |  | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL
| BID AMOUNT |  | ----- | ------ |  | 2998000 |  | 2726000 |  | 2484000 |  | 2988000 |  |  |  | 7068007 |  | 14630000
| Bondable/Rate |  | Y | a | Y / 1.25% | a | NO | CAN'T BOND | Y / 2% | a | Y / 1.44% | a | Y / 1.25% | a
| Bond Included |  | NO | W/GC | NO | OK | NO | OK | NO | OK | Y | -43000 | NO | OK
| Sales Tax - 5% |  | Y | a | Y | a | Y | a | Y | a | Y | a | Y | a
| Addenda 1, 2, 3 |  | Y | a | NO | 1 & 2 only | Y | a | Y | a | Y | a | Y | a
01454 | Mock Up Requirements |  | Y | a | Y | a | Y | a | Y | a | Y | a | Y | a
02517 | Stone Paving |  | Y | a | Y | a | Y | a | Y | a | Y | a | NO
04450 | Stone Veneer |  | Y | a | Y | a | Y | a | Y | a | Y | a |  | 1620000
3.1 | Stone @ entry wall planters |  | Y | a | Y | a | Y | a | Y | a | Y | a | NO
<6k> | Stone @ pond outfall |  | NO | W/UTIL | Y | -8000 | Y | -6000 | NO | OK | NO | OK | NO | OK
| Column covers |  | Y | a | Y | a | Y | a | Y | a | Y | a | Y | a
19k | Rigid insulation @ your work |  | Y | a | NO | 19000 | Y | a | NO | 19000 | NO | 19000 | Y | a
09380 | Natural Stone Flooring |  | Y | a | Y | a | Y | a | Y | a | Y | a | NO
2.01 | Supplier Carrera Marble or Equal |  | Y | a | Y | a | Y | a | Y | a | Y | a | NO
3.1 | Granite flooring |  | Y | a | Y | a | Y | a | Y | a | Y | a | NO
3.2 | Slate floors, walls, base |  | Y | a | Y | a | Y | a | Y | a | Y | a | NO
| Vanities & countertops |  | Y | a | Y | a | Y | a | Y | a | Y | a | NO
| Sills |  | Y | a | Y | a | Y | a | Y | a | Y | a | NO
| Grout as required |  | Y | a | Y | a | Y | a | Y | a | Y | a | Y | a
| Stone to stone caulk only |  | Y | a | NO | 42000 | NO | 10000 | Y | a | Y | a | Y | a
15k | Flashing as required |  | Y | a | NO | 15000 | NO | 10000 | NO | 15000 | NO | 15000 | NO | 15000
| Stone @ food service A/5-44 |  | Y | a | Y | a | Y | a | Y | a | Y | a | NO
3.6 | Metal Trim at Stone Transitions |  | Y | a | Y | a | Y | a | Y | a | Y | a | NO
4.1 | Stone Sealer |  | Y | a | Y | a | Y | a | Y | a | Y | a | NO
|  | Sub Total |  | 0 |  | 3066000 |  | 2740000 |  | 2518000 |  | 2979000 | INCOMPLETE |  |  | 7068007 |  | 14630000
CAN'T BOND

## TILE
16
PROPOSAL
|  |  | SUMMARY |  | 09310 - CERAMIC TILE
PROJECT | City of San Jose Central Service Yard
| San Jose, CA |  |  | SCOPE
DESIRED
SEC. | DESCRIPTION |  | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL
| Bid Amount |  | ----- | ------
| Bondable / Rate |  | Y | a
| Bond Included |  | N | W/ GC
| Sales Tax @ 8.25 |  | Y | a
| Addenda |  | Y | a
| LEED Credit or spec'd materials |  | Y | a
09300 | Ceramic Tile (Walls & Floors) |  | ----- | ------
| Tile Patterns |  | Y | a
| Joint Sealants applicable to tile scope |  | Y | a
| Waterproofing Floors |  | Y | a
| Waterproof walls |  | Y | a
| Tape Cement board |  | Y | a
| Thresholds & Transition Strips |  | Y | a
| Marble Thresholds |  | Y | a
| Mud set all tile and slope to drain |  | Y | a
| Shower walls (Full HT) |  | Y | a
| Attic Stock |  | Y | a
|  | Sub Total |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total

## REINFORCING
5
PROPOSAL
|  |  | SUMMARY |  | 03200 - CONCRETE REINFORCING
PROJECT | City of San Jose Central Service Yard
| San Jose, CA |  |  | SCOPE
DESIRED
SEC. | DESCRIPTION |  | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL
Bid Amount
| Bondable / Rate |  | Y | a
| Bond Included |  | N | W/ GC
| Addenda |  |  | N/A
| Sales Tax @ 8.25 |  | Y | a
03200 | Reinforcing Steel |  | ----- | ------
| Building F |  | Y | a
| Building G |  | Y | a
| Building H |  | Y | a
| Site Concrete |  | Y | a
04810 | Unit Masonry Reinforcing FOB |  | Y | a
| Detailing / Shop Dwgs |  | Y | a
| Hoisting |  | Y | a
| Installation |  | Y | a
| all rigging, bracing guys, etc.. To load, unload & install |  | Y | a
| a. Slab on Grade |  | Y | a
| b. Foundations |  | Y | a
| c. Continuous Foundations |  | Y | a
| d. Reinforcing dowels for CMU walls |  | Y | a
| e. Curb and Housekeeping pad dowels and reinforcing. |  | Y | a
| f. Smooth dowels as required. |  | Y | a
| Corrdinate w/ Inspector of record & QC Mgr |  | Y | a
| Corrdinate move-ins w/ CPM Schedule |  | Y | a
| Provide and remove dunnage |  | Y | a
| Weekly Housekeeping for own work |  | Y | a
|  | Sub Total |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0
Total

## FLOORING
18
PROPOSAL
|  |  | SUMMARY |  | 09650 - FLOORING
PROJECT | City of San Jose Central Service Yard
| San Jose, CA |  |  | SCOPE
DESIRED
SEC. | DESCRIPTION |  | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL
| Bid Amount |  | ----- | ------
| Bondable / Rate |  | Y | a
| Bond Included |  | N | W/ GC
| Sales Tax @ 8.25 |  | Y | a
| Addenda |  |  | N/A
09650 | Resilient Flooring |  | ----- | ------
| Linoleum |  | Y | a
| Rubber Floor w/ pattern |  | Y | a
| Rubber Base |  | Y | a
| Moisture Test |  | Y | a
| Minor Floor Prep |  | Y | a
| Vapor Emissions System |  | N | OK
| Attic Stock |  | Y | a
| Samples |  | Y | a
|  | Sub Total |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total

## MASONRY
6
PROPOSAL
|  |  | SUMMARY |  | 04200 - MASONRY
PROJECT | City of San Jose Central Service Yard
| San Jose, CA |  |  | SCOPE
DESIRED
SEC. | DESCRIPTION |  | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL
| Bid Amount |  | ----- | ------
| Bondable / Rate |  | Y | a
| Bond Included |  | N | W/GC
| Sales Tax @ 8.25 |  | Y | a
| Addenda |  |  | N/A
| Installation |  | Y | a
04200 | CMU Block - 8x8x16 gray smooth |  | ----- | ------ | ----- | ------ | ----- | ------ | ----- | ------ | ----- | ------ | ----- | ------
| Building F |  | Y | a
| Building G |  | Y | a
| Building H |  | Y | a
| LEED - Recycled Material (50%) |  | Y | a
| Install all Masonry Reinforcing |  | Y | a
| Provide Masonry Reinforcing |  | N | w/ Reinforcing
| Coordinate w/ MEP - penetrations |  | Y | a
| Control joints as specified |  | Y | a
| Bunkers 9, 10, & 11 |  | Y | a
| Hoisting |  | Y | a
| Grout as applies |  | Y | a
| Scaffolding |  | Y | a
| Clean up / House keeping |  | Y | a
| Caulking of expansion jnts |  | N | w/ sealants
| Set Door & Window Frames |  | N | w/ GC
| Drill & Epoxy Dowels |  | N | w/ Reinforcing
| Sealer |  | N | w/ paint
|  | Sub Total |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
Total

## METAL BUILDING
22
PROPOSAL
|  |  | SUMMARY |  | 131250 - PRE-ENGINEERED BUILDINGS
PROJECT | City of San Jose Central Service Yard
| San Jose, CA |  |  | SCOPE
DESIRED
SEC. | DESCRIPTION |  | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL
Bid Amount
| Bondable / Rate |  | Y | a
| Bond Included |  | NO | W/ GC
| Addenda |  | Y | a
| Sales Tax @ 8.25 |  | Y | a
| Bldg. F - 30,729 sf |  | Y | a
| Covered Parking - 15,800 sf |  | Y | a
| Bldg G - 31,140 sf |  | Y | a
| Bldg H - Vehicle Wash 5,440 sf |  | Y | a
| Galvanized steel members |  | Y | a
| Engineer/design - Cal. stamp |  | Y | a
| Roof - Standing seam (24 ga.) |  | Y | a
| Wall panels - 22 ga. |  | Y | a
| Roof insulation - R30 |  | Y | a
| Wall insulation - R19 |  | Y | a
| Gutters & Downspouts |  | Y | a
| Frame openings |  | Y | a
| Doors, frames, & Hardware |  | NO | w/door
| Roll up doors |  | NO | w/rollup
| Windows & glazing |  | NO | w/glazing
| Skylights w/ curb & flashing |  | Y | a
| Kynar Finish |  | Y | a
| Anchor bolts - F.O.B. |  | Y | a
| Primed structural steel |  | Y | a
| Sealant as applies |  | Y | a
| Fab lead time / Errection Start |  | 22 | weeks
|  | Sub Total |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total