## Staffing
City of San Jose, Central Service Yard
STAFFING MATRIX | [16 empty] | Notice to Proceed: | 2008-03-01
Time Extension Analysis
Year: | 2008 | [9 empty] | 2009
Month: | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
Month #: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | Totals
Project Manager | [18 empty] | 1 | 1 | 1 |  | 3
Estimator
Project Superintendent
Project Engineer | [18 empty] | 1 | 1 | 1 |  | 3
Office Engineer | [18 empty] | 1 | 1 | 1 |  | 3
Field Engineer #1
Field Engineer #2
Office Manager | [18 empty] | 1 | 1 | 1 |  | 3
Intern
12
[19 empty] | 4 | 4 | 4
[7 empty] | = | Existing Staff | [5 empty] | = | Extended Staffing per owner request

## GCs
City of San Jose, Central Service Yard
GENERAL CONDITIONS ESTIMATE |  |  |  |  | Time Extension Analysis
|  |  | Labor |  | Material |  | Equip/Subs
Item | QTY | UNIT | $/UNIT | AMT | $/UNIT | AMT | $/UNIT | AMT | Total
SUPERVISION
Project Manager | 3 | MO | 12000 | 36000 |  |  |  |  | 36000 | 243302 | -207302
Estimator | 0 | MO | 9000 | 0 |  |  |  |  | 0 | 47025 | -47025
Project Superintendent | 0 | MO | 12000 | 0 |  |  |  |  | 0 | 217134 | -217134
Project Engineer | 3 | MO | 10000 | 30000 |  |  |  |  | 30000 | 189954 | -159954
Office Engineer | 3 | MO | 8500 | 25500 |  |  |  |  | 25500 | 151938 | -126438
Office Manager | 0 | MO | 5500 | 0 |  |  |  |  | 0 | 116766 | -116766
Travel & Expenses | 0 | MO |  |  |  |  | 700 | 0 | 0 | 12330 | -12330
Salary Medical | 9 | MO |  |  |  |  | 900 | 8100 | 8100 | 0 | 8100
Moving & Relocation | 0 | EA |  |  |  |  | 5000 | 0 | 0 | 27000 | -27000
Total |  |  |  | 91500 |  | 0 |  | 8100 | 99600 | 1005449 | -905849
ENGINEERING & SURVEY WORK
Field Engineer #1 | 0 | MO | 7500 | 0 |  |  |  |  | 0 | 132288 | -132288
Field Engineer #2 | 0 | MO | 7500 | 0 |  |  |  |  | 0 | 107484 | -107484
Intern | 0 | MO | 4800 | 0 |  |  |  |  | 0 | 28475 | -28475
Intern Housing | 0 | MO | 1500 | 0 |  |  |  |  | 0 | 1200 | -1200
FE Equipment | 0 | MO | 100 | 0 |  |  | 250 | 0 | 0 | 5732 | -5732
Professional Surveyor | 0 | LSUM | 30000 | 0 |  |  |  |  | 0 | 30000 | -30000
Sub Bid Packages | 0 | EA |  |  |  |  | 300 | 0 | 0 | 18000 | -18000
Plans for Owner | 0 | EA |  |  |  |  | 300 | 0 | 0 | 18000 | -18000
Additional Plans | 0 | SET |  |  | 500 | 0 |  |  | 0 | 32475 | -32475
Construction Drawing Printing | 0 | LSUM |  |  | 10000 | 0 |  |  | 0 | 10825 | -10825
As-Built Printing | 0 | LSUM |  |  | 10000 | 0 |  |  | 0 | 10825 | -10825
O&M Manuals | 0 | SET |  |  | 500 | 0 |  |  | 0 | 1000 | -1000
Total |  |  |  | 0 |  | 0 |  | 0 | 0 | 396304 | -396304
SAFETY
Drug Testing | 0 | EA |  |  |  |  | 200 | 0 | 0 | 800 | -800
Employee Training/Incentives | 0 | EA |  |  | 250 | 0 | 100 | 0 | 0 | 6871 | -6871
First Aid Supplies | 1 | EA |  |  | 200 | 216.5 |  |  | 216.5 | 650 | -433.5
Fire Protection (1/5k SF) | 0 | EA |  |  | 55 | 0 |  |  | 0 | 2405 | -2405
Excav. Barricades | 0 | LF | 0.5 | 0 | 0.5 | 0 |  |  | 0 | 104 | -104
Total |  |  |  | 0 |  | 216.5 |  | 0 | 216.5 | 10830 | -10613.5
TEMP FACILITIES
Office Trailer 1 24x60 | 3 | MO |  |  |  |  | 850 | 2550 | 2550 | 15374 | -12824
Office Trailer 2 12x60 | 0 | MO |  |  |  |  | 475 | 0 | 0 | 8624 | -8624
Setup & Remove Trailers | 1 | EA |  |  |  |  | 1500 | 1500 | 1500 | 6099 | -4599
Temp Toilets | 0 | MO |  |  |  |  | 95 | 0 | 0 | 6840 | -6840
Wash Stations | 0 | MO |  |  |  |  | 90 | 0 | 0 | 6480 | -6480
Photos | 0 | MO |  |  |  |  | 600 | 0 | 0 | 10800 | -10800
Digital Camera | 0 | LSUM |  |  | 2000 | 0 |  |  | 0 | 2165 | -2165
Preconstuction Photo Surveys | 0 | LSUM |  |  |  |  | 1000 | 0 | 0 | 1000 | -1000
Bulletin Boards | 0 | EA |  |  | 800 | 0 |  |  | 0 | 1666 | -1666
Project Sign | 0 | EA | 200 | 0 | 800 | 0 |  |  | 0 | 1066 | -1066
Office Supplies - HPCC | 1.5 | MO |  |  | 925 | 1501.9688 |  |  | 1501.9688 | 18000 | -16498.0312
Copy Machine (incl. service) | 3 | MO |  |  | 300 | 974.25 | 400 | 1200 | 2174.25 | 13046 | -10871.75
Fax Machine | 0 | EA |  |  | 1000 | 0 |  |  | 0 | 1083 | -1083
Computers | 0 | EA |  |  | 2300 | 0 |  |  | 0 | 12449 | -12449
Printers | 0 | EA |  |  | 500 | 0 |  |  | 0 | 541 | -541
Office Network | 0 | LSUM |  |  | 750 | 0 | 3000 | 0 | 0 | 3812 | -3812
Office Software | 0 | LSUM |  |  | 925 | 0 |  |  | 0 | 5000 | -5000
Primavera Software/Maintenance | 0 | LSUM |  |  |  |  | 25000 | 0 | 0 | 23871 | -23871
Prolog Software | 0 | EA |  |  |  |  | 8500 | 0 | 0 | 0 | 0
Postage & Shipping | 1.5 | MO |  |  |  |  | 400 | 600 | 600 | 7200 | -6600
Telephone Service | 0 | LSUM |  |  |  |  | 2000 | 0 | 0 | 2000 | -2000
Telephone Equipment Rental | 3 | MO |  |  |  |  | 1050 | 3150 | 3150 | 18900 | -15750
Cell Phone Charges | 6 | MO |  |  |  |  | 150 | 900 | 900 | 13500 | -12600
Temp Fence | 0 | LF |  |  |  |  | 10 | 0 | 0 | 9400 | -9400
Drinking Water/Coffee | 3 | MO |  |  | 200 | 649.5 |  |  | 649.5 | 3674 | -3024.5
Temp Water Usage | 3 | MO |  |  |  |  | 200 | 600 | 600 | 3600 | -3000
Temp Power - Office Usage | 3 | MO |  |  | 200 | 649.5 | 150 | 450 | 1099.5 | 3897 | -2797.5
Temp Power - Project | 0 | MO |  |  | 1000 | 0 | 8500 | 0 | 0 | 142730 | -142730
Street Sweeper | 0 | EA |  |  |  |  | 1000 | 0 | 0 | 6000 | -6000
Field Water/Ice/Cups | 0 | MO | 200 | 0 | 200 | 0 |  |  | 0 | 7497 | -7497
Total |  |  |  | 0 |  | 3775.2188 |  | 10950 | 14725.2188 | 356314 | -341588.7812
BUILDING SERVICES
Weekly Cleanup (2mandays/wk) | 0 | WK | 1200 | 0 | 70 | 0 | 10 | 0 | 0 | 83525 | -83525
Dumpster Rental | 1 | PULLS |  |  |  |  | 450 | 450 | 450 | 29250 | -28800
Final Building Cleaning (Int & Ext) | 5000 | SF |  |  |  |  | 0.45 | 2250 | 2250 | 29500 | -27250
Total |  |  |  | 0 |  | 0 |  | 2700 | 2700 | 142275 | -139575
EQUIPMENT & TRANSPORTATION
Forklift | 0 | MO |  |  | 700 | 0 | 2500 | 0 | 0 | 9773 | -9773
Pickup | 0 | MO |  |  |  |  | 900 | 0 | 0 | 0 | 0
Sedan | 3 | MO |  |  |  |  | 900 | 2700 | 2700 | 0 | 2700
Cranes | 0 | MO |  |  |  |  | 5000 | 0 | 0 | 30000 | -30000
Compressor | 0 | MO |  |  | 600 | 0 | 410 | 0 | 0 | 6357 | -6357
Radios | 0 | EA |  |  | 750 | 0 |  |  | 0 | 6495 | -6495
Small Tools | 0 | MO |  |  | 1200 | 0 |  |  | 0 | 20000 | -20000
Total |  |  |  | 0 |  | 0 |  | 2700 | 2700 | 72625 | -69925
SUMMARY
SUPERVISION |  | LSUM |  | 91500 |  | 0 |  | 8100 | 99600 | 1005449 | -905849
ENGINEERING & SURVEY WORK |  | LSUM |  | 0 |  | 0 |  | 0 | 0 | 396304 | -396304
SAFETY |  | LSUM |  | 0 |  | 216.5 |  | 0 | 216.5 | 10830 | -10613.5
TEMP FACILITIES |  | LSUM |  | 0 |  | 3775.2188 |  | 10950 | 14725.2188 | 356314 | -341588.7812
BUILDING SERVICES |  | LSUM |  | 0 |  | 0 |  | 2700 | 2700 | 142275 | -139575
EQUIPMENT & TRANSPORTATION |  | LSUM |  | 0 |  | 0 |  | 2700 | 2700 | 72625 | -69925
TOTAL |  |  |  | 91500 |  | 3991.7188 |  | 24450 | 119941.7188
|  |  |  | 274500 |  | 11975.1562 |  | 73350 | 359825.1562 | 1983797 | -1863855.2812
|  |  |  | 1298549 |  | 286035 |  | 444030 | 2052211
|  |  |  | -1024049 |  | -274059.8438 |  | -370680 | -1692385.8438