## TILE
16
PROPOSAL
|  |  | SUMMARY |  | 09310 - CERAMIC TILE
PROJECT | City of San Jose Central Service Yard |  |  |  | Formula 1 Tile |  | Venice Tile |  | BM Tile Co
| San Jose, CA |  |  | SCOPE | Oakland, CA |  | San Jose, CA |  | San Francisco, CA
|  |  |  | DESIRED | (510) 565-4300 |  | (408) 882-4565 |  | (415) 842-9200
[5 empty] | Mike Dretti |  | Jeff Bourdee |  | Alfred Wayne
SEC. | DESCRIPTION |  | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL
| Bid Amount |  | ----- | ------ |  | 182000 |  | 186000 |  | 192000
| Bondable / Rate |  | Y | a |  | Can't Bond | Y | 1.05% | Y | 1.75%
| Bond Included |  | N | W/ GC | N | OK | Y | -2000 | N | OK
| Sales Tax @ 8.25 |  | Y | a | Y | a | Y | a | Y | a
| Addenda |  |  | N/A |  | N/A |  | N/A |  | N/A
| LEED Credit or spec'd materials |  | Y | a | Y | a | Y | a | Y | a
09300 | Ceramic Tile (Walls & Floors) |  | ----- | ------ | ----- | ------ | ----- | ------ | ----- | ------
| Tile Patterns |  | Y | a | Y | a | Y | a | Y | a
| Joint Sealants applicable to tile scope |  | Y | a | Y | a | Y | a | Y | a
| Waterproofing Floors |  | Y | a | Y | a | Y | a | Y | a
| Waterproof walls |  | Y | a | Y | a | Y | a | Y | a
| Tape Cement board |  | Y | a | Y | a | Y | a | Y | a
| Thresholds & Transition Strips |  | Y | a | Y | a | Y | a | Y | a
| Marble Thresholds |  | Y | a | N | 4000 | N | 5000 | N | 5000
| Mud set all tile and slope to drain |  | Y | a | Y | a | Y | a | Y | a
| Shower walls (Full HT) |  | Y | a | Y | a | Y | a | Y | a
| Attic Stock |  | Y | a | Y | a | Y | a | Y | a
|  | Sub Total |  | 0 |  | 186000 |  | 189000.0105 |  | 197000.0175 |  | 0 |  | 0
Total

## REINFORCING
5
PROPOSAL
|  |  | SUMMARY |  | 03200 - CONCRETE REINFORCING
PROJECT | City of San Jose Central Service Yard |  |  |  | Harv's Discount Rebar |  | Best At Reinforcing |  | SMS Fabricators, Inc.
| San Jose, CA |  |  | SCOPE | Dublin, CA |  | Santa Rosa, CA |  | Metropolis, CA
|  |  |  | DESIRED | (925) 555-0733 |  | (707) 555-2333 |  | (559) 292-6764
[5 empty] | Harv Bar |  | Rean Forest |  | Lex Toothor
SEC. | DESCRIPTION |  | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL
| Bid Amount |  |  |  |  | 369000 |  | 312000 |  | 274000
| Bondable / Rate |  | Y | a | Y | 1.75% | Y | 1.5% | Y | 1.2%
| Bond Included |  | N | W/ GC | N | OK | N | OK | N | OK
| Addenda |  |  | N/A |  | N/A |  | N/A |  | N/A
| Sales Tax @ 8.25 |  | Y | a | Y | a | Y | a | Y | a
03200 | Reinforcing Steel |  | ----- | ------ | ----- | ------ | ----- | ------ | ----- | ------
| Building F |  | Y | a | Y | a | Y | a | Y | a
| Building G |  | Y | a | Y | a | Y | a | Y | a
| Building H |  | Y | a | Y | a | Y | a | Y | a
| Site Concrete |  | Y | a | Y | a | Y | a | Y | a
04810 | Unit Masonry Reinforcing FOB |  | Y | a | Y | a | N | 15000 | Y | a
| Detailing / Shop Dwgs |  | Y | a | Y | a | Y | a | Y | a
| Hoisting |  | Y | a | Y | a | Y | a | N | 30000
| Installation |  | Y | a | Y | a | Y | a | Y | a
| all rigging, bracing guys, etc.. To load, unload & install |  | Y | a | Y | a | Y | a | N | 5000
| a. Slab on Grade |  | Y | a | Y | a | Y | a | Y | a
| b. Foundations |  | Y | a | Y | a | Y | a | Y | a
| c. Continuous Foundations |  | Y | a | Y | a | Y | a | Y | a
| d. Reinforcing dowels for CMU walls |  | Y | a | Y | a | Y | a | Y | a
| e. Curb and Housekeeping pad dowels and reinforcing. |  | Y | a | Y | a | Y | a | Y | a
| f. Smooth dowels as required. |  | Y | a | N | 2000 | Y | a | N | 3000
| Corrdinate w/ Inspector of record & QC Mgr |  | Y | a | Y | a | Y | a | Y | a
| Corrdinate move-ins w/ CPM Schedule |  | Y | a | Y | a | Y | a | Y | a
| Provide and remove dunnage |  | Y | a | Y | a | Y | a | Y | a
| Weekly Housekeeping for own work |  | Y | a | N | 5000 | Y | a | Y | a
|  | Sub Total |  |  |  | 376000.0175 |  | 327000.015 |  | 312000.012
Total

## FLOORING
18
PROPOSAL
|  |  | SUMMARY |  | 09650 - FLOORING
PROJECT | City of San Jose Central Service Yard |  |  |  | Bedrock Floor Cov |  | RE-NU Floor Cov |  | Flat Floors Flooring |  | TRIPLE "H" Flooring
| San Jose, CA |  |  | SCOPE | Bedrock, CA |  | Petaluma, CA |  | Santa Rosa, CA |  | Milpitas, CA
|  |  |  | DESIRED | (714) 548-1983 |  | (707) 555-4000 |  | (707) 555-2351 |  | (408) 648-1360
[5 empty] | George Slate |  | Ren Oldies |  | Ensal Ergo |  | Mike Myers
SEC. | DESCRIPTION |  | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL
| Bid Amount |  | ----- | ------ |  | 419000 |  | 412000 |  | 410000 |  | 425000
| Bondable / Rate |  | Y | a | Y | 1.65% | Y | 2.25% |  | N/A | Y | 1.01%
| Bond Included |  | N | W/ GC | Y | -7000 | N | OK |  | N/A | N | OK
| Sales Tax @ 8.25 |  | Y | a | Y | a | Y (7.75%) | 1000 |  | N/A | Y (8.25%) | a
| Addenda |  |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
09650 | Resilient Flooring |  | ----- | ------ | ----- | ------ | ----- | ------ | ----- | ------ | ----- | ------ | ----- | ------
| Linoleum |  | Y | a | Y | a | Y | a |  | N/A | Y | a
| Rubber Floor w/ pattern |  | Y | a | Y | a | Y | a |  | N/A | Y | a
| Rubber Base |  | Y | a | Y | a | Y | a |  | N/A | Y | a
| Moisture Test |  | Y | a | Y | a | Y | a |  | N/A | Y | a
| Minor Floor Prep |  | Y | a | Y | a | N | 5000 |  | N/A | Y | a
| Vapor Emissions System |  | N | OK | N | OK | N | OK |  | N/A | N | OK
| Attic Stock |  | Y | a | Y | a | Y | a |  | N/A | Y | a
| Samples |  | Y | a | Y | a | Y | a |  | N/A | Y | a
|  | Sub Total |  | 0 |  | 412000.0165 |  | 418000.0225 | Incomplete - |  |  | 425000.0101 |  | 0
Wrong Job
Total

## MASONRY
6
PROPOSAL
|  |  | SUMMARY |  | 04200 - MASONRY
PROJECT | City of San Jose Central Service Yard |  |  |  | WDB, INC. |  | Big Jimmy's Masonry |  | Apollo Masonry
| San Jose, CA |  |  | SCOPE | Pleasanton, CA |  |  |  | Orange , CA
|  |  |  | DESIRED | (925) 555-5576 |  | (714) 478-1717 |  | (714) 776-8100
[5 empty] | Ed Bloque |  | Jim Little |  | Cosmo Spacely
SEC. | DESCRIPTION |  | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL
| Bid Amount |  | ----- | ------ |  | 155000 |  | 130000 |  | 115000
| Bondable / Rate |  | Y | a | Y | 1.5% | Y | 1.55% | Y | 1.75%
| Bond Included |  | N | W/GC | N | OK | Y | -2000 | N | OK
| Sales Tax @ 8.25 |  | Y | a | Y | a | Y | a | N | 3000
| Addenda |  |  | N/A |  | N/A |  | N/A |  | N/A
| Installation |  | Y | a | Y | a | Y | a | Y | a
04200 | CMU Block - 8x8x16 gray smooth |  | ----- | ------ | ----- | ------ | ----- | ------ | ----- | ------ | ----- | ------ | ----- | ------
| Building F |  | Y | a | Y | a | Y | a | Y | a
| Building G |  | Y | a | Y | a | Y | a | Y | a
| Building H |  | Y | a | Y | a | Y | a | N
| LEED - Recycled Material (50%) |  | Y | a | Y | a | Y | a | Y | a
| Install all Masonry Reinforcing |  | Y | a | Y | a | Y | a | Y | a
| Provide Masonry Reinforcing |  | N | w/ Reinforcing | Y | -10000 | N | OK | N | OK
| Coordinate w/ MEP - penetrations |  | Y | a | Y | a | Y | a | Y | a
| Control joints as specified |  | Y | a | Y | a | Y | a | Y | a
| Bunkers 9, 10, & 11 |  | Y | a | Y | a | Y | a | Y | a
| Hoisting |  | Y | a | Y | a | Y | a | Y | a
| Grout as applies |  | Y | a | Y | a | Y | a | Y | a
| Scaffolding |  | Y | a | Y | a | Y | a | Y | a
| Clean up / House keeping |  | Y | a | Y | a | Y | a | Y | a
| Caulking of expansion jnts |  | N | w/ sealants | N | OK | N | OK | N | OK
| Set Door & Window Frames |  | N | w/ GC | N | OK | N | OK | N | OK
| Drill & Epoxy Dowels |  | N | w/ Reinforcing | N | OK | N | OK | N | OK
| Sealer |  | N | w/ paint | N | OK | N | OK | N | OK
|  | Sub Total |  | 0 |  | 145000.015 |  | 128000.0155 | INCOMPLETE
Did not bid Bldg. H
Total

## METAL BUILDING
22
PROPOSAL
|  |  | SUMMARY |  | 131250 - PRE-ENGINEERED BUILDINGS
PROJECT | City of San Jose Central Service Yard |  |  |  | BIBI |  | OBP Steel |  | CM Errectors
| San Jose, CA |  |  | SCOPE | Oakland, CA |  | Salem, OR |  | Stockton, CA
|  |  |  | DESIRED | (510) 555-0111 |  | (505) 739-6312 |  | (209) 394-3352
[5 empty] | Jack |  | Bob |  | Burt Sesame
SEC. | DESCRIPTION |  | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL | UNIT | TOTAL
| Bid Amount |  |  |  |  | 2673000 |  | 2305000 |  | 2692000
| Bondable / Rate |  | Y | a | Y | 1.25% | Y | 1.4% | Y | 1%
| Bond Included |  | N | W/ GC | N | OK | N | OK | N | OK
| Addenda |  | Y | a |  | N/A |  | N/A |  | N/A
| Sales Tax @ 8.25 |  | Y | a | 8.25% | a | N | 76000 | 8.25% | a
| Bldg. F - 30,729 sf |  | Y | a | Y | a | Y | a | Y | a
| Covered Parking - 15,800 sf |  | Y | a | Y | a | Y | a | Y | a
| Bldg G - 31,140 sf |  | Y | a | Y | a | Y | a | Y | a
| Bldg H - Vehicle Wash 5,440 sf |  | Y | a | Y | a | Y | a | Y | a
| Galvanized steel members |  | Y | a | Y | a | Y | a | Y | a
| Engineer/design - Cal. stamp |  | Y | a | Y | a | Y | a | Y | a
| Roof - Standing seam (24 ga.) |  | Y | a | Y | a | Y | a | Y | a
| Wall panels - 22 ga. |  | Y | a | Y | a | Y | a | Y | a
| Roof insulation - R30 |  | Y | a | Y | a | Y | a | Y | a
| Wall insulation - R19 |  | Y | a | Y | a | Y | a | Y | a
| Gutters & Downspouts |  | Y | a | Y | a | Y | a | Y | a
| Frame openings |  | Y | a | Y | a | Y | a | Y | a
| Doors, frames, & Hardware |  | N | w/door | N | OK | N | OK | N | OK
| Roll up doors |  | N | w/rollup | N | OK | N | OK | N | OK
| Windows & glazing |  | N | w/glazing | N | OK | N | OK | Y | -54000
| Skylights w/ curb & flashing |  | Y | a | Y | a | Y | a | Y | a
| Kynar Finish |  | Y | a | Y | a | Y | a | Y | a
| Anchor bolts - F.O.B. |  | Y | a | Y | a | Y | a | N | 4000
| Primed structural steel |  | Y | a | Y | a | Y | a | Y | a
| Sealant as applies |  | Y | a | Y | a | Y | a | Y | a
| Fab lead time / Errection Start |  | 22 | weeks | 22 | weeks | 30 | weeks | 20 | weeks
|  | Sub Total |  | 0 |  | 2673000.0125 |  | 2381000.014 |  | 2642000.01 |  | 0 |  | 0
Total