## 01 - FSR - Part A
| #REF! |  |  |  |  | LastCol
Header1 | Sanford Consortium for Regenerative Medicine
Header2 | Bid Package Summary - Financial Status Report
Header3
Header4
|  |  |  | DESIGN |  |  |  | BUYOUT |  |  |  | CONSTRUCTION
Descriptions |  |  |  | Original Construction Budget | Owner | Revised Construction |  | Buyout | Gain/Loss | Comments |  | Subcontract | Contingency | Owner | Adjusted
[5 empty] | Changes | Budget | [5 empty] | Amount | Changes | Changes | Contract Amount
| BP # | CC# |  | AMOUNT | AMOUNT | AMOUNT |  | AMOUNT | AMOUNT |  |  | AMOUNT | AMOUNT | AMOUNT | AMOUNT
LineH |  |  | Division 2
LineD1 | 2B | 0230000 | Earthwork and Demo - Grading Dirt Inc. | 568000 | -102000 | 466000 |  | 453000 | 13000 |  |  | 453000 | 0 | 0 | 453000
LineD1 | 2B | 0230100 | Additional Import/Export | 65000 | 0 | 65000 |  | 65000 | 0 |  |  | 65000 | 0 | 0 | 65000
| 2B | 0230200 | Import Base for Temp Road | 25000 | 0 | 25000 |  | 25000 | 0 |  |  | 25000 | 0 | 0 | 25000
| 2B | 0230300 | Street Sweeping | 15000 | 0 | 15000 |  | 15000 | 0 |  |  | 15000 | 0 | 0 | 15000
| 2B | 0230400 | Golf Course Demo and Grading | 50000 | 0 | 50000 |  | 50000 | 0 |  |  | 50000 | 0 | 0 | 50000
| 2D2 | 0240600 | Site Concrete & Unit Pavers - Budget | 951000 | -243000 | 708000 |  | 500000 | 208000 |  |  | 500000 | 0 | 0 | 500000
| 2D1 | 0240610 | Curb & Gutter at Asphalt Paving - Budget | 222000 | 70000 | 292000 |  | 292000 | 0 |  |  | 292000 | 0 | 0 | 292000
| 2A | 0242200 | Perm & Temp Shoring and Drilled Piers - Pier Tech | 83000 | 17000 | 100000 |  | 224000 | -124000 |  |  | 224000 | 0 | 0 | 224000
| 2A | 0242210 | Temp Shoring for Basement Excavation | 78000 | 11000 | 89000 |  | 0 | 89000 |  |  | 0 | 0 | 0 | 0
| 18E | 0241100 | Drilled Caissons | 0 | 25000 | 25000 |  | 0 | 25000 |  |  | 0 | 0 | 0 | 0
| 2C | 0250600 | Site Utilities - Pipe Diggers | 949000 | 211000 | 1160000 |  | 1160000 | 0 |  |  | 1160000 | 0 | 0 | 1160000
| 2C | 0250610 | Site Utility Completion Reserve | 84000 | 0 | 84000 |  | 84000 | 0 |  |  | 84000 | 0 |  | 84000
| 2C | 0250620 | Temp Storm Drain Relocation/Dewatering | 10000 | 0 | 10000 |  | 10000 | 0 |  |  | 10000 | 0 |  | 10000
| 2C | 0250650 | Site Survey - Coastal Surveying | 38000 | 0 | 38000 |  | 38000 | 0 |  |  | 38000 | 0 | 0 | 38000
| 2C | 0250660 | Site Survey - Additional Work | 17000 | 0 | 17000 |  | 17000 | 0 |  |  | 17000 | 0 | 0 | 17000
| 2E | 0240650 | Asphalt Paving - Budget | 560000 | -20000 | 540000 |  | 540000 | 0 |  |  | 540000 | 0 | 0 | 540000
| 2F | 0290000 | Landscaping & Irrigation - Budget | 1040000 | 55000 | 1095000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| 2F | 0290100 | Landscape Grading Budget | w/ Above | 0 | 0 |  | 20000 | -20000 |  |  | 20000 | 0 | 0 | 20000
| 2F | 0290200 | Bio Swale Coordination | w/ Above | 0 | 0 |  | 10000 | -10000 |  |  | 10000 | 0 | 0 | 10000
| 2F | 0290300 | Landscape Completion Reserve | w/ Above | 0 | 0 |  | 20000 | -20000 |  |  | 20000 | 0 | 0 | 20000
| 1C | 0156400 | Site Fencing - Temporary Links Co. | 52000 | 0 | 52000 |  | 20000 | 32000 |  |  | 20000 | 0 | 0 | 20000
| 1D | 0156400 | Temp Fence/Traffic Control - Budget | 47000 | 0 | 47000 |  | 79000 | -32000 |  |  | 79000 | 0 | 0 | 79000
| 1E | 0156700 | SWPPP - Budget | 100000 | 0 | 100000 |  | 100000 | 0 |  |  | 100000 | 0 | 0 | 100000
LineD1
LineD1 |  |  | Total Division 2 | 4954000 | 24000 | 4978000 |  | 3722000 | 161000 |  |  | 3722000 | 0 | 0 | 3722000
LineT1 |  |  | Division 3
LineD2 | 3D | 0320100 | Reinforcing - Rod Benders Inc. | 2664000 | -852000 | 1812000 |  | 1641000 | 171000 |  |  | 1641000 | 0 | 0 | 1641000
| 3D | 0320110 | MEP UG Conc. Duct Reinforcing | 0 | 0 | 0 |  | 34000 | -34000 |  |  | 34000 | 0 | 0 | 34000
| 3D | 0320120 | Slab Construction Joints | 0 | 0 | 0 |  | 28000 | -28000 |  |  | 28000 | 0 | 0 | 28000
| 3D | 0320130 | Ped. Bridge Reinforcing | 0 | 0 | 0 |  | 23000 | -23000 |  |  | 23000 | 0 | 0 | 23000
| 3D | 0320140 | DBS Budget | 0 | 0 | 0 |  | 50000 | -50000 |  |  | 50000 | 0 | 0 | 50000
| 3D | 0320150 | Supplemental Rebar Tonnage | 0 | 0 | 0 |  | 17000 | -17000 |  |  | 17000 | 0 | 0 | 17000
| 3A | 0330600 | Structural Concrete - Hensel Phelps | 9180000 | 481000 | 9661000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| 18A | 0181700 | Mock-up Concrete Allowance | 50000 | 10000 | 60000 |  | 60000 | 0 |  |  | 60000 | 0 | 0 | 60000
| 1B | 0162030 | Tower Crane - Budget | 720000 | 0 | 720000 |  | 720000 | 0 |  |  | 720000 | 0 | 0 | 720000
| 1B | 0162000 | Man Material Hoist - Budget | 455000 | 0 | 455000 |  | 455000 | 0 |  |  | 455000 | 0 | 0 | 455000
LineT2 |  |  | Total Division 3 | 13069000 | -361000 | 12708000 |  | 3028000 | 19000 |  |  | 3028000 | 0 | 0 | 3028000
LineH |  |  | Division 5
LineD3 | 5A | 0500100 | Structural Steel - Iron Fabrications | 964000 | 627000 | 1591000 |  | 1550000 | 41000 |  |  | 1550000 | 0 | 0 | 1550000
| 5A | 0500101 | Structural Steel Detail Completion | w/ Above | 0 | 0 |  | 41000 | -41000 |  |  | 41000 | 0 | 0 | 41000
| 5B | 500110 | Metal Decking - Corrogated Metals Inc. | 142000 | 18000 | 160000 |  | 116000 | 44000 |  |  | 116000 | 0 | 0 | 116000
| 5B | 500115 | Metal Deck Completion - Opening Reinforcing | w/ Above | 0 | 0 |  | 44000 | -44000 |  |  | 44000 | 0 | 0 | 44000
| 5D | 0500120 | Ornamental Railings - Budget | 752000 | 72000 | 824000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| 5C | 0552000 | Misc. Metals & Stairs - Stair Erectors Inc. | 1790000 | -655000 | 1135000 |  | 891000 | 244000 |  |  | 891000 | 0 | 0 | 891000
| 5C | 552100 | TS Supports for Roof Screen | w/ Above | 0 | 0 |  | 20000 | -20000 |  |  | 20000 | 0 | 0 | 20000
| 5C | 552200 | Temp Guardrail at Slab Edge Perimeter | w/ Above | 0 | 0 |  | 20000 | -20000 |  |  | 20000 | 0 | 0 | 20000
| 5C | 552300 | Guardrailat Headwall & Serpentive Retaining Wall | w/ Above | 0 | 0 |  | 5000 | -5000 |  |  | 5000 | 0 | 0 | 5000
| 5C | 552400 | Misc Metal Detail Completion | w/ Above | 0 | 0 |  | 60000 | -60000 |  |  | 60000 | 0 | 0 | 60000
LineH |  |  | Total Division 5 | 3648000 | 62000 | 3710000 |  | 2747000 | 963000 |  |  | 2747000 | 0 | 0 | 2747000
LineH |  |  | Division 6
| 6B | 0610000 | Rough Carpentry Budget - Hensel Phelps | 23000 | 0 | 23000 |  | 23000 | 0 |  |  | 23000 | 0 | 0 | 23000
| 6C | 0612000 | Exterior Woodwork - Special Exteriors | 598000 | -342000 | 256000 |  | 186000 | 70000 |  |  | 186000 | 0 | 0 | 186000
| 6C | 0612100 | Fill Fastener Holes Concealed | w/ Above | 0 | 0 |  | 5000 | -5000 |  |  | 5000 | 0 | 0 | 5000
| 6C | 0612200 | Furnish & Install Drop in Anchors | w/ Above | 0 | 0 |  | 10000 | -10000 |  |  | 10000 | 0 | 0 | 10000
| 6C | 0612300 | Penetrating Sealer for All Lumber | w/ Above | 0 | 0 |  | 5000 | -5000 |  |  | 5000 | 0 | 0 | 5000
| 6A | 0621000 | Architectural Millwork - Budget | 540000 | 56000 | 596000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  |  | Total Division 6 | 1161000 | -286000 | 875000 |  | 229000 | 50000 |  |  | 229000 | 0 | 0 | 229000
Division 7
| 7A/7B1 | 0712000 | Waterproofing/Pedestal Pavers - Waterstopping Inc. | 270000 | 410000 | 680000 |  | 618000 | 62000 |  |  | 618000 | 0 | 0 | 618000
LineD4 | 7A/7B1 | 0712010 | Waterproofing Substrate Prep | w/ Above | 0 | 0 |  | 15000 | -15000 |  |  | 15000 | 0 | 0 | 15000
| 7A/7B1 | 0712030 | Water Repellent at Exterior Concrete Walls | w/ Above | 0 | 0 |  | 32000 | -32000 |  |  | 32000 | 0 | 0 | 32000
| 7B | 0712100 | Roofing - Budget | 594000 | -2000 | 592000 |  | 550000 | 42000 |  |  | 550000 | 0 | 0 | 550000
LineD4 | 7C | 0760000 | Composite Panels, Sheetmetal & Flashings - Budget | 1480000 | 100000 | 1580000 |  | 1580000 | 0 |  |  | 1580000 | 0 | 0 | 1580000
| 7C | 0760100 | Sheetmetal Detail Completion | 0 | 86000 | 86000 |  | 86000 | 0 |  |  | 86000 | 0 | 0 | 86000
| 7D | 0782000 | Firestopping & Sealant Budget | 30000 | 0 | 30000 |  | 30000 | 0 |  |  | 30000 | 0 | 0 | 30000
|  |  | Total Division 7 | 2374000 | 594000 | 2968000 |  | 2911000 | 57000 |  |  | 2911000 | 0 | 0 | 2911000
Division 8
| 8A | 0810000 | Doors, Frame & Hardware - Swinging Hardware | 987000 | -146000 | 841000 |  | 680000 | 161000 |  |  | 680000 | 0 | 0 | 680000
| 8A | 0810200 | HM Frame Stocking/Installation Budget | w/ Above | 0 | 0 |  | 20000 | -20000 |  |  | 20000 | 0 | 0 | 20000
| 8A | 0810300 | Stair 1 & 4 Security Gates Hardware & CRs | w/ Above | 0 | 0 |  | 5000 | -5000 |  |  | 5000 | 0 | 0 | 5000
| 8A | 0810400 | Protection - Wood Doors & Hardware | w/ Above | 0 | 0 |  | 20000 | -20000 |  |  | 20000 | 0 | 0 | 20000
| 8A | 0810500 | Storefront Hardware Completion | w/ Above | 0 | 0 |  | 5000 | -5000 |  |  | 5000 | 0 | 0 | 5000
| 8A | 0810600 | DFH Design Completion | w/ Above | 0 | 0 |  | 25000 | -25000 |  |  | 25000 | 0 | 0 | 25000
| 8A | 0810700 | DFH Security Coordination/Interface | w/ Above | 0 | 0 |  | 10000 | -10000 |  |  | 10000 | 0 | 0 | 10000
| 8A | 0880000 | Curtainwall, Storefront, Trespa, & Interior Glazing | 5097000 | -918000 | 4179000 |  | 4211000 | -32000 |  |  | 4211000 | 0 | 0 | 4211000
| 8B | 0880100 | Glass/Glazing/Trespa Completion | 0 | 100000 | 100000 |  | 68000 | 32000 |  |  | 68000 | 0 | 0 | 68000
LineT4 |  |  | Total Division 8 | 6084000 | -964000 | 5120000 |  | 5044000 | 76000 |  |  | 5044000 | 0 | 0 | 5044000
LineH |  |  | Division 9
LineD5 | 9A | 0924000 | Drywall, Framing, & Insulation - Budget | 4210000 | -546000 | 3664000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| 9A | 0924100 | Drywall Premium Time | w/ Above | 0 | 0 |  | 50000 | -50000 |  |  | 50000 | 0 | 0 | 50000
| 9A | 0924200 | Drywall Punchlist/Repairs | w/ Above | 0 | 0 |  | 50000 | -50000 |  |  | 50000 | 0 | 0 | 50000
| 9A | 0924300 | Weather Proof Drywall Allowance | w/ Above | 0 | 0 |  | 72000 | -72000 |  |  | 72000 | 0 | 0 | 72000
| 9B | 0930000 | Stone & Tile - Budget | 302000 | -62000 | 240000 |  | 240000 | 0 |  |  | 240000 | 0 | 0 | 240000
| 9C | 0951000 | Acoustical Ceiling - Budget | 1435000 | -459000 | 976000 |  | 850000 | 126000 |  |  | 850000 | 0 | 0 | 850000
| 9D | 0960000 | Flooring & Sealed Concrete - Budget | 575000 | -4000 | 571000 |  | 400000 | 171000 |  |  | 400000 | 0 | 0 | 400000
| 9E | 0990000 | Paint & Special Coating - Budget | 264000 | 60000 | 324000 |  | 400000 | -76000 |  |  | 400000 | 0 | 0 | 400000
LineD5 | 9E | 0990100 | Paint Punchlist/Repairs | 30000 | 10000 | 40000 |  | 40000 | 0 |  |  | 40000 | 0 | 0 | 40000
| 9F | 0961000 | Epoxy Coatings - Budget | 700000 | 128000 | 828000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| 9B1 | 962000 | Grind & Polish Concrete - Budget | 0 | 115000 | 115000 |  | 150000 | -35000 |  |  | 150000 | 0 | 0 | 150000
LineT5 |  |  | Total Division 9 | 7516000 | -758000 | 6758000 |  | 2252000 | 14000 |  |  | 2252000 | 0 | 0 | 2252000
LineH |  |  | Division 10
| 10A | 1000100 | Building Specialties - Budget | 744000 | -744000 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
| 10A | 0931200 | Coiling Doors & Grills - Budget | 0 | 45000 | 45000 |  | 50000 | -5000 |  |  | 50000 | 0 | 0 | 50000
| 10A | 1020000 | Operable Partition - Budget | 0 | 36000 | 36000 |  | 36000 | 0 |  |  | 36000 | 0 | 0 | 36000
| 10A | 1030000 | Prefab Hazmat Buidling - Budget | 0 | 45000 | 45000 |  | 51000 | -6000 |  |  | 51000 | 0 | 0 | 51000
| 10A | 1040000 | Signage Allowance | 0 | 82000 | 82000 |  | 85000 | -3000 |  |  | 85000 | 0 | 0 | 85000
| 10A | 1050000 | Code & ADA Signage | 0 | 40000 | 40000 |  | 37000 | 3000 |  |  | 37000 | 0 | 0 | 37000
| 10A | 1080000 | Toilet Accessories & Specialties - Budget | 0 | 373000 | 373000 |  | 200000 | 173000 |  |  | 200000 | 0 | 0 | 200000
| 10A | 1202000 | Window Treatment - Budget | 0 | 86000 | 86000 |  | 86000 | 0 |  |  | 86000 | 0 | 0 | 86000
| 10A | 1206100 | Fixed Audience Seating - Budget | 0 | 88000 | 88000 |  | 100000 | -12000 |  |  | 100000 | 0 | 0 | 100000
LineD6 | 18C | 1000200 | Final Cleaning - Budget | 0 | 89000 | 89000 |  | 89000 | 0 |  |  | 89000 | 0 | 0 | 89000
|  |  | Total Division 10 | 744000 | 140000 | 884000 |  | 734000 | 150000 |  |  | 734000 | 0 | 0 | 734000
Division 11
LineD6 | 12B | 1100100 | Window Washing Allowance | 200000 | 0 | 200000 |  | 200000 | 0 |  |  | 200000 | 0 | 0 | 200000
|  |  | Total Division 11 | 200000 | 0 | 200000 |  | 200000 | 0 |  |  | 200000 | 0 | 0 | 200000
Division 12
| 12A | 1100500 | Lab Casework & Equipment - LCE Co. | 7850000 | -232000 | 7618000 |  | 7906000 | -288000 |  |  | 7906000 | 0 | 0 | 7906000
LineD6 | 12C | 1100001 | Food Service Budget | 100000 | -100000 | 0 |  | 0 |  | FS by Developer |  | 0 | 0 | 0 | 0
|  |  | Total Division 12 | 7950000 | -332000 | 7618000 |  | 7906000 | -288000 |  |  | 7906000 | 0 | 0 | 7906000
Division 14
LineD6 | 14A | 1400200 | Elevators - CONA Elevators | 890000 | -56000 | 834000 |  | 860000 | -26000 |  |  | 860000 | 0 | 0 | 860000
| 14A | 1400210 | Temp Elevator Operator | 100000 | 0 | 100000 |  | 100000 | 0 |  |  | 100000 | 0 | 0 | 100000
LineT6 |  |  | Total Division 14 | 990000 | -56000 | 934000 |  | 960000 | -26000 |  |  | 960000 | 0 | 0 | 960000
Division 15
| 15B | 1500400 | Fire Protection - Wet Suppression Inc. | 740000 | 39000 | 779000 |  | 830000 | -51000 |  |  | 830000 | 0 | 0 | 830000
| 15A | 1500500 | HVAC/Plumbing - Torrey Pines Mechanical | 12962000 | 129000 | 13091000 |  | 13000000 | 91000 |  |  | 13000000 | 0 | 0 | 13000000
| 15A | 1500550 | HVAC/Plumbing Design Completion Reserve | 0 | 0 | 0 |  | 100000 | -100000 |  |  | 100000 | 0 | 0 | 100000
|  |  | Total Division 15 | 13702000 | 168000 | 13870000 |  | 13930000 | -60000 |  |  | 13930000 | 0 | 0 | 13930000
Division 16
| 16 | 1600000 | Electrical - La Jolla Electric | 6697000 | 291000 | 6988000 |  | 6893000 | 95000 |  |  | 6893000 | 0 | 0 | 6893000
| 16 | 1600300 | Electrical - Completion | 0 | 0 | 0 |  | 50000 | -50000 |  |  | 50000 | 0 | 0 | 50000
LineT7 |  |  | Total Division 16 | 6697000 | 291000 | 6988000 |  | 6943000 | 45000 |  |  | 6943000 | 0 | 0 | 6943000
Misc. Items
| X | 1000000 | Misc. Items | 2712000 | -2712000 | 0 |  | 0 | 0 | w/ other budget |  | 0 | 0 | 0 | 0
LineT7 |  |  | Total Misc. Items | 2712000 | -2712000 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
|  |  | Subtotal - BUILDING & SITE | 71801000 | -4190000 | 67611000 |  | 50606000 | 1161000 | 0 |  | 50606000 | 0 | 0 | 50606000
HeaderGC |  |  | GENERAL CONDITIONS
GC01 | 1A | 0132000 | General Conditions - Lump Sum | 4900000 | -400000 | 4500000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
STotalGC |  |  | Subtotal - GENERAL CONDITIONS | 4900000 | -400000 | 4500000 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
Blank
HeaderIR |  |  | INDIRECTS & RESERVES
IR03 | 18B | 0152100 | Temp Power Usage 3 Mos Prior to Substantial Comp | 0 | 60000 | 60000 |  | 60000 | 0 |  |  | 60000 | 0 | 0 | 60000
| 18F | 0133400 | Waterproofing Testing Consultant - Budget | 0 | 55000 | 55000 |  | 55000 | 0 |  |  | 55000 | 0 | 0 | 55000
IR07 |  | 1000001 | Contractor's Bond - Non D/B | 660000 | -660000 | 0 |  | 0 | 0 | No Prime Contract Bond |  | 0 | 0 | 0 | 0
|  | 9022000 | General Liability Insurance | 525000 | -112000 | 413000 |  | 413000 | 0 |  |  | 413000 | 0 | 0 | 413000
|  | 9030000 | Sub Bonds | 439000 | -151000 | 288000 |  | w/ Subs | 288000 |  |  | w/ Subs | 0 | 0 | 0
IR11 |  | 9032000 | LEED Silver Allowance | 350000 | -250000 | 100000 |  | 100000 | 0 |  |  | 100000 | 0 | 0 | 100000
|  | 9032500 | LEED Consultant | 75000 | -75000 | 0 |  | 0 | 0 | by Developer |  | 0 | 0 | 0 | 0
IR14 |  | 0130000 | Preconstruction Costs | 225000 | 0 | 225000 |  | 225000 | 0 |  |  | 225000 | 0 | 0 | 225000
|  | 0130500 | Design assist | 0 | 460000 | 460000 |  | 460000 | 0 |  |  | 460000 | 0 | 0 | 460000
|  | 9098000 | HPCC Construction Contingency | 2000000 | 0 | 2000000 |  | 2000000 | 0 |  |  | 3449000 | 0 | 0 | 3449000
|  | 9098500 | Owner Design Contingency | 0 | 1000000 | 1000000 |  | 1000000 | 0 |  |  | 1000000 | 0 | 0 | 1000000
STotalIR |  |  | Subtotal - INDIRECTS & RESERVES | 4274000 | 327000 | 4601000 |  | 4313000 | 288000 |  |  | 5762000 | 0 | 0 | 5762000
Blank
HeaderFE |  |  | FEES
FE01 | 5.076% | 9099000 | Contractor's Fee | 4330000 | -460000 | 3870000 |  | 3870000 | 0 |  |  | 3870000 | 0 | 0 | 3870000
Total |  |  | TOTAL CONSTRUCTION COST | 85305000 | -4723000 | 80582000 |  | 58789000 | 1449000 |  | 0 | 60238000 | 0 | 0 | 60238000
CONTINGENCY RECAP
[6 empty] | Original GMP | Design Budget | Buyout Budget | Construction Budget | Revised
[6 empty] | Budget | Adjustments | Adjustments | Adjustments | Amount
|  |  |  | HPCC Construction Contingency |  | 2000000 | 0 | 1449000 | 0 | 3449000
|  |  |  | Owner Design Contingency |  | 0 | 1000000 | 0 | 0 | 1000000
Footer |  |  |  | Totals |  | 2000000 | 1000000 | 1449000 | 0 | 4449000
Disclaimer
Logo
Footer |  |  |  |  | Blue Cells are scopes of work yet to be purchased. Values based on budgetary or prelimenary pricing.
Footer
Footer

## 01 - FSR - Part B
| #REF! |  |  |  |  | LastCol
Header1 | Sanford Consortium for Regenerative Medicine
Header2 | Bid Package Summary - Financial Status Report
Header3
Header4
|  |  |  | DESIGN |  |  |  | BUYOUT |  |  |  | CONSTRUCTION
Descriptions |  |  |  | Original Construction Budget | Owner | Revised Construction |  | Buyout | Gain/Loss | Comments |  | Subcontract | Contingency | Owner | Adjusted
[5 empty] | Changes | Budget | [5 empty] | Amount | Changes | Changes | Contract Amount
| BP # | CC# |  | AMOUNT | AMOUNT | AMOUNT |  | AMOUNT | AMOUNT |  |  | AMOUNT | AMOUNT | AMOUNT | AMOUNT
LineH |  |  | Division 2
LineD1 | 2B | 0230000 | Earthwork and Demo - Grading Dirt Inc. | 568000 | -102000 | 466000 |  | 453000 | 13000 |  |  | 453000 | 0 | 0 | 453000
LineD1 | 2B | 0230100 | Additional Import/Export | 65000 | 0 | 65000 |  | 65000 | 0 |  |  | 65000 | 0 | 0 | 65000
| 2B | 0230200 | Import Base for Temp Road | 25000 | 0 | 25000 |  | 25000 | 0 |  |  | 25000 | 0 | 0 | 25000
| 2B | 0230300 | Street Sweeping | 15000 | 0 | 15000 |  | 15000 | 0 |  |  | 15000 | 0 | 0 | 15000
| 2B | 0230400 | Golf Course Demo and Grading | 50000 | 0 | 50000 |  | 50000 | 0 |  |  | 50000 | 0 | 0 | 50000
| 2D2 | 0240600 | Site Concrete & Unit Pavers - Budget | 951000 | -243000 | 708000 |  | 500000 | 208000 |  |  | 500000 | 0 | 0 | 500000
| 2D1 | 0240610 | Curb & Gutter at Asphalt Paving - Budget | 222000 | 70000 | 292000 |  | 292000 | 0 |  |  | 292000 | 0 | 0 | 292000
| 2A | 0242200 | Perm & Temp Shoring and Drilled Piers - Pier Tech | 83000 | 17000 | 100000 |  | 224000 | -124000 |  |  | 224000 | 0 | 0 | 224000
| 2A | 0242210 | Temp Shoring for Basement Excavation | 78000 | 11000 | 89000 |  | 0 | 89000 |  |  | 0 | 0 | 0 | 0
| 18E | 0241100 | Drilled Caissons | 0 | 25000 | 25000 |  | 0 | 25000 |  |  | 0 | 0 | 0 | 0
| 2C | 0250600 | Site Utilities - Pipe Diggers | 949000 | 211000 | 1160000 |  | 1160000 | 0 |  |  | 1160000 | 0 | 0 | 1160000
| 2C | 0250610 | Site Utility Completion Reserve | 84000 | 0 | 84000 |  | 84000 | 0 |  |  | 84000 | 0 | 0 | 84000
| 2C | 0250620 | Temp Storm Drain Relocation/Dewatering | 10000 | 0 | 10000 |  | 10000 | 0 |  |  | 10000 | 0 | 0 | 10000
| 2C | 0250650 | Site Survey - Coastal Surveying | 38000 | 0 | 38000 |  | 38000 | 0 |  |  | 38000 | 0 | 0 | 38000
| 2C | 0250660 | Site Survey - Additional Work | 17000 | 0 | 17000 |  | 17000 | 0 |  |  | 17000 | 0 | 0 | 17000
| 2E | 0240650 | Asphalt Paving - Budget | 560000 | -20000 | 540000 |  | 540000 | 0 |  |  | 540000 | 0 | 0 | 540000
| 2F | 0290000 | Landscaping & Irrigation - Budget | 1040000 | 55000 | 1095000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| 2F | 0290100 | Landscape Grading Budget | w/ Above | 0 | 0 |  | 20000 | -20000 |  |  | 20000 | 0 | 0 | 20000
| 2F | 0290200 | Bio Swale Coordination | w/ Above | 0 | 0 |  | 10000 | -10000 |  |  | 10000 | 0 | 0 | 10000
| 2F | 0290300 | Landscape Completion Reserve | w/ Above | 0 | 0 |  | 20000 | -20000 |  |  | 20000 | 0 | 0 | 20000
| 1C | 0156400 | Site Fencing - Temporary Links Co. | 52000 | 0 | 52000 |  | 20000 | 32000 |  |  | 20000 | 0 | 0 | 20000
| 1D | 0156400 | Temp Fence/Traffic Control - Budget | 47000 | 0 | 47000 |  | 79000 | -32000 |  |  | 79000 | 0 | 0 | 79000
| 1E | 0156700 | SWPPP - Budget | 100000 | 0 | 100000 |  | 100000 | 0 |  |  | 100000 | 0 | 0 | 100000
LineD1
LineD1 |  |  | Total Division 2 | 4954000 | 24000 | 4978000 |  | 3722000 | 161000 |  |  | 3722000 | 0 | 0 | 3722000
LineT1 |  |  | Division 3
LineD2 | 3D | 0320100 | Reinforcing - Rod Benders Inc. | 2664000 | -852000 | 1812000 |  | 1641000 | 171000 |  |  | 1641000 | 0 | 0 | 1641000
| 3D | 0320110 | MEP UG Conc. Duct Reinforcing | 0 | 0 | 0 |  | 34000 | -34000 |  |  | 34000 | 0 | 0 | 34000
| 3D | 0320120 | Slab Construction Joints | 0 | 0 | 0 |  | 28000 | -28000 |  |  | 28000 | 0 | 0 | 28000
| 3D | 0320130 | Ped. Bridge Reinforcing | 0 | 0 | 0 |  | 23000 | -23000 |  |  | 23000 | 0 | 0 | 23000
| 3D | 0320140 | DBS Budget | 0 | 0 | 0 |  | 50000 | -50000 |  |  | 50000 | 0 | 0 | 50000
| 3D | 0320150 | Supplemental Rebar Tonnage | 0 | 0 | 0 |  | 17000 | -17000 |  |  | 17000 | 0 | 0 | 17000
| 3A | 0330600 | Structural Concrete - Hensel Phelps | 9180000 | 481000 | 9661000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| 18A | 0181700 | Mock-up Concrete Allowance | 50000 | 10000 | 60000 |  | 60000 | 0 |  |  | 60000 | 0 | 0 | 60000
| 1B | 0162030 | Tower Crane - Budget | 720000 | 0 | 720000 |  | 720000 | 0 |  |  | 720000 | 0 | 0 | 720000
| 1B | 0162000 | Man Material Hoist - Budget | 455000 | 0 | 455000 |  | 455000 | 0 |  |  | 455000 | 0 | 0 | 455000
LineT2 |  |  | Total Division 3 | 13069000 | -361000 | 12708000 |  | 3028000 | 19000 |  |  | 3028000 | 0 | 0 | 3028000
LineH |  |  | Division 5
LineD3 | 5A | 0500100 | Structural Steel - Iron Fabrications | 964000 | 627000 | 1591000 |  | 1550000 | 41000 |  |  | 1550000 | 0 | 0 | 1550000
| 5A | 0500101 | Structural Steel Detail Completion | w/ Above | 0 | 0 |  | 41000 | -41000 |  |  | 41000 | 0 | 0 | 41000
| 5B | 500110 | Metal Decking - Corrogated Metals Inc. | 142000 | 18000 | 160000 |  | 116000 | 44000 |  |  | 116000 | 0 | 0 | 116000
| 5B | 500115 | Metal Deck Completion - Opening Reinforcing | w/ Above | 0 | 0 |  | 44000 | -44000 |  |  | 44000 | 0 | 0 | 44000
| 5D | 0500120 | Ornamental Railings - Budget | 752000 | 72000 | 824000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| 5C | 0552000 | Misc. Metals & Stairs - Stair Erectors Inc. | 1790000 | -655000 | 1135000 |  | 891000 | 244000 |  |  | 891000 | 0 | 0 | 891000
| 5C | 552100 | TS Supports for Roof Screen | w/ Above | 0 | 0 |  | 20000 | -20000 |  |  | 20000 | 0 | 0 | 20000
| 5C | 552200 | Temp Guardrail at Slab Edge Perimeter | w/ Above | 0 | 0 |  | 20000 | -20000 |  |  | 20000 | 0 | 0 | 20000
| 5C | 552300 | Guardrailat Headwall & Serpentive Retaining Wall | w/ Above | 0 | 0 |  | 5000 | -5000 |  |  | 5000 | 0 | 0 | 5000
| 5C | 552400 | Misc Metal Detail Completion | w/ Above | 0 | 0 |  | 60000 | -60000 |  |  | 60000 | 0 | 0 | 60000
LineH |  |  | Total Division 5 | 3648000 | 62000 | 3710000 |  | 2747000 | 963000 |  |  | 2747000 | 0 | 0 | 2747000
LineH |  |  | Division 6
| 6B | 0610000 | Rough Carpentry Budget - Hensel Phelps | 23000 | 0 | 23000 |  | 23000 | 0 |  |  | 23000 | 0 | 0 | 23000
| 6C | 0612000 | Exterior Woodwork - Special Exteriors | 598000 | -342000 | 256000 |  | 186000 | 70000 |  |  | 186000 | 0 | 0 | 186000
| 6C | 0612100 | Fill Fastener Holes Concealed | w/ Above | 0 | 0 |  | 5000 | -5000 |  |  | 5000 | 0 | 0 | 5000
| 6C | 0612200 | Furnish & Install Drop in Anchors | w/ Above | 0 | 0 |  | 10000 | -10000 |  |  | 10000 | 0 | 0 | 10000
| 6C | 0612300 | Penetrating Sealer for All Lumber | w/ Above | 0 | 0 |  | 5000 | -5000 |  |  | 5000 | 0 | 0 | 5000
| 6A | 0621000 | Architectural Millwork - Budget | 540000 | 56000 | 596000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  |  | Total Division 6 | 1161000 | -286000 | 875000 |  | 229000 | 50000 |  |  | 229000 | 0 | 0 | 229000
Division 7
| 7A/7B1 | 0712000 | Waterproofing/Pedestal Pavers - Waterstopping Inc. | 270000 | 410000 | 680000 |  | 618000 | 62000 |  |  | 618000 | 0 | 0 | 618000
LineD4 | 7A/7B1 | 0712010 | Waterproofing Substrate Prep | w/ Above | 0 | 0 |  | 15000 | -15000 |  |  | 15000 | 0 | 0 | 15000
| 7A/7B1 | 0712030 | Water Repellent at Exterior Concrete Walls | w/ Above | 0 | 0 |  | 32000 | -32000 |  |  | 32000 | 0 | 0 | 32000
| 7B | 0712100 | Roofing - Budget | 594000 | -2000 | 592000 |  | 550000 | 42000 |  |  | 550000 | 0 | 0 | 550000
LineD4 | 7C | 0760000 | Composite Panels, Sheetmetal & Flashings - Budget | 1480000 | 100000 | 1580000 |  | 1580000 | 0 |  |  | 1580000 | 0 | 0 | 1580000
| 7C | 0760100 | Sheetmetal Detail Completion | 0 | 86000 | 86000 |  | 86000 | 0 |  |  | 86000 | 0 | 0 | 86000
| 7D | 0782000 | Firestopping & Sealant Budget | 30000 | 0 | 30000 |  | 30000 | 0 |  |  | 30000 | 0 | 0 | 30000
|  |  | Total Division 7 | 2374000 | 594000 | 2968000 |  | 2911000 | 57000 |  |  | 2911000 | 0 | 0 | 2911000
Division 8
| 8A | 0810000 | Doors, Frame & Hardware - Swinging Hardware | 987000 | -146000 | 841000 |  | 680000 | 161000 |  |  | 680000 | 0 | 0 | 680000
| 8A | 0810200 | HM Frame Stocking/Installation Budget | w/ Above | 0 | 0 |  | 20000 | -20000 |  |  | 20000 | 0 | 0 | 20000
| 8A | 0810300 | Stair 1 & 4 Security Gates Hardware & CRs | w/ Above | 0 | 0 |  | 5000 | -5000 |  |  | 5000 | 0 | 0 | 5000
| 8A | 0810400 | Protection - Wood Doors & Hardware | w/ Above | 0 | 0 |  | 20000 | -20000 |  |  | 20000 | 0 | 0 | 20000
| 8A | 0810500 | Storefront Hardware Completion | w/ Above | 0 | 0 |  | 5000 | -5000 |  |  | 5000 | 0 | 0 | 5000
| 8A | 0810600 | DFH Design Completion | w/ Above | 0 | 0 |  | 25000 | -25000 |  |  | 25000 | 0 | 0 | 25000
| 8A | 0810700 | DFH Security Coordination/Interface | w/ Above | 0 | 0 |  | 10000 | -10000 |  |  | 10000 | 0 | 0 | 10000
| 8A | 0880000 | Curtainwall, Storefront, Trespa, & Interior Glazing | 5097000 | -918000 | 4179000 |  | 4211000 | -32000 |  |  | 4211000 | 0 | 0 | 4211000
| 8B | 0880100 | Glass/Glazing/Trespa Completion | 0 | 100000 | 100000 |  | 68000 | 32000 |  |  | 68000 | 0 | 0 | 68000
LineT4 |  |  | Total Division 8 | 6084000 | -964000 | 5120000 |  | 5044000 | 76000 |  |  | 5044000 | 0 | 0 | 5044000
LineH |  |  | Division 9
LineD5 | 9A | 0924000 | Drywall, Framing, & Insulation - Budget | 4210000 | -546000 | 3664000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| 9A | 0924100 | Drywall Premium Time | w/ Above | 0 | 0 |  | 50000 | -50000 |  |  | 50000 | 0 | 0 | 50000
| 9A | 0924200 | Drywall Punchlist/Repairs | w/ Above | 0 | 0 |  | 50000 | -50000 |  |  | 50000 | 0 | 0 | 50000
| 9A | 0924300 | Weather Proof Drywall Allowance | w/ Above | 0 | 0 |  | 72000 | -72000 |  |  | 72000 | 0 | 0 | 72000
| 9B | 0930000 | Stone & Tile - Budget | 302000 | -62000 | 240000 |  | 240000 | 0 |  |  | 240000 | 0 | 0 | 240000
| 9C | 0951000 | Acoustical Ceiling - Budget | 1435000 | -459000 | 976000 |  | 850000 | 126000 |  |  | 850000 | 0 | 0 | 850000
| 9D | 0960000 | Flooring & Sealed Concrete - Budget | 575000 | -4000 | 571000 |  | 400000 | 171000 |  |  | 400000 | 0 | 0 | 400000
| 9E | 0990000 | Paint & Special Coating - Budget | 264000 | 60000 | 324000 |  | 400000 | -76000 |  |  | 400000 | 0 | 0 | 400000
LineD5 | 9E | 0990100 | Paint Punchlist/Repairs | 30000 | 10000 | 40000 |  | 40000 | 0 |  |  | 40000 | 0 | 0 | 40000
| 9F | 0961000 | Epoxy Coatings - Budget | 700000 | 128000 | 828000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| 9B1 | 962000 | Grind & Polish Concrete - Budget | 0 | 115000 | 115000 |  | 150000 | -35000 |  |  | 150000 | 0 | 0 | 150000
LineT5 |  |  | Total Division 9 | 7516000 | -758000 | 6758000 |  | 2252000 | 14000 |  |  | 2252000 | 0 | 0 | 2252000
LineH |  |  | Division 10
| 10A | 1000100 | Building Specialties - Budget | 744000 | -744000 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
| 10A | 0931200 | Coiling Doors & Grills - Budget | 0 | 45000 | 45000 |  | 50000 | -5000 |  |  | 50000 | 0 | 0 | 50000
| 10A | 1020000 | Operable Partition - Budget | 0 | 36000 | 36000 |  | 36000 | 0 |  |  | 36000 | 0 | 0 | 36000
| 10A | 1030000 | Prefab Hazmat Buidling - Budget | 0 | 45000 | 45000 |  | 51000 | -6000 |  |  | 51000 | 0 | 0 | 51000
| 10A | 1040000 | Signage Allowance | 0 | 0 | 0 |  | 0 | 0 | Returned to Owner |  | 0 | 0 | 0 | 0
| 10A | 1050000 | Code & ADA Signage | 0 | 40000 | 40000 |  | 37000 | 3000 |  |  | 37000 | 0 | 0 | 37000
| 10A | 1080000 | Toilet Accessories & Specialties - Budget | 0 | 373000 | 373000 |  | 200000 | 173000 |  |  | 200000 | 0 | 0 | 200000
| 10A | 1202000 | Window Treatment - Budget | 0 | 86000 | 86000 |  | 86000 | 0 |  |  | 86000 | 0 | 0 | 86000
| 10A | 1206100 | Fixed Audience Seating - Budget | 0 | 88000 | 88000 |  | 100000 | -12000 |  |  | 100000 | 0 | 0 | 100000
LineD6 | 18C | 1000200 | Final Cleaning - Budget | 0 | 89000 | 89000 |  | 89000 | 0 |  |  | 89000 | 0 | 0 | 89000
|  |  | Total Division 10 | 744000 | 58000 | 802000 |  | 649000 | 153000 |  |  | 649000 | 0 | 0 | 649000
Division 11
LineD6 | 12B | 1100100 | Window Washing Allowance | 200000 | -200000 | 0 |  | 0 | 0 | Returned to Owner |  | 0 | 0 | 0 | 0
|  |  | Total Division 11 | 200000 | -200000 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
Division 12
| 12A | 1100500 | Lab Casework & Equipment - LCE Co. | 7850000 | -232000 | 7618000 |  | 7906000 | -288000 |  |  | 7906000 | 0 | 0 | 7906000
LineD6 | 12C | 1100001 | Food Service Budget | 100000 | -100000 | 0 |  | 0 |  | FS by Developer |  | 0 | 0 | 0 | 0
|  |  | Total Division 12 | 7950000 | -332000 | 7618000 |  | 7906000 | -288000 |  |  | 7906000 | 0 | 0 | 7906000
Division 14
LineD6 | 14A | 1400200 | Elevators - CONA Elevators | 890000 | -56000 | 834000 |  | 860000 | -26000 |  |  | 860000 | 0 | 0 | 860000
| 14A | 1400210 | Temp Elevator Operator | 100000 | 0 | 100000 |  | 100000 | 0 |  |  | 100000 | 0 | 0 | 100000
LineT6 |  |  | Total Division 14 | 990000 | -56000 | 934000 |  | 960000 | -26000 |  |  | 960000 | 0 | 0 | 960000
Division 15
| 15B | 1500400 | Fire Protection - Wet Suppression Inc. | 740000 | 39000 | 779000 |  | 830000 | -51000 |  |  | 830000 | 0 | 0 | 830000
| 15A | 1500500 | HVAC/Plumbing - Torrey Pines Mechanical | 12962000 | 129000 | 13091000 |  | 13000000 | 91000 |  |  | 13000000 | 0 | 0 | 13000000
| 15A | 1500550 | HVAC/Plumbing Design Completion Reserve | 0 | 0 | 0 |  | 100000 | -100000 |  |  | 100000 | 0 | 0 | 100000
|  |  | Total Division 15 | 13702000 | 168000 | 13870000 |  | 13930000 | -60000 |  |  | 13930000 | 0 | 0 | 13930000
Division 16
| 16 | 1600000 | Electrical - La Jolla Electric | 6697000 | 291000 | 6988000 |  | 6893000 | 95000 |  |  | 6893000 | 0 | 0 | 6893000
| 16 | 1600300 | Electrical - Completion | 0 | 0 | 0 |  | 50000 | -50000 |  |  | 50000 | 0 | 0 | 50000
LineT7 |  |  | Total Division 16 | 6697000 | 291000 | 6988000 |  | 6943000 | 45000 |  |  | 6943000 | 0 | 0 | 6943000
Misc. Items
| X | 1000000 | Misc. Items | 2712000 | -2712000 | 0 |  | 0 | 0 | w/ other budget |  | 0 | 0 | 0 | 0
LineT7 |  |  | Total Misc. Items | 2712000 | -2712000 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
|  |  | Subtotal - BUILDING & SITE | 71801000 | -4472000 | 67329000 |  | 50321000 | 1164000 | 0 |  | 50321000 | 0 | 0 | 50321000
HeaderGC |  |  | GENERAL CONDITIONS
GC01 | 1A | 0132000 | General Conditions - Lump Sum | 4900000 | -400000 | 4500000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
STotalGC |  |  | Subtotal - GENERAL CONDITIONS | 4900000 | -400000 | 4500000 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
Blank
HeaderIR |  |  | INDIRECTS & RESERVES
IR03 | 18B | 0152100 | Temp Power Usage 3 Mos Prior to Substantial Comp | 0 | 0 | 0 |  | 60000 | -60000 | Returned to Owner |  | 60000 | 0 | 0 | 60000
| 18F | 0133400 | Waterproofing Testing Consultant - Budget | 0 | 55000 | 55000 |  | 55000 | 0 |  |  | 55000 | 0 | 0 | 55000
IR07 |  | 1000001 | Contractor's Bond - Non D/B | 660000 | -660000 | 0 |  | 0 | 0 | No Prime Contract Bond |  | 0 | 0 | 0 | 0
|  | 9022000 | General Liability Insurance | 525000 | -112000 | 413000 |  | 413000 | 0 |  |  | 413000 | 0 | 0 | 413000
|  | 9030000 | Sub Bonds | 439000 | -151000 | 288000 |  | w/ Subs | 288000 |  |  | w/ Subs | 0 | 0 | 0
IR11 |  | 9032000 | LEED Silver Allowance | 350000 | -350000 | 0 |  | 100000 | -100000 | Returned to Owner |  | 100000 | 0 | 0 | 100000
|  | 9032500 | LEED Consultant | 75000 | -75000 | 0 |  | 0 | 0 | by Developer |  | 0 | 0 | 0 | 0
IR14 |  | 0130000 | Preconstruction Costs | 225000 | 0 | 225000 |  | 225000 | 0 |  |  | 225000 | 0 | 0 | 225000
|  | 0130500 | Design assist | 0 | 460000 | 460000 |  | 460000 | 0 |  |  | 460000 | 0 | 0 | 460000
|  | 9098000 | HPCC Construction Contingency | 2000000 | -2000000 | 0 |  | 0 | 0 | Returned to Owner |  | 1292000 | 0 | 0 | 1292000
|  | 9098500 | Owner Design Contingency | 0 | 0 | 0 |  | 0 | 0 | Returned to Owner |  | 0 | 0 | 0 | 0
STotalIR |  |  | Subtotal - INDIRECTS & RESERVES | 4274000 | -2833000 | 1441000 |  | 1313000 | 128000 |  |  | 2605000 | 0 | 0 | 2605000
Blank
HeaderFE |  |  | FEES
FE01 | 5.076% | 9099000 | Contractor's Fee | 4330000 | -460000 | 3870000 |  | 3870000 | 0 |  |  | 3870000 | 0 | 0 | 3870000
Total |  |  | TOTAL CONSTRUCTION COST | 85305000 | -8165000 | 77140000 |  | 55504000 | 1292000 |  | 0 | 56796000 | 0 | 0 | 56796000
CONTINGENCY RECAP
[6 empty] | Original GMP | Design Budget | Buyout Budget | Construction Budget | Revised
[6 empty] | Budget | Adjustments | Adjustments | Adjustments | Amount
|  |  |  | HPCC Construction Contingency |  | 2000000 | -2000000 | 1292000 | 0 | 1292000
|  |  |  | Owner Design Contingency |  | 0 | 0 | 0 | 0 | 0
Footer |  |  |  | Totals |  | 2000000 | -2000000 | 1292000 | 0 | 1292000
Disclaimer
Logo
Footer |  |  |  |  | Blue Cells are scopes of work yet to be purchased. Values based on budgetary or prelimenary pricing.
Footer
Footer