## Sheet1
CHANGE ORDER REQUEST
SANFORD CONSORTIUM
Hensel Phelps Construction co.
2880 Torrey Pines Scenic Drive,
Attention | Project Engineer | [5 empty] | San Diego, CA 92037.
FCC JOB # AAA123
FCC COR NO.: | AA
FCC PCO NO.: | XX
SUBJECT: | ASI 20 PRICING
DATE: | 2013-02-02
GC REFERENCE No.:
RFI No.:
SKETCHES
DESCRIPTION OF WORK: Added labor, material, and equipment costs to include plumbing revisions, sump tank for Aquatic Center and associated changes.
Costs include all fabrication and delivery.
Exclusions
To avoid Impact, Please respond by : ASAP
| Position | QUANTITY | UNITS | RATE/U.P. | LABOR(a) | MATERIAL(b) | EQUIP (d) | SUBTOTAL
Labor
Pipe-Fitters | Foreman | 36 | hr | 125.68 | 4524.48 | 0 | 0 | 4524.48
Pipe-Fitters | Journeyman | 24 | hr | 118.73 | 2849.52 | 0 | 0 | 2849.52
Pipe-Fitters | Apprentice | 16 | hr | 86.8 | 1388.8 | 0 | 0 | 1388.8
Materials (Material Tax Included)
Piping |  | 350 | lnft | 2.56 | 0 | 896 | 0 | 896
Sinks |  | 3 | ea | 450 | 0 | 1350 | 0 | 1350
Small Miscellaneous Materials |  | 1 | ls | 520 | 0 | 520 | 0 | 520
Tier Subcontractor (No Markup included)
Aquaneering (Equipment cost for delivery) | Sump Tank | 1 | LS | 3452 | 250 | 3452 | 265 | 3967
Subtotal | [7 empty] | 15495.8
Total fees on subcontracted work (10%) | [7 empty] | 396.7
Total Overhead and Profit (5%) | [7 empty] | 794.625
Subtotal | [7 empty] | 16687.125
Insurance (2%) | [7 empty] | 333.7425
Bond (1.25%) | [7 empty] | 208.5891
City Tax | [7 empty] | 0
Total | [7 empty] | 17229.4566
FLOW CONSTRUCTION COMPANY
ABC WATER STREET, WATER | [6 empty] | __________________________
CA - 00000. | [6 empty] | PROJECT MANAGER
Subcontractor License No. :XYZXYZ | [6 empty] | This quote is valid for 30 days
FCC