## Summary
COMPANY: | Wall Contractors, Inc. |  | Sub CE # | XX
DATE: | 2013-02-01 |  | HPCC CE # | 102
PROJECT ELEMENT: | Sanford Corsortium |  | Bulletin/ RFI# | ASI 20
DESCRIPTION: | Wall Framing, Caulking, Head of Wall and all other relevant details in ASI 20. Inclusive of all costs to be incurred for modification of wall layout per ASI 20.
Total Labor (All fringe benefits, insurance and workers comp. included) |  |  | 5565.64 | (From Page 2)
Total Materials (All applicable taxes included) |  |  | 2808.005 | (From Page 3)
Total Equipment (All applicable taxes and rental costs included) |  |  | 448 | (From Page 4)
|  | Direct Cost of Work Subtotal | 8821.645
Overhead and Profit
| Profit & Overhead | 5% | 441.0822
|  | Overhead and Profit Subtotal | 441.0822
Lower Tiered Subcontractors |  |  | 0 | (From Page 5)
| Subcontracting Markup | 15% | 0%
|  | Lower Tiered Subcontractors Subtotal | 0
Insurance and Bonds
| Insurance | 2.5% | 231.5682
| Perform. & Pay. Bonds | 2.5% | 231.5682
|  | Insurance and Bonds Subtotal | 463.1364
|  | Total Cost of Change | 9725.8636
Time Extension Requested in Working Days (Include backup documentation) |  |  | xx | (Attach Backup)

## Labor Backup
COMPANY: | Wall Contractors, Inc. |  |  | Sub CE # | XX
DATE: | 2013-02-01 |  |  | HPCC CE # | 102
PROJECT ELEMENT: | Sanford Corsortium |  |  | Bulletin/ RFI# | ASI 20
DESCRIPTION: | Wall Framing, Caulking, Head of Wall and all other relevant details in ASI 20. Inclusive of all costs to be incurred for modification of wall layout per ASI 20.
NAME | CLASSIFICATION | HOURS | S.T. RATE | O.T. RATE | TOTAL
Framer - Drywaller | Foreman (ST) | 12 | 87.34 |  | 1048.08
Framer- Drywaller - 4hrs of layout included. | Journeyman (ST) | 12 | 88.27 |  | 1059.24
Framer- Drywaller | Journeyman (OT) | 12 |  | 117.31 | 1407.72
Taper | Journeyman (ST) | 12 | 95.43 |  | 1145.16
Taper | Journeyman (OT) | 8 |  | 113.18 | 905.44
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Total Direct Labor Cost | 5565.64

## Material Backup
COMPANY: | Wall Contractors, Inc. |  | Sub CE # | XX
DATE: | 2013-02-01 |  | HPCC CE # | 102
PROJECT ELEMENT: | Sanford Corsortium |  | Bulletin/ RFI# | ASI 20
DESCRIPTION: | Wall Framing, Caulking, Head of Wall and all other relevant details in ASI 20. Inclusive of all costs to be incurred for modification of wall layout per ASI 20.
Description |  | Quantity | Unit/ Cost | Total
One Lump Sum (LS) quote from WALL SUPPLIES |  | 1 | 2594 | 2594
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal Material Cost | 2594
|  | 8.25% | Sales Tax | 214.005
|  |  | Total Material Cost | 2808.005

## Equipment Backup
COMPANY: | Wall Contractors, Inc. |  |  | Sub CE # | XX
DATE: | 2013-02-01 |  |  | HPCC CE # | 102
PROJECT ELEMENT: | Sanford Corsortium |  |  | Bulletin/ RFI# | ASI 20
DESCRIPTION: | Wall Framing, Caulking, Head of Wall and all other relevant details in ASI 20. Inclusive of all costs to be incurred for modification of wall layout per ASI 20.
Description |  | Unit | Duration | Unit Cost | Total
Scissor Lift (Monthly rental) |  | LS | 1 | 448 | 448
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Total Equipment Cost | 448

## Lower Tier Sub
COMPANY: | Wall Contractors, Inc. | Sub CE # | XX
DATE: | 2013-02-01 | HPCC CE # | 102
PROJECT ELEMENT: | Sanford Corsortium | Bulletin/ RFI# | ASI 20
DESCRIPTION: | Wall Framing, Caulking, Head of Wall and all other relevant details in ASI 20. Inclusive of all costs to be incurred for modification of wall layout per ASI 20.
Description |  |  | Total
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  | Total Second Tier Subcontract Cost | 0