IGNITE BROTHERS, INC.

SUITE 123, ABC ROAD, NFPA, CA 90909

February 1st, 2013.

Project Engineer,

Hensel Phelps Construction co.

2880 Torrey Pines Scenic Drive,

San Diego, CA  92037.

Attn: Project Engineer

RE: CE 102 Pricing

Sir,

Ignite Brothers, Inc. hereby submits the price of $8,756.00 to provide design and construction  services as follows for ASI 20. We submit the following breakdown.

Labor – 36 Journeyman hours @ 102.81 - 	$3701.00					Material Invoice - 					$2003.00

Design 40 hours @ 82.00	-		   	$3280.00

Subtotal  - 		   	$8984.00

15% Overhead and Profit – $1348.00

2 % Bond –			$207.00

Total - 			$10539.00

PRICING VALID FOR THIRTY (30) DAYS.  SUBJECT TO CHANGE PRIOR TO ACCEPTANCE.

By signing below, you acknowledge that the above described work shall modify the terms and conditions of the contract and that you are directing Ignite Brothers, Inc. to proceed with the work as described above.  You further agree to issue a valid change order within 10 working days of the completion of the above described work.  In the absence of a valid change order being issued, you acknowledge that the total cost of this change will be added to the next billing cycle as a valid claim.

Very truly yours,

Ignite Brothers Inc.

Fire Man,

Project Manager

Hardware supply incorporated

321 XYZ ST, NFPA, CA 90909

MATERIAL INVOICE

Pricing Quotation, as requested by Ignite Brothers, Inc.

| Sr. No. | Description | Quantity | Unit | Rate | Total |
| --- | --- | --- | --- | --- | --- |
| 1 | Valves | 10 | EA | $45 | 450 |
| 2 | Tags | 15 | EA | $8.25 | 123.75 |
| 3 | Piping Material | 1 | Lumpsum | $1400 | 1300.25 |
| 4 | Attachments | 1 LS | EA | $150 | 128.50 |
| Total |  |  |  |  | 2002.5 |

Sales tax and other applicable taces are not included. Quantities are approximate – Unit Prices Prevail.

The above Items are quoted F.O.B. truck load quantities.

All Items are in Stock.

Please place order no later than 10am, the day before delivery is required.

Your Sincerely,

Office Manager.