## Letter
Project and Mailing Address:
SCRM
Hensel Phelps Construction Co.
2880 Torrey Pines Scenic Drive
La Jolla, California 92037
Tel. (858) 678-0171
Fax (858) 678-0378
2013-02-06
Sanford Consortium, LLC
655 W. Broadway, Suite 1450
San Diego, California 92101
Attention: | Owner
Reference: | SCRM
HPCC Job No. 4008067
Subject:
Dear Eric:
Attached is our Proposal to perform the subject Change Order work summarized as follows:
The total estimated cost for this proposed change is. . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |  | -19682.706
Schedule extension required. . .. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |  | NA | Calendar days
This proposal is based on incorporating this change into the normal sequence of work without any acceleration measures.
It includes only the usual cost elements such as labor, materials, normal markups and does not include any amounts
for changes in the sequence of work, delays, disruptions, rescheduling, extended overhead, acceleration and/or impact costs.
This Change Order Proposal is valid until:
If a written Change Order or directive is not received prior to this date, this proposal is void and must be
re-evaluated related to cost and schedule impact.
Hensel Phelps Construction Co. has proceeded with this work. Please respond to this Change Estimate as
soon as possible.
If you have any questions, please contact the undersigned.
Sincerely,
Hensel Phelps Construction Co.
Name
Project Engineer
xc: 4008067.1.30,
CE No.102
Sanford Consortium hereby accepts Hensel Phelps proposal for additional work.
A formal Change Order for this work will be forthcoming.
Sanford Consortium, LLC |  | Date
Hensel Phelps Construction Co. will not proceed with this work, until receipt of your written direction.
If you wish us to proceed prior to receipt of a signed change order, please sign below as acceptance of
this change and return to the jobsite address above.
Hensel Phelps Construction Co. is proceeding with this work based upon your verbal direction and have
written change orders to Subcontractors for all or a portion of the work.

## Summary
| SCRM |  | CE NO. | 102
La Jolla, CA
|  |  | Date: | 2013-02-06
ADDITIVE CHANGES
CHANGE ESTIMATE
PROPOSAL SUMMARY
ASI#20 - Aquaneering Underground Plumbing & Sump Tank Removal
1 | HPCC SELFWORK | 0
2 | SUBCONTRACTORS | -17835
3 | SUBTOTAL ALL DIRECT COSTS (#1 + #2) |  | -17835
4 | DESIGN FEES |  |  | NIC
5 | GENERAL CONDITIONS (1.5%) |  |  | -267.525
6 | SUBTOTAL (#3 through #5) |  | -18102.525
7 | BOND (2%) |  |  | -362.0505
8 | GL INSURANCE (2%) |  |  | -362.0505
9 | SUBTOTAL ALL COSTS EXCEPT CONTRACTOR'S FEE |  | -18826.626
10 | CONTRACTOR'S FEE (4.8 %) | -884.8514 |  | -856.08
11 | TOTAL PROPOSED CHANGE ORDER COST |  |  | -19682.706
REFERENCE DOCUMENTS
ASI#20
Note on A9: TPS: ENTER DESCRIPTION HERE.
Note on H2: TPS: Enter CE # here. All other cells linked to this one.
Note on H4: TPS: Enter Date Here. All other cells linked to this one.
Note on H29: TPS: Note formula: if x < 0, then fee is $0

## Subcontractors
ATTACHMENT #2
TO CHANGE ESTIMATE PROPOSAL SUMMARY
| SCRM |  | CE NO. | 102
La Jolla, CA
|  |  | Date: | 2013-02-06
ADDITIVE CHANGES
SUBCONTRACTOR WORK
| Scope of Work | Subcontractor |  | Cost
1 | Plumbing | Flow Construction Company
2 | Framing | Wall Contractors, Inc.
3 | Mechanical | Blow Mechanical
4 | Fire Protection | Ignite Brothers, Inc.
5 | Ceilings | Top Incorporation |  | -9867
6 | Painting | Color Contractors |  | -7968
7 | Electrical | Electrify Contractors
8
9
10
11
12
13
14
|  | TOTAL SUBCONTRACTOR COST |  | -17835