## BUYOUT
|  | California Veterans Home, Fresno | [5 empty] | OFFICE INFO ONLY
[5 empty] | ACTION |  |  | COST CONTROL INFORMATION |  | COST CONTROL INFORMATION
DATE
|  | SUPPLIER OR | NEED | LETTER | CONTRACT | CONTRACT | BOND | NOT | TOTAL EST. | Budget | PURCHASED. | GAIN | SUB/VEND
| ITEM DESCRIPTION | SUBCONTRACTOR | TO | TO | MAILED | EXEC | EXEC | USED | AMOUNT | AMOUNT | AMOUNT | OR | +/-
|  |  | PURCHASE | DST | [7 empty] | LOSS | SUMMARY
| Genera Conditions & General Requirements | [7 empty] | 6651240
005001 | Supervision | Hensel Phelps | [7 empty] | 2872990 | 2872990 | 0
005002 | Engineering & Survey Work | Hensel Phelps | [7 empty] | 2783350 | 2783350 | 0
005003 | Safety Requirements | Hensel Phelps | [7 empty] | 74040 | 74040 | 0
005004 | Temp Facilities | Hensel Phelps | [7 empty] | 580320 | 580320 | 0
005005 | Building Services | Hensel Phelps | [7 empty] | 128940 | 128940 | 0
005006 | Transpeortation | Hensel Phelps | [7 empty] | 211600 | 211600 | 0
005007 | Sales Tax on Material | Hensel Phelps | [7 empty] | 15883 | 15883 | 0
| Division 2 - Existing Conditions | [7 empty] | 130000
023120 | Site Survey Assessment | Western Tech | [7 empty] | 95000 | 64000 | 31000
023610 | Termite Control | Vox Con | [7 empty] | 35000 | 35000 | 0
| Division 3 - Concrete | [7 empty] | 4143793
031000 | Concrete Forming and Accessories | Hensel Phelps | [7 empty] | W/Con. | W/Con. | W/Con.
032000 | Concrete Reinforcement | CMC Rebar | 2013-08-22 | [6 empty] | 571700 | 571700 | 0
033000 | Cast in Place Concrete | Hensel Phelps | [7 empty] | 3572093 | 3572093 | 0
033500 | Concrete Material | Hensel Phelps | [7 empty] | W/ Above | W/ Above | W/ Above
| Division 4 - Masonry | [7 empty] | 1584413
042200 | Concrete Unit | Stoney Masonry | [7 empty] | 378310 | 228725 | 149585
044800 | Cultered Stone Venneer | Bratton Masonry | [7 empty] | 1206103 | 268217 | 937886
| Division 5 - Metals | [7 empty] | 3753861
050530 | Standard for Aluminum Work | Lucrosol | [7 empty] | W/Below | W/Below | W/Below | W/Below
050650 | Welded Stud Connectors | Lucrosol | [7 empty] | W/Below | W/Below | W/Below | W/Below
051200 | Structural Steel | Lucrosol | [7 empty] | 1747270 | 1561070 | 186200
052100 | Steel Joists | Lucrosol | [7 empty] | W/Above | W/Above | W/Above
053100 | Steel Deck | Lucrosol | [7 empty] | 303610 | 277750 | 25860
054000 | Cold-Formed Metal Framing | Insul-Acoustics | [7 empty] | 150000 | W/Drywall | 150000
055000 | Metal Fabricatons | Lucrosol | [7 empty] | 535980 | 615000 | -79020
055100 | Metal Stairs | Lucrosol | [7 empty] | 943501 | 875000 | 68501
055213 | Pipe & Tube Railings | Lucrosol | [7 empty] | W/Above | W/Above | W/Above
058000 | Roof Expansion Joint Assembly | Water Out R Us | [7 empty] | 73500 | 93500 | -20000
| Division 6 - Wood & Plastic | [7 empty] | 6633612
061000 | Rough Carpentry | Harly-Fass Framing | [7 empty] | 3345000 | 3325570 | 19430
061500 | Wood Trusses | Harly-Faas Framing | [7 empty] | W/Above | W/Above | W/Above
061643 | Gypsum Sheathing | Insul-Acoustics | [7 empty] | W/ Div 9 | W/ Div 9 | W/ Div 9
062000 | Finish Carpentry | WAC | [7 empty] | 3288612 | 3423000 | -134388
064000 | Architectual Woodwork | WAC | [7 empty] | W/Above | W/Above | W/Above
066500 | Soid Surfacing | WAC | [7 empty] | W/Above | W/Above | W/Above
| Division 7 - Waterproofing & Damproofing | [7 empty] | 4929315
071326 | Self-Adhering Sheet Waterproofing | Tile Runners | [7 empty] | 65000 | 71000 | -6000
071750 | Water Repellant Coatings at Masonry | Wm. B. Saleh | [7 empty] | 125120 | W/Paint | 125120
072100 | Thermal Insulation | The Works | [7 empty] | 538850 | 368000 | 170850
072200 | Roof & Deck Insulation | Tile Runners | [7 empty] | 135000 | 132000 | 3000
072620 | Vapor Barrier | Wanda's Waterproofing | [7 empty] | 235000 | 235000 | 0
072710 | Building Paper | Tile Runners | [7 empty] | 55000 | 68000 | -13000
073200 | Roof Tiles | Tile Runners | [7 empty] | 637521 | 612000 | 25521
074113 | Metal Roof Panels | Progressive Roofing | [7 empty] | 1030480 | 916770 | 113710
074646 | Fiber Cement Siding | Harly-Faas Framing | [7 empty] | 640344 | 635000 | 5344
075419 | Polyvinyl-Chloride Roofing | Progressive Roofing | [7 empty] | W/Above | W/Above | W/Above
076200 | Sheet Metal Flashing and Trim | Tile Runners | [7 empty] | 92000 | 81000 | 11000
077100 | Roof Specialties | Tile Runners | [7 empty] | 1200000 | 1064000 | 136000
078400 | FireStopping | Insul-Acoustics | [7 empty] | 100000 | W/Insul Acous | 100000
079200 | Joint Sealants | Tile Runners | [7 empty] | 75000 | 100000 | -25000
| Division 8 - Doors, Frames & Hardware | [7 empty] | 5355939
081100 | Metal Doors and Frames | ABBA Distributors | [7 empty] | 748078 | 748078 | 0
081416 | Flush Wood Doors | ABBA Distributors | [7 empty] | 547227 | 547227 | 0
083100 | Access Doors and Panels | With All Trades | [7 empty] | 128816 | W/ Trades | 128816
083310 | Coiling Counter Doors | ABBA Distributors | [7 empty] | W/Above | W/Above | W/Above
083323 | Overhead Coiling Doors | ABBA Distributors | [7 empty] | W/Above | W/Above | W/Above
084100 | Entrances and Storefronts | San Joaquin Glass | [7 empty] | 1129180 | 1350000 | -220820
084229 | Double Entrance Door | San Joaquin Glass | [7 empty] | 738400 | 650000 | 88400
085200 | Wood Windows | San Joaquin Glass | [7 empty] | 819776 | 796495 | 23281
086200 | Unit Skylights | San Joaquin Glass | [7 empty] | 10000 | W/Windows | 10000
087100 | Door Hardware | ABBA Distributors | [7 empty] | 1132962 | 1122500 | 10462
088000 | Glazing | San Joaquin Glass | [7 empty] | 58500 | 73335 | -14835
089000 | Wall Louvers | Frank M. Booth Design-Build | [7 empty] | 43000 | W/Mech | 43000
| Division 9 - Finishes | [7 empty] | 10105903
090000 | Finishes | Tarlton & Son | [7 empty] | 829517 | 462664 | 366853
092200 | Supports for Plaster and Gy Board | Tarlton & Son | [7 empty] | W/Above | W/Above | W/Above
092237 | Lath & Accessories | Tarlton & Son | [7 empty] | W/Above | W/Above | W/Above
092700 | Portland Cement Plastering | Tarlton & Son | [7 empty] | W/Above | W/Above | W/Above
092900 | Gypsum Board - Interior | The Works | [7 empty] | 1461632 | 1544000 | -82368
092900 | Gypsum Board - Exterior | Tarlton & Son | [7 empty] | 2823936 | 3063395 | -239459
093013 | Ceramic Tile | VISALIA CERAMIC TILE | [7 empty] | 1500000 | 1458000 | 42000
095113 | Acoustical Panel Ceilings | The Works | [7 empty] | 750000 | 760000 | -10000
096150 | Water Vapor Emission and Alkalinty Conrol System | Stego | [7 empty] | 408501 | 408501 | 0
096516 | Resilient Sheet Flooring | MCC Flooring | [7 empty] | 198292 | 947602 | -749310
096813 | Tile Carpeting | MCC Flooring | [7 empty] | 814762 | W/Above | 814762
097700 | Fierglass Reinforced Panels | Hensel Phelps | [7 empty] | 37752 | 37752 | 0
098433 | Sound Absorbing Wall Units | The Works | [7 empty] | 650000 | 646000 | 4000
099100 | Painting | Wm. B. Saleh | [7 empty] | 631511 | 602308 | 29203
099413 | Textured Wall Finish | Insul-Acoustics | [7 empty] | W/Gyp | W/Gyp | W/Gyp
099750 | Special Coatings for Steel | Wm. B. Saleh | [7 empty] | W/Above | W/Above | W/Above
| Division 10 - Specialties | [7 empty] | 2182659
101100 | Visual Display Surfaces | KKO | [7 empty] | 12262 | 55000 | -42738
101920 | Cubicle Track, Hardwar and Curtains | KKO | [7 empty] | 40620 | W/Above | 40620
102113 | Operable Partitions | KKO | [7 empty] | 62500 | W/Toilet Acc | 62500
102600 | Wall and Corner Guards | FP Construction | [7 empty] | 447691 | W/FP | 447691
102630 | Protective Wall Covering | FP Construction | [7 empty] | 700660 | W/FP | 700660
102813 | Toilet Accessories | KKO | [7 empty] | 628282 | 678300 | -50018
103000 | Manufactured Fireplaces | ACC Manufacture | [7 empty] | 55000 | 53200 | 1800
104400 | Fire-Protection Specialties | ACC Manufacture | [7 empty] | 147404 | 145000 | 2404
105100 | Metal Lockers | KKO | [7 empty] | 39540 | W/Toilet Acc | 39540
105500 | Postal Specialties | KKO | [7 empty] | 36500 | 35000 | 1500
107500 | Flagpoles | American | [7 empty] | 12200 | 12200 | 0
| Division 11 - Equipment | [7 empty] | 1359503
110360 | Transaction Windows | KKO | [7 empty] | 18916 | 19000 | -84
111300 | Audio-Visual Equipment | KKO | [7 empty] | 56200 | 55000 | 1200
111610 | Loading Dock Bumpers | KKO | [7 empty] | 13500 | 26520 | -13020
111620 | Loading Dock Levelers | KKO | [7 empty] | 12000 | W/Above | 12000
114000 | Food Service Equipment | Kamran | [7 empty] | 1090000
117000 | Medical Equipment | Blah Equipment | [7 empty] | 168887 | 168887 | 0
117010 | Equipment Scheudle | Blah Equipment | [7 empty] | W/Above | W/Above | W/Above
| Division 12- Furnishings | [7 empty] | 1018235
124820 | Floor Mats & Frames | KKO | [7 empty] | 147000 | 137000 | 10000
122113 | Horizontal Louver Blinds | KKO | [7 empty] | 29250 | 25000 | 4250
124950 | Window Shades | KKO | [7 empty] | 160200 | 172000 | -11800
129300 | Site Furnishings | Babby Sites | [7 empty] | 681785 | 675000 | 6785
Division 13 - Special Construction
| Division 14 - Conveying Equipment | [7 empty] | 80000
142400 | Hydraulic Elevators | OTIS | [7 empty] | 80000 | 56585 | 23415
| Division 21 - Fire Protection System | [7 empty] | 1430348
211313 | Wet-Pipe Fire Sprinkler Systems | Aero Automatic | [7 empty] | 1430348 | 1049850 | 380498
| Division 22 - Plumbing | [7 empty] | 6640000
220500 | Common Work Results for Plumbing | Piper's Plumbing |  |  |  | 2010-04-30 | 2010-05-06 |  |  | 6640000 | 6640000 | 0
220513 | Common Motor Requirements for Plumbing Equipment | [8 empty] | W/Above | W/Above | W/Above
220516 | Expansion Fittings and Loops for Plumbing Pipe | [8 empty] | W/Above | W/Above | W/Above
220519 | Meters and Gauges for Plumbing Pipe | [8 empty] | W/Above | W/Above | W/Above
220523 | General Duty Valves for Plumbing | [8 empty] | W/Above | W/Above | W/Above
220529 | Hangers and Supports for Plumbing Pipe and Equipment | [8 empty] | W/Above | W/Above | W/Above
220548 | Vibration and Seismic Controls for Plumbing Piping and Equipment | [8 empty] | W/Above | W/Above | W/Above
220553 | Identification for Plumbing Piping and Equipment | [8 empty] | W/Above | W/Above | W/Above
220700 | Plumbing Insulation | [8 empty] | W/Above | W/Above | W/Above
221116 | Domestic Water Piping | [8 empty] | W/Above | W/Above | W/Above
221119 | Domestic Water Piping Specialties | [8 empty] | W/Above | W/Above | W/Above
221316 | Sanitary Waste and Vent Piping | [8 empty] | W/Above | W/Above | W/Above
221319 | Sanitary Waste Piping Specialties | [8 empty] | W/Above | W/Above | W/Above
221323 | Sanitary Waste Interceptors | [8 empty] | W/Above | W/Above | W/Above
221413 | Facility Storm Drainage Piping | [8 empty] | W/Above | W/Above | W/Above
221423 | Storm Drainage Piping Specialties | [8 empty] | W/Above | W/Above | W/Above
223100 | Domestic Water Softners | [8 empty] | W/Above | W/Above | W/Above
223400 | Fuel-Fired Domestic Water Heaters | [8 empty] | W/Above | W/Above | W/Above
224000 | Plumbing Fixtures | [8 empty] | W/Above | W/Above | W/Above
224500 | Emergency Plumbing Fixtures | [8 empty] | W/Above | W/Above | W/Above
| Division 23 - Mechanical | [7 empty] | 16741000
230500 | Common Work Results for HVAC | Frank M. Booth Design-Build | 2013-08-22 |  |  | 2010-04-30 | 2010-05-06 |  |  | 16741000 | 16741000 | 0
230513 | Common Motor Requirements for HVAC Equipment | [8 empty] | W/Above | W/Above | W/Above
230516 | Expansion Fittings and Loops for HVAC Piping | [8 empty] | W/Above | W/Above | W/Above
230519 | Meters and Gauges for HVAC Piping | [8 empty] | W/Above | W/Above | W/Above
230523 | General Duty Valves for HVAC Piping | [8 empty] | W/Above | W/Above | W/Above
230529 | Hangers and supposts for HVAC Piping and Equipment | [8 empty] | W/Above | W/Above | W/Above
230533 | Heat Tracing for HVAC Piping | [8 empty] | W/Above | W/Above | W/Above
230548 | Vibration and Seismic Controls for HVAC Piping and equipment | [8 empty] | W/Above | W/Above | W/Above
230553 | Identification for HVAC Piping and Equipment | [8 empty] | W/Above | W/Above | W/Above
230593 | Testing, Adjusting and Balancing for HVAC | [8 empty] | W/Above | W/Above | W/Above
230700 | HVAC Insulation | [8 empty] | W/Above | W/Above | W/Above
230800 | Commissiongin of HVAC | [8 empty] | W/Above | W/Above | W/Above
230900 | Instrumentation and Control for HVAC | [8 empty] | W/Above | W/Above | W/Above
231123 | Facility Natural-Gas Piping | [8 empty] | W/Above | W/Above | W/Above
232112 | Underground Pre-Insulated Chilled and Hot Water Piping | [8 empty] | W/Above | W/Above | W/Above
232113 | Hydronic Piping | [8 empty] | W/Above | W/Above | W/Above
232123 | Hydronic Pumps | [8 empty] | W/Above | W/Above | W/Above
232500 | HVAC Water Treatment | [8 empty] | W/Above | W/Above | W/Above
233113 | Metal Ducts | [8 empty] | W/Above | W/Above | W/Above
23300 | Air Duct Accessories | [8 empty] | W/Above | W/Above | W/Above
233423 | HVAC Power Ventilators | [8 empty] | W/Above | W/Above | W/Above
233433 | Air Curtains | [8 empty] | W/Above | W/Above | W/Above
233600 | Air Terminal Units | [8 empty] | W/Above | W/Above | W/Above
233713 | Diffusers, Registers and Grilles | [8 empty] | W/Above | W/Above | W/Above
233723 | HVAC Gravity Ventilators | [8 empty] | W/Above | W/Above | W/Above
234100 | Particulate Air Filtration | [8 empty] | W/Above | W/Above | W/Above
235100 | Breeching, Chimneys, and Stacks | [8 empty] | W/Above | W/Above | W/Above
235233 | Water-Tube Boilers | [8 empty] | W/Above | W/Above | W/Above
236416 | Centrifuggal Water Chillers | [8 empty] | W/Above | W/Above | W/Above
236500 | Cooling Tower | [8 empty] | W/Above | W/Above | W/Above
237313 | Modular Central-Station Air Handling Units | [8 empty] | W/Above | W/Above | W/Above
237433 | Packaged, Outdoor, Makeup Air Unit | [8 empty] | W/Above | W/Above | W/Above
238119 | Rooftop Packaged Heat Pump Units | [8 empty] | W/Above | W/Above | W/Above
238123 | Computer Room Air Conditioners | [8 empty] | W/Above | W/Above | W/Above
238126 | Split-System Air-Conditioning Units | [8 empty] | W/Above | W/Above | W/Above
238219 | Fan Coil Units | [8 empty] | W/Above | W/Above | W/Above
238313 | Radiant-Heating Electric Cables | [8 empty] | W/Above | W/Above | W/Above
| Division 26 - Electrical | [7 empty] | 13956900
260500 | Common Work Results for Electrical | Empire Electric | 2013-08-22 |  |  | 2010-05-03 | 2010-04-30 |  |  | 13956900 | 13606900 | 350000
260519 | Low-Voltage Electrical Power Conductors and Cables | [8 empty] | W/Above | W/Above | W/Above
260526 | Grounding and Bonding for Electrical | [8 empty] | W/Above | W/Above | W/Above
260529 | Hangers and Supports for Electrictal Systems | [8 empty] | W/Above | W/Above | W/Above
260533 | Raceway and Boxes for Electrical Systems | [8 empty] | W/Above | W/Above | W/Above
260536 | Cable Tras for Electrical Systems | [8 empty] | W/Above | W/Above | W/Above
260543 | Underground Ducts and Raceways for Electrical Systems | [8 empty] | W/Above | W/Above | W/Above
260548 | Vibration and Seismic Controsls for Electrical Systems | [8 empty] | W/Above | W/Above | W/Above
260553 | Identifications for Electical Systems | [8 empty] | W/Above | W/Above | W/Above
260573 | Overcurrent Protective Device Coordination Study | [8 empty] | W/Above | W/Above | W/Above
260800 | Lighting Control Devises | [8 empty] | W/Above | W/Above | W/Above
260923 | Low-Voltage Transformers | [8 empty] | W/Above | W/Above | W/Above
262200 | Switchboards | [8 empty] | W/Above | W/Above | W/Above
262413 | Panelboards | [8 empty] | W/Above | W/Above | W/Above
262416 | Wiring Devises | [8 empty] | W/Above | W/Above | W/Above
262726 | Fuses | [8 empty] | W/Above | W/Above | W/Above
262813 | Enclosed Switches and Circuit Breakers | [8 empty] | W/Above | W/Above | W/Above
262816 | Variable-Frequency Motor Controllers | [8 empty] | W/Above | W/Above | W/Above
262923 | Engine Generators | [8 empty] | W/Above | W/Above | W/Above
263353 | Static Uniterupted Power Supply | [8 empty] | W/Above | W/Above | W/Above
263600 | Transfer Switch | [8 empty] | W/Above | W/Above | W/Above
264313 | Transient-Voltage Supressian for Low-Voltage Electrical Power Circuits | [8 empty] | W/Above | W/Above | W/Above
265100 | Interior Lighting | [8 empty] | W/Above | W/Above | W/Above
265600 | Exterior Lighting | [8 empty] | W/Above | W/Above | W/Above
| Division 27 - Communications | [7 empty] | W/Elec
270500 | Common Work Results for Comm | [8 empty] | W/Elec | W/Elec | W/Elec
271100 | Coom Equipment Room Fittings | [8 empty] | W/Elec | W/Elec | W/Elec
271300 | Comm Backbone Cabling | [8 empty] | W/Elec | W/Elec | W/Elec
271500 | Comm Horizontal Cabling | [8 empty] | W/Elec | W/Elec | W/Elec
274133 | Master Antenna TV System | [8 empty] | W/Elec | W/Elec | W/Elec
275105 | Assisted Listening System | [8 empty] | W/Elec | W/Elec | W/Elec
275116 | Public Address and Mass Notification Systems | [8 empty] | W/Elec | W/Elec | W/Elec
275119 | Wander Guard System | [8 empty] | W/Elec | W/Elec | W/Elec
275223 | Nurse Call & Staff Locator | [8 empty] | W/Elec | W/Elec | W/Elec
| Division 28 - Electrical Safety and Security | [7 empty] | W/Elec
281000 | Electric Access Control And Security System | [8 empty] | W/Elec | W/Elec | W/Elec
282323 | Closed Circuit TV System | [8 empty] | W/Elec | W/Elec | W/Elec
283111 | Digital Addressable Fire Alarm System and Mass Notifications | [8 empty] | W/Elec | W/Elec | W/Elec
283500 | Refrigerant Detention and Alarm | [8 empty] | W/Elec | W/Elec | W/Elec
| Division 31 - Earthwork | [7 empty] | 1314336
311100 | Site Clearing and Grubbing | GRG Construction | 2013-08-22 | [6 empty] | 1314336 | 1046553 | 267783
312200 | Finished Grading | [8 empty] | W/ Above | W/ Above | W/ Above
312300 | Excavation and Fill | [8 empty] | W/ Above | W/ Above | W/ Above
312500 | Erosion and Sedimentation Controls | [8 empty] | W/ Above | W/ Above | W/ Above
| Division 32 - Exterior Improvements | [7 empty] | 4317642
321116.16 | Aggregate Subbase Courses | Concrete Done with Love | [7 empty] | W/Site Con | W/Site Con | W/Site Con
321123 | Aggregate Base Courses | Concrete Done with Love | [7 empty] | W/Site Con | W/Site Con | W/Site Con
321213 | Preparatory Coats | Chales Court | [7 empty] | 50000 | 52000 | -2000
321216 | Asphalt Paving | Highlands | [7 empty] | 725363 | 562343 | 163020
321236 | Seal Coats | Highlands | [7 empty] | W/Above | W/Above | W/Above
321313 | Concrete Paving | Concrete Done with Love | [7 empty] | 1262202 | 1315000 | -52798
321316 | Decorative Concrete Paving | Concrete Done with Love | [7 empty] | W/Above | W/Above | W/Above
321440 | Decomposed Granite Paving | Concrete Done with Love | [7 empty] | 123300 | W/Land | 123300
321443 | Porous Unit Paving | European Pavers | [7 empty] | 342500 | 450000 | -107500
321613 | Concrete Curbs and Gutters | Concrete Done with Love | [7 empty] | W/Site Con | W/Site Con | W/Site Con
321723.13 | Painted Pavement Markings | Falcon | [7 empty] | 43800 | 43800 | 0
321726 | Tactile Warning Surface | Concrete Done with Love | [7 empty] | W/Site Con | W/Conc | W/Conc
323119 | Decorative Metal Fences and Gates | Security Fence | [7 empty] | 396325 | 398000 | -1675
323219 | Unit Masonty Retaining Walls | Stoney Masonry | [7 empty] | W/Masonry | W/Masonry | W/Masonry
328000 | Irrigation Work | AAA Landscape | [7 empty] | 1374152 | 1372000 | 2152
328100 | Irrigation Central Controller | AAA Landscape | [7 empty] | W/Above | W/Above | W/Above
328200 | Irrigation Booster Pump | AAA Landscape | [7 empty] | W/Above | W/Above | W/Above
329113 | Soil Preparation | AAA Landscape | [7 empty] | W/Above | W/Above | W/Above
329300 | Planting Work | AAA Landscape | [7 empty] | W/Above | W/Above | W/Above
329413 | Landscape Edgeing | AAA Landscape | [7 empty] | W/Above | W/Above | W/Above
329443 | Tree Grates | AAA Landscape | [7 empty] | W/Above | W/Above | W/Above
| Division 33 - Utilities | [7 empty] | 1107250
330513 | Manholes and Structures | Highlands | [7 empty] | 1107250 | 1098315 | 8935
331116 | Site Water Utility Distribution Piping | Highlands | [7 empty] | W/Above | W/Above | W/Above
331216 | Water Utility Distrubtion Valves | Highlands | [7 empty] | W/Above | W/Above | W/Above
333116 | Privat Sanitay Sewage Piping | Highlands | [7 empty] | W/Above | W/Above | W/Above
334100 | Storm Drain Piping | Highlands | [7 empty] | W/Above | W/Above | W/Above
335100 | Natural Gas Distribution | Highlands | [7 empty] | W/Above | W/Above | W/Above
| Allowances, Utility Fees, Design Fees & Testing | [7 empty] | 6163094
990000 | Allow for Re-Tests | Hensel Phelps | [7 empty] | 20000 | 20000 | 0
990001 | Allow for 10 Additional Card Readers | Hensel Phelps | [7 empty] | 40000 | 40000 | 0
990002 | Allow for 10 Additional Security Cameras | Hensel Phelps | [7 empty] | 40000 | 40000 | 0
990003 | Allow to Furnish & Instal State Group 2 Equipment | Hensel Phelps | [7 empty] | 40000 | 40000 | 0
990007 | DSA Fees | Hensel Phelps | [7 empty] | 15000 | 15000 | 0
990011 | City of Fresno Street Imp FEE | Hensel Phelps | [7 empty] | 150000 | 150000 | 0
990012 | City of Fresno Flood Control FEE | Hensel Phelps | [7 empty] | 115440 | 115440 | 0
990014 | P G & E GAS | Hensel Phelps | [7 empty] | 10000 | 10000 | 0
990016 | A/E FEES | KMD | 2013-05-01 | [6 empty] | 5562654 | 5494654 | 68000
990017 | Model Costs | HPCC | [7 empty] | 0 | 11000 | -11000
990018 | 3D Coordination | Lucrosol | [7 empty] | 0 | 125000 | -125000
990019 | Soils Report | Technicon | [7 empty] | 35000 | 13655 | 21345
990020 | Civil Engineer | KMD | [7 empty] | W/Design | W/Design | W/Design
990021 | Hydrology Report ** w/Civil** | KMD | [7 empty] | W/Design | W/Design | W/Design
990022 | Arborist NONE | KMD | [7 empty] | W/Design | W/Design | W/Design
990023 | Peer Reviewers | KMD | [7 empty] | W/Design | W/Design | W/Design
990024 | Commissioning Agent BY OWNER | KMD | [7 empty] | W/Design | W/Design | W/Design
990025 | DVBE Outreach Consultant | Hensel Phelps | [7 empty] | 40000 | 40000 | 0
990026 | LOW VOLTAGE PEER REVIEW | Hensel Phelps | [7 empty] | 30000 | 30000 | 0
990027 | STRUCTURAL PEER REVIEW | Hensel Phelps | [7 empty] | 20000 | 20000 | 0
990028 | TAYLOR ENG PEER REVIEW | Hensel Phelps | [7 empty] | 20000 | 20000 | 0
990029 | MISC | Hensel Phelps | [7 empty] | 25000 | 25000 | 0
| Bonds & Insurance | [7 empty] | 2529715
991000 | 100% Perf and Pay Bond 1.05% | Flood & Peterson | [7 empty] | 1270500 | 1270500 | 0
991001 | ADD for OVER 24 months | Flood & Peterson | [7 empty] | 38115 | 38115 | 0
991002 | ADD For 2 Year Warranty .002 | Flood & Peterson | [7 empty] | 242000 | 242000 | 0
991004 | Builder's Risk Insurance by GC . | Flood & Peterson | [7 empty] | 979100 | 580164 | 398936
| Fee & Contingency | [7 empty] | 11596350
999000 | Contingency (Construction) | Hensel Phelps | [7 empty] | 2500000 | 2500000 | 0
999001 | Contingency (Design & Estimating) | Hensel Phelps | [7 empty] | 2997950 | 2997950 | 0
999004 | Software .0004 | Hensel Phelps | [7 empty] | 48400 | 48400 | 0
999006 | FEE 5% | Hensel Phelps | [7 empty] | 6050000 | 6050000 | 0
| TOTAL | [7 empty] | 113725108 | 113740991 | 107704706 | 4946285
| Buy-out Complete (%) | [9 empty] | 99.04%