## FSR Summary
Emeryville Medical Office Building
Financial Status Report
Updated: | 2017-02-07 09:27
Estimate Summary |  |  |  | Buyout Summary |  |  | Total
A | B | C |  | D | E | F | G
Buyout Complete?
DIV | Description | Design Development Budget |  |  | Subcontractor | Final GMP | Projected Gains / Losses
76500
|  | $/SF | Amount | (Y/N) | Name | Amount | Amount
DESIGN
0 | Site Survey, Geotechnical Report | 3.4859 | 266668 | Y | Hensel Phelps | 266668 | 0
0 | Schematic Design Development | 8.4789 | 648636 | Y | Hensel Phelps | 648636 | 0
0 | Design Development | 8.4789 | 648636 | Y | Hensel Phelps | 648636 | 0
0 | Construction Documents | 11.3052 | 864848 | Y | Hensel Phelps | 864848 | 0
0 | Construction Administration | 10.462 | 800344 | Y | Hensel Phelps | 800344 | 0
| Subtotal - DESIGN | 42.2109 | 3229132 |  |  | 3229132 | 0
PRECONSTRUCTION SERVICES
0 | Schedule Development | 1.1922 | 91200 | Y | Hensel Phelps | 91200 | 0
0 | Estimate Development | 1.4013 | 107200 | Y | Hensel Phelps | 107200 | 0
0 | Pre-Con General Conditions | 0.65359 | 50000 | Y | Hensel Phelps | 50000 | 0
0 | Field Investigation (laser scan) |  | 0 | N |  |  | 0
| Subtotal - PRE CON | 3.2471 | 248400 |  |  | 248400 | 0
GC
1 | General Conditions | 39.2157 | 3000000 | Y |  |  | 3000000
| Subtotal - GC | 39.2157 | 3000000 |  |  | 0 | 3000000
BUILDING & SITE
2 | Selective Demolition | 2.5914 | 198240 | Y | Wreck it Ralph | 182193 | 16047
3 | Concrete & Reinforcing | 6.315 | 483099 | Y | Hensel Phelps | 372820 | 110279
3 | Concrete Mockup Allowance | 0.26144 | 20000 | Y | Hensel Phelps | 20000 | 0
5 | Steel, Metal Deck, Stairs | 12.2231 | 935065 | Y | Perfection Erection | 861833 | 73232
5 | Metal Support Assemblies | 2.2876 | 175000 | N |  |  | 175000
5 | Architectural Woodwork | 12.3742 | 946623 | Y | AMD | 1049560 | -102937
7 | Roofing | 0.87712 | 67100 | Y | No Drips Roofing | 75750 | -8650
8 | Doors, Frames, Hardware | 28.7534 | 2199638 | Y | Argyle Doors | 1545268 | 654370
8 | Interior Glazing | 3.281 | 251000 | Y | Looking Glass, Inc | 395199 | -144199
8 | Interior Mock-up Allowance | 0.26144 | 20000 | N | TBD | 55000 | -35000
9 | Drywall / Framing | 26.1438 | 2000000 | N |  |  | 2000000
9 | Insulation Allowance | 1.0458 | 80000 | N | TBD | 80000 | 0
9 | Tile | 4.4649 | 341565 | Y | Stone Hard | 230121 | 111444
9 | Acoustical Ceiling | 13.0719 | 1000000 | N |  |  | 1000000
9 | Carpet, Resilient, Fluid Applied Flooring | 13.6278 | 1042528 | Y | Christian Brothers | 859027 | 183501
9 | Floor Leveling Allowance | 0.98039 | 75000 | Y | Christian Brothers | 75000 | 0
9 | Solid Surface Panels | 4.3917 | 335965 | Y | Desert Streams, Inc. | 193438 | 142527
9 | Paint & Wall Covering | 6.8156 | 521395 | Y | Desert Streams, Inc. | 385222 | 136173
9 | Final Cleaning | 2.1529 | 164700 | Y | Mr. Belvedere | 119755 | 44945
10 | Signage - Interior | 3.3875 | 259145 | Y | Marco Polo Signs | 213644 | 45501
10 | Building Specialties | 8.4967 | 650000 | N |  |  | 650000
11 | Healthcare Equipment Install | 2.9412 | 225000 | Y | Acme Health Supplies | 258144 | -33144
11 | ENT Microscope - Vibration Pads | 0.019608 | 1500 | N | TBD | 1489 | 11
11 | MRI Crane & Rigging | 0.19608 | 15000 | Y | Perfection Erection | 30000 | -15000
12 | Window Shades | 2.5291 | 193475 | Y | Peak-A-Boo Shades | 276484 | -83009
13 | Lead Shielding | 1.1111 | 85000 | N |  |  | 85000
14 | Elevator | 1.6652 | 127389 | Y | That'll Be Extra, Inc. | 197389 | -70000
21 | Fire Protection | 4.8902 | 374100 | Y | A-1 Steak Sauce | 374202 | -102
22 | Plumbing & Med Gas | 55.1333 | 4217697 | Y | Mario Bros. Plumping | 4224059 | -6362
23 | HVAC | 109.6993 | 8392000 | Y | Tin Knockers & Assoc. | 8481500 | -89500
26 | Electrical & Low Voltage Infrastructure | 68.9175 | 5272191 | Y | Cash Valley Electric | 5280953 | -8762
26 | Temp Lighting Allowance | 0.3268 | 25000 | Y | Cash Valley Electric | 25000 | 0
26 | Low Voltage Wiring | 0.19608 | 15000 | Y | Cash Valley Electric | 20000 | -5000
32 | Signage - Exterior | 1.7647 | 135000 | Y | Priax Signs | 42854 | 92146
32 | Canopy & Site Modifications | 3.6557 | 279660 | Y | Landscapes R Us | 279660 | 0
33 | Site Utilities | 4.7823 | 365849 | Y | Bali Construction | 385498 | -19649
| Subtotal - BUILDING & SITE | 411.633 | 31489924 |  |  | 26591062 | 4898862
PERMITS & FEES
90 | Plan Check and Permit Fees | 3.8943 | 297913 | Y | Owner | 297913 | 0
90 | Encroachment Permit | 0.55706 | 42615 | Y | Owner | 42615 | 0
| Subtotal - PERMITS | 4.4513 | 340528 | - | - | 340528 | 0
| CONTINGENCY / RESERVES | %
90 | Design | 3% | 954913.56 | Y | Hensel Phelps | 954913.56 | 0
90 | Buyout |  | 0 | Y | Hensel Phelps | 0 | 0
90 | Construction |  | 0 | Y | Hensel Phelps | 0 | 0
| Subtotal - CONTINGENCY | 12.4825 | 954913.56 | - | - | 954913.56 | 0
| INSURANCE & BONDS | %
90 | Builder's Risk | 0.5% | 190137 | Y | Owner | 190137 | 0
90 | GL Insurance | 0.53% | 233591 | Y | Hensel Phelps |  | 233591
90 | Bond | 0.615% | 271028 | Y | Hensel Phelps |  | 271028
90 | DIC (if needed) | 0% | 0 | Y | Hensel Phelps |  | 0
| Subtotal - BOND & INSURANCE | 9.0818 | 694756 | - | - | 190137 | 504619
| FEES | %
90 | Contractor's Fee |  | 0 | Y | Hensel Phelps | 0 | 0
| Subtotal - FEES | 0 | 0 | - | - | 0 | 0
| TOTAL CONSTRUCTION COST | 522.3223 | 39957653.56 | - | - | 31554172.56 | 8403481

## Sheet1
Final GMP Bid
Emeryville Medical Office Building | Bonds and Insurance Quote
Emeryville, CA | [5 empty] | 2017-02-09
|  | JOB DURATION | 437 | WORK DAYS
|  | INSURANCE BASED ON | 18 | MONTHS
|  | BASIS | UNIT COST | EXTENSION | REMARKS
TAXES
School Tax |  | - | 0% | N/A
Gross Receipts Tax |  | - | 0% | N/A
Misc. Taxes and Fees |  | - | 0% | N/A
TOTAL TAXES |  | - | - | 0
PERMITS
Building Permit |  | - | 0% | N/A
Offsite Engr Permit |  | - | 0% | N/A
Other Permits |  | - | 0% | N/A
TOTAL BUILDING PERMITS |  | - | - | 0
BONDS
Payment and Performance |  | - | 0.62% | 271028 | 6.15 | per $1000 per year
Plus Over 18 Mo Surcharge |  | - | 4% |  | Add'l mos | 1% per Additional Mo
CA Insurance Guarantee Fund |  |  | 0% | N/A
Extended Warrranty over 12 Mo |  |  | 0% | N/A | 0 | $1.00 per $1000 per yr
TOTAL BONDS |  | - | - | 271028
BUILDERS RISK INSURANCE
Builder's Risk |  | - | 0% | N/A | With Owner
Earthquake Coverage |  | - | 0% | N/A
Tornado Insurance |  | - | 0% | N/A
TOTAL BUILDER'S RISK |  | - | - | 0
LIABILITY INSURANCE
General Liability |  | - | 0.5301% | 233591 | 5.3005 | per $1000 per year
Plus Over 18 Mo Surcharge |  | - | 4% |  | Add'l mos | 1% per Additional Mo
Errors & Omissions |  | - | 0% | N/A
Professional Liability |  | - | 0% | N/A
Railroad Protective |  | - | 0% | N/A
Longshoremen's |  | - | 0% | N/A
Misc. Insurance |  | - | 0% | N/A
TOTAL LIABILITY INSURANCE |  | - | - | 233591
|  |  | TOTAL BONDS AND INSURANCE : | 504619
BONDS AND INSURANCE BACKUP |  |  |  |  | EXTENDED BY:
CHECKED BY: