## Sheet1
UC Riverside - Multidisciplinary Research Building I
|  |  |  | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | Staff Totals
Month: | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
Month #:
Staff Member
Project Manager | 0.25 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [7 empty] | 30.75
Project Superintendent |  | 0.25 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [7 empty] | 30.25
Area Superintendent 1 | [39 empty] | 22 | bar: 2020 MAR to 2021 DEC
Area Superintendent 2 | [39 empty] | 26 | bar: 2020 MAR to 2022 APR
Area Superintendent 3 | [39 empty] | 25 | bar: 2020 APR to 2022 APR
Area Superintendent 4 | [39 empty] | 25 | bar: 2020 APR to 2022 APR
Project Engineer | [39 empty] | 31 | bar: NOV to 2022 MAY
Project Engineer | [39 empty] | 30 | bar: NOV to 2022 APR
Office Engineer | [39 empty] | 29 | bar: DEC to 2022 APR
Office Engineer | [39 empty] | 28 | bar: DEC to 2022 MAR
Field Engineer | [39 empty] | 26 | bar: 2020 FEB to 2022 MAR
Field Engineer | [39 empty] | 27 | bar: 2020 FEB to 2022 APR
QC Engineer | [39 empty] | 19 | bar: 2020 MAY to 2021 NOV
Design Manager | OCT: 0.5; NOV: 1; DEC: 1; 2020 JAN: 1; 2020 FEB: 1; 2020 MAR: 1; 2020 APR: 1; 2020 MAY: 1; 2020 JUN: 1; 2020 JUL: 1; 2020 AUG: 1; 2020 SEP: 1; 2020 OCT: 0.5 | 12
Safety Engineer | [39 empty] | 24 | bar: 2020 MAY to 2022 APR
Intern (Hourly) | [39 empty] | 0
Office Manager (Hourly) |  |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [7 empty] | 26.5