## GCs for main project
X.3.4 UCR MRB GENERAL CONDITIONS ESTIMATE
Cells highlighted in yellow can be edited
|  |  | Labor |  | Material |  | Equip/Subs
Item | QTY | UNIT | $/UNIT | AMT | $/UNIT | AMT | $/UNIT | AMT | Total
SUPERVISION
Project Manager | 30.75 | MO | 14000 | 430500 |  |  |  |  | 430500
Project Superintendent | 30.25 | MO | 14000 | 423500 |  |  |  |  | 423500
Project Engineer | 61 | MO | 11500 | 701500 |  |  |  |  | 701500
Office Engineer | 57 | MO | 9700 | 552900 |  |  |  |  | 552900
QC Engineer | 19 | MO | 11500 | 218500 |  |  |  |  | 218500
Design Manager | 12 | MO | 9700 | 116400 |  |  |  |  | 116400
Office Manager | 26.5 | MO | 6800 | 180200 |  |  |  |  | 180200
Travel Expenses | 5 | MO |  |  | 3000 | 15000 |  |  | 15000
Moving & Relocation | 4 | LSUM |  |  | 2500 | 10000 |  |  | 10000
Total |  |  |  | 2623500 |  | 25000 |  | 0 | 2648500
ENGINEERING & SURVEY WORK
Area Superintendent | 98 | MO | 12500 | 1225000 |  |  |  |  | 1225000
Field Engineer | 53 | MO | 9500 | 503500 |  |  |  |  | 503500
Safety Engineer | 24 | MO | 11500 | 276000 |  |  |  |  | 276000
Intern | 0 | MO | 2600 | 0 |  |  |  |  | 0
Intern Housing | 0 | MO |  |  |  |  | 2600 | 0 | 0
Field Engineer Equipment | 22 | MO |  |  | 100 | 2200 | 1000 | 22000 | 24200
Professional Surveyor | 1 | LSUM |  |  |  |  | 10000 | 10000 | 10000
Print Drawings | 1 | LSUM |  |  | 5000 | 5000 |  |  | 5000
BIM Support | 5 | MO |  |  | 10000 | 50000 |  |  | 50000
Total |  |  |  | 2004500 |  | 7200 |  | 32000 | 2043700
SAFETY
Drug Testing | 2 | EA |  |  | 400 | 800 |  |  | 800
Safety Incentives | 23 | MO |  |  | 200 | 4600 |  |  | 4600
Employee Training | 23 | MO |  |  | 250 | 5750 | 275 | 6325 | 12075
First Aid Supplies | 1 | LS |  |  | 2500 | 2500 |  |  | 2500
Fire Extinguishers (1/3k SF) | 65 | EA | 25 | 1625 | 50 | 3250 |  |  | 4875
Heat Stress/Lunch Tent | 1 | LS |  |  | 5000 | 5000 |  |  | 5000
Lunch Area Supplies/Maintenance | 23 | MO | 1000 | 23000 |  |  |  |  | 23000
Total |  |  |  | 24625 |  | 21900 |  | 6325 | 52850
TEMP FACILITIES
Office Trailer | 25 | MO |  |  |  |  | 10000 | 250000 | 250000
Office Trailer - Set Up/Removal | 1 | EA |  |  |  |  | 25898 | 25898 | 25898
Janitorial Service for Office Space | 25 | MO |  |  |  |  | 1500 | 37500 | 37500
Temp Toilets | 24 | MO |  |  |  |  | 2000 | 48000 | 48000
Wash Stations | 24 | MO |  |  |  |  | 500 | 12000 | 12000
Professional Photos | 1 | LSUM |  |  | 2500 | 2500 |  |  | 2500
Bulletin Boards | 1 | EA |  |  | 2000 | 2000 |  |  | 2000
Project Sign | 1 | EA |  |  | 800 | 800 |  |  | 800
Office Furniture | 1 | LSUM |  |  | 10000 | 10000 |  |  | 10000
Office Supplies | 24 | MO |  |  | 600 | 14400 |  |  | 14400
Office Equipment | 24 | MO |  |  | 3000 | 72000 | 700 | 16800 | 88800
Certified Payroll Reporting | 24 | MO |  |  |  |  | 700 | 16800 | 16800
Computers | 15 | EA |  |  | 3000 | 45000 |  |  | 45000
Printers/Plotters | 24 | MO |  |  | 5600 | 134400 |  |  | 134400
Postage & Shipping | 24 | MO |  |  | 700 | 16800 |  |  | 16800
Telephone & Internet Service Install | 1 | LSUM |  |  |  |  | 15000 | 15000 | 15000
Telephone & Internet Rental | 24 | MO |  |  |  |  | 1800 | 43200 | 43200
Temp Fence | 2500 | LF |  |  |  |  | 10 | 25000 | 25000
Relocate Temp Fence | 4 | EA |  |  |  |  | 1000 | 4000 | 4000
SWPPP Setup | 1 | LSUM |  |  |  |  | 5000 | 5000 | 5000
SWPPP Maintenance - 20 hrs/month | 22 | MO | 3500 | 77000 |  |  |  |  | 77000
Dust Control - 20 hrs/month | 12 | MO | 2500 | 30000 |  |  |  |  | 30000
Drinking Water Service | 22 | MO |  |  | 50 | 1100 |  |  | 1100
Ice, Jugs, Cups | 22 | MO |  |  | 200 | 4400 |  |  | 4400
Office Coffee & Cups | 24 | MO |  |  | 500 | 12000 |  |  | 12000
Temp Asphalt Parking Area | 1 | LSUM |  |  |  |  | 40000 | 40000 | 40000
Street Sweeper | 75 | DAY |  |  |  |  | 500 | 37500 | 37500
Construction Power & Lights Set Up | 1 | LSUM |  |  |  |  | 30000 | 30000 | 30000
Construction Power & Lights Maintenance | 22 | MO |  |  |  |  | 1000 | 22000 | 22000
Total |  |  |  | 107000 |  | 315400 |  | 628698 | 1051098
BUILDING SERVICES
Weekly Cleanup (2 man days/wk) | 100 | WK | 1800 | 180000 | 100 | 10000 |  |  | 190000
Dumpster Rental - 40 CUYD | 250 | PULL |  |  |  |  | 500 | 125000 | 125000
Final Clean-Up - BLDG | 230000 | SF |  |  |  |  | 0.6 | 138000 | 138000
Final Clean-Up - SITE | 2.5 | ACRE |  |  |  |  | 1500 | 3750 | 3750
Total |  |  |  | 180000 |  | 10000 |  | 266750 | 456750
FORKLIFT, MAJOR EQUIPMENT & TOOLS
Gradall - 6000# Forklift (1/2 time operation) | 22 | MO | 5500 | 121000 | 1000 | 22000 | 2200 | 48400 | 191400
Water Truck 2500 GAL | 22 | MO |  |  | 750 | 16500 | 2000 | 44000 | 60500
Generator Unit Rental | 3 | MO |  |  | 400 | 1200 | 1500 | 4500 | 5700
250 CFM Compressor | 6 | MO |  |  | 500 | 3000 | 1500 | 9000 | 12000
Misc. Power Equipment | 1 | LSUM |  |  | 5000 | 5000 |  |  | 5000
Small Tools | 1 | LSUM |  |  | 10000 | 10000 |  |  | 10000
Repairs & Maintenance | 1 | LSUM |  |  |  |  | 20000 | 20000 | 20000
Total |  |  |  | 121000 |  | 57700 |  | 125900 | 304600
TRANSPORTATION
Pickup | 22 | MO |  |  |  |  | 625 | 13750 | 13750
Sedan | 22 | MO |  |  |  |  | 625 | 13750 | 13750
FE Carts | 22 | MO |  |  |  |  | 700 | 15400 | 15400
Vehicle Fuel | 22 | MO |  |  | 600 | 13200 |  |  | 13200
Vehicle Maintenance | 22 | MO |  |  | 100 | 2200 |  |  | 2200
Total |  |  |  | 0 |  | 15400 |  | 42900 | 58300
SUMMARY
SUPERVISION |  | LSUM |  | 2623500 |  | 25000 |  | 0 | 2648500
ENGINEERING & SURVEY WORK |  | LSUM |  | 2004500 |  | 7200 |  | 32000 | 2043700
SAFETY |  | LSUM |  | 24625 |  | 21900 |  | 6325 | 52850
TEMP FACILITIES |  | LSUM |  | 107000 |  | 315400 |  | 628698 | 1051098
BUILDING SERVICES |  | LSUM |  | 180000 |  | 10000 |  | 266750 | 456750
FORKLIFT, MAJOR EQ, & TOOLS |  | LSUM |  | 121000 |  | 57700 |  | 125900 | 304600
TRANSPORTATION |  | LSUM |  | 0 |  | 15400 |  | 42900 | 58300
SALES TAX ON MATERIAL | 8.75% | PCT |  |  | 452600 | 39602.5 |  |  | 39602.5
TOTAL |  |  |  | 5060625 |  | 492202.5 |  | 1102573 | 6655400.5
[7 empty] | Check: | 6655400.5 | Good