## GCs for Vivarium Buildout
X.3.5 UCR MRB VIVARIUM SHELL/IMAGING CORE BUILDOUT GENERAL CONDITIONS ESTIMATE TEMPLATE
|  |  | Labor |  | Material |  | Equip/Subs
Item | QTY | UNIT | $/UNIT | AMT | $/UNIT | AMT | $/UNIT | AMT | Total
SUPERVISION
Project Manager |  | MO | 14000 | 0 |  |  |  |  | 0
Project Superintendent |  | MO | 14000 | 0 |  |  |  |  | 0
Project Engineer |  | MO | 11500 | 0 |  |  |  |  | 0
Office Engineer |  | MO | 9700 | 0 |  |  |  |  | 0
QC Engineer |  | MO | 11500 | 0 |  |  |  |  | 0
Design Manager |  | MO | 9700 | 0 |  |  |  |  | 0
Office Manager |  | MO | 6800 | 0 |  |  |  |  | 0
Toll Road/Parking |  | MO |  |  | 200 | 0 |  |  | 0
Moving & Relocation |  | LSUM |  |  | 2500 | 0 |  |  | 0
Total |  |  |  | 0 |  | 0 |  | 0 | 0
ENGINEERING & SURVEY WORK
Area Superintendent |  | MO | 12500 | 0 |  |  |  |  | 0
Field Engineer |  | MO | 9500 | 0 |  |  |  |  | 0
Safety Engineer |  | MO | 11500 | 0 |  |  |  |  | 0
Intern |  | MO | 2600 | 0 |  |  |  |  | 0
Intern Housing |  | MO |  |  |  |  | 2600 | 0 | 0
Field Engineer Equipment |  | MO |  |  | 100 | 0 | 1000 | 0 | 0
Professional Surveyor |  | LSUM |  |  |  |  | 10000 | 0 | 0
Print Drawings |  | LSUM |  |  | 5000 | 0 |  |  | 0
BIM Support |  | MO |  |  | 10000 | 0 |  |  | 0
Total |  |  |  | 0 |  | 0 |  | 0 | 0
SAFETY
Drug Testing |  | EA |  |  | 400 | 0 |  |  | 0
Safety Incentives |  | MO |  |  | 200 | 0 |  |  | 0
Employee Training |  | MO |  |  | 250 | 0 | 275 | 0 | 0
First Aid Supplies |  | LS |  |  | 2500 | 0 |  |  | 0
Fire Extinguishers (1/3k SF) |  | EA | 25 | 0 | 50 | 0 |  |  | 0
Heat Stress/Lunch Tent |  | LS |  |  | 5000 | 0 |  |  | 0
Lunch Area Supplies/Maintenance |  | MO | 1000 | 0 |  |  |  |  | 0
Total |  |  |  | 0 |  | 0 |  | 0 | 0
TEMP FACILITIES
Office Trailer |  | MO |  |  |  |  | 10000 | 0 | 0
Office Trailer - Set Up/Removal |  | EA |  |  |  |  | 25898 | 0 | 0
Janitorial Service for Office Space |  | MO |  |  |  |  | 1000 | 0 | 0
Temp Toilets |  | MO |  |  |  |  | 2000 | 0 | 0
Wash Stations |  | MO |  |  |  |  | 200 | 0 | 0
Professional Photos |  | LSUM |  |  | 2500 | 0 |  |  | 0
Bulletin Boards |  | EA |  |  | 2000 | 0 |  |  | 0
Project Sign |  | EA |  |  | 800 | 0 |  |  | 0
Office Furniture |  | LSUM |  |  | 10000 | 0 |  |  | 0
Office Supplies |  | MO |  |  | 600 | 0 |  |  | 0
Office Equipment |  | MO |  |  | 500 | 0 | 100 | 0 | 0
Certified Payroll Reporting |  | MO |  |  |  |  | 700 | 0 | 0
Computers |  | EA |  |  | 3000 | 0 |  |  | 0
Printers/Plotters |  | MO |  |  | 2000 | 0 |  |  | 0
Postage & Shipping |  | MO |  |  | 700 | 0 |  |  | 0
Telephone & Internet Service Install |  | LSUM |  |  |  |  | 15000 | 0 | 0
Telephone & Internet Rental |  | MO |  |  |  |  | 1000 | 0 | 0
Temp Fence |  | LF |  |  |  |  | 10 | 0 | 0
Relocate Temp Fence |  | EA |  |  |  |  | 1000 | 0 | 0
SWPPP Setup |  | LSUM |  |  |  |  | 1000 | 0 | 0
SWPPP Maintenance - 10 hrs/month |  | MO | 500 | 0 |  |  |  |  | 0
Dust Control - 20 hrs/month |  | MO | 2500 | 0 |  |  |  |  | 0
Drinking Water Service |  | MO |  |  | 50 | 0 |  |  | 0
Ice, Jugs, Cups |  | MO |  |  | 200 | 0 |  |  | 0
Office Coffee & Cups |  | MO |  |  | 500 | 0 |  |  | 0
Temp Asphalt Parking Area |  | LSUM |  |  |  |  | 40000 | 0 | 0
Street Sweeper |  | DAY |  |  |  |  | 200 | 0 | 0
Construction Power & Lights Set Up |  | LSUM |  |  |  |  | 30000 | 0 | 0
Construction Power & Lights Maintenance |  | MO |  |  |  |  | 1000 | 0 | 0
Total |  |  |  | 0 |  | 0 |  | 0 | 0
BUILDING SERVICES
Weekly Cleanup (1 man days/wk) |  | WK | 1000 | 0 | 100 | 0 |  |  | 0
Dumpster Rental - 40 CUYD |  | PULL |  |  |  |  | 500 | 0 | 0
Final Clean-Up - BLDG |  | SF |  |  |  |  | 0.6 | 0 | 0
Final Clean-Up - SITE |  | ACRE |  |  |  |  | 1500 | 0 | 0
Total |  |  |  | 0 |  | 0 |  | 0 | 0
FORKLIFT, MAJOR EQUIPMENT & TOOLS
Gradall - 6000# Forklift (1/2 time operation) |  | MO | 5500 | 0 | 1000 | 0 | 2200 | 0 | 0
Water Truck 2500 GAL |  | MO |  |  | 750 | 0 | 2000 | 0 | 0
Generator Unit Rental |  | MO |  |  | 400 | 0 | 1500 | 0 | 0
250 CFM Compressor |  | MO |  |  | 500 | 0 | 1500 | 0 | 0
Misc. Power Equipment |  | LSUM |  |  | 5000 | 0 |  |  | 0
Small Tools |  | LSUM |  |  | 1000 | 0 |  |  | 0
Repairs & Maintenance |  | LSUM |  |  |  |  | 1000 | 0 | 0
Total |  |  |  | 0 |  | 0 |  | 0 | 0
TRANSPORTATION
Pickup |  | MO |  |  |  |  | 625 | 0 | 0
Sedan |  | MO |  |  |  |  | 625 | 0 | 0
FE Carts |  | MO |  |  |  |  | 700 | 0 | 0
Vehicle Fuel |  | MO |  |  | 600 | 0 |  |  | 0
Vehicle Maintenance |  | MO |  |  | 100 | 0 |  |  | 0
Total |  |  |  | 0 |  | 0 |  | 0 | 0
SUMMARY
SUPERVISION |  | LSUM |  | 0 |  | 0 |  | 0 | 0
ENGINEERING & SURVEY WORK |  | LSUM |  | 0 |  | 0 |  | 0 | 0
SAFETY |  | LSUM |  | 0 |  | 0 |  | 0 | 0
TEMP FACILITIES |  | LSUM |  | 0 |  | 0 |  | 0 | 0
BUILDING SERVICES |  | LSUM |  | 0 |  | 0 |  | 0 | 0
FORKLIFT, MAJOR EQ, & TOOLS |  | LSUM |  | 0 |  | 0 |  | 0 | 0
TRANSPORTATION |  | LSUM |  | 0 |  | 0 |  | 0 | 0
SALES TAX ON MATERIAL | 8.75% | PCT |  |  | 0 | 0 |  |  | 0
TOTAL |  |  |  | 0 |  | 0 |  | 0 | 0
[7 empty] | Check: | 0 | Good