## 1A. Self Perform Summary
ASC Region 7 Commercial Competition
Change Management: Owner Change Order Request
Description: | Cost for the buildout of the vivarium in the level 1 shell space.
Reference: |  | Initiating Document: | Bulletin 16 | CE # | 1 | PCCO # | 1
Hensel Phelps Costs
1 | Labor |  |  |  |  | $
2 | Material |  |  |  |  | $
3 | Freight |  |  |  |  | $
4 | Tax |  |  |  |  | $
5 | Subtotal (Lines 1 - 4) |  |  |  |  | $
Subcontractor Costs
6 | Plumbing |  |  |  | GIVEN | $ | 469240
7 | Mechanical |  |  |  | GIVEN | $ | 644528
8 | Electrical |  |  |  | GIVEN | $ | 528050
9 | Signage |  |  |  | GIVEN | $ | 4347.42
10 | Paint |  |  |  | GIVEN | $ | 27894
11 | Fire Protection |  |  |  | GIVEN | $ | 111109
12 | Ceilings |  |  |  | GIVEN | $ | 6998
13 | Cleaning |  |  |  | GIVEN | $ | 1990.56
14 | Framing |  |  |  |  | $
15 | Epoxy Flooring |  |  |  |  | $
16 | Subtotal (Lines 6 - 15) |  |  |  |  | $
Total Costs
17 | Hensel Phelps & Subcontractor Direct Cost Total (Lines 5 & 16) |  |  |  |  | $
18 | Hensel Phelps Bonds & Insurance |  |  |  | 1.1% | $
19 | Contractor Fee |  |  |  | 6% | $
20 | Total |  |  |  |  | $

## 1B. Subcontracted Summary
ASC Region 7 Commercial Competition
Change Management: Owner Change Order Request
Description: | Cost for the buildout of the vivarium in the level 1 shell space.
Reference: |  | Initiating Document: | Bulletin 16 | CE # | 1 | PCCO # | 1
Subcontractor Costs
1 | Plumbing |  |  |  | GIVEN | $ | 469240
2 | Mechanical |  |  |  | GIVEN | $ | 644528
3 | Electrical |  |  |  | GIVEN | $ | 528050
4 | Signage |  |  |  | GIVEN | $ | 4347.42
5 | Paint |  |  |  | GIVEN | $ | 27894
6 | Fire Protection |  |  |  | GIVEN | $ | 111109
7 | Ceilings |  |  |  | GIVEN | $ | 6998
8 | Cleaning |  |  |  | GIVEN | $ | 1990.56
9 | Framing |  |  |  |  | $
10 | Specialties |  |  |  |  | $
11 | Epoxy Flooring |  |  |  |  | $
12 | Subtotal (Lines 1 - 11) |  |  |  |  | $
Total Costs
13 | Subcontractor Direct Cost Total |  |  |  |  | $
14 | Hensel Phelps Bonds & Insurance |  |  |  | 1.1% | $
15 | Contractor Fee |  |  |  | 6% | $
16 | Total |  |  |  |  | $

## 2. Labor & Material
CE#
DATE:
Labor & Material Worksheet
[5 empty] | D |  |  | I | N
|  | A | B | C | ( A * C ) | G | H | ( A * G * H ) | (D+I)
Item |  |  |  | Material |  | Craft Labor Team
# | Description | Quantity | Unit | Cost/Unit | Cost | MH/Unit | Rate | Cost | TOTAL
Labor & Material
1 | SANIRAIL CRASH RAIL | 0 | LF | 50 |  | 0.1 | 140
2 | 3 1/2" X 3 1/2" SS 4' CG | 0 | EA | 175 |  | 0.1 | 70
3 | 10LB FIRE EXTINGUISHER | 0 | EA | 356 |  | 0.05 | 70
4 | ACROVYN 4000 - WP (4x10 SHEETS) | 0 | SF | 7 |  | 0.1 | 140
5 | FIRE EXTINGUISHER CABINET | 0 | EA | 243 |  | 1 | 70
| Subtotal |  |  |  | 0 |  |  | 0 | 0
[8 empty] | Freight | 2500 | GIVEN
[8 empty] | Tax | 0
[8 empty] | OH&P | 0
[8 empty] | Total | 2500

## 3. Framing
Subcontractor Summary
Framing
Description: | Install additional framing and drywall throughout the updated vivarium buildout in the shell space.
Reference: |  | Initiating Document: | Bulletin 16 | CE # | 1 | PCCO # | 1
Subcontractor Costs
1 | Labor & Material |  |  |  |  | $
2 | Equipment |  |  |  |  | $
3 | 3rd Tier Sub Costs (Sub Name) |  |  |  |  | $
4 | Subtotal (Lines 1 - 3) |  |  |  |  | $
5 | Taxes |  |  |  |  | $
6 | Overhead & Profit |  |  |  |  | $
7 | Subtotal (Lines 4 - 6) |  |  |  |  | $
8 | Bonds and Insurance |  |  |  |  | $
9 | Total |  |  |  |  | $

## 4. Specialties + Casework
Subcontractor Summary
Specialties
Description: | Install handrails, wall protection, fire extinguishers, fire extinguisher cabinets, lockers, towel dispensers, and corner guards throughout the vivarium
Reference: |  | Initiating Document: | Bulletin 16 |  | CE # | 1 | PCCO # | 1
includes isec and l2
Subcontractor Costs
1 | Labor | [5 empty] | $
2 | Material | [5 empty] | $
3 | Equipment/Freight | [5 empty] | $
4 | 3rd Tier Sub Costs (Sub Name) | [5 empty] | $
5 | Subtotal (Lines 1 - 4) | [5 empty] | $
6 | Taxes | [5 empty] | $
7 | Overhead & Profit | [5 empty] | $
8 | Subtotal (Lines 5 - 7) | [5 empty] | $
9 | Bonds and Insurance | [5 empty] | $
10 | Total | [5 empty] | $

## 5. Flooring
Subcontractor Summary
Epoxy Flooring
Description: | Install epoxy flooring throughout the vivarium buildout
Reference: |  | Initiating Document: | Bulletin 16 | CE # | 1 | PCCO # | 1
Subcontractor Costs
1 | Labor |  |  |  |  | $
2 | Material |  |  |  |  | $
3 | Equipment |  |  |  |  | $
4 | 3rd Tier Sub Costs (Sub Name) |  |  |  |  | $
5 | Subtotal (Lines 1 - 4) |  |  |  |  | $
6 | Taxes |  |  |  |  | $
7 | Overhead & Profit |  |  |  |  | $
8 | Subtotal (Lines 5 - 7) |  |  |  |  | $
9 | Bonds and Insurance |  |  |  |  | $
10 | Total |  |  |  |  | $