## Sheet1
|  | Risk Mitigation Matrix |  |  |  | Reference Document X.5.2
| Risk Type | Risk Description | Potential Consequence | Likelihood | Responsible Party | Risk Mitigation Strategy
| Catagories: | Provide: List of Descriptions - | Provide: List of Consequences - | High/Med/Low | Owner/Arch/GC/Sub | Provide: List of Strategies -
1 | Systems Integration - Ensure that all rail, train and building systems work are integrated for safe and efficient operation
2 | Construction Schedule and Sequencing - Complete the physical construction of the OMF project within the boundary posts of design/permiting and systems integration
3 | Labor, Materials and Equipment - Ensure that there is an adequate supply of skilled labor, materials and equipment given the booming construction market in the PNW along with known future construction
4 | Environmental Risks -Soil & Site Work, containment, treatment and discharge of stormwater
5 | Exterior Enclosure - Ensure the exterior enclosures of the OMF and MOW buildings are complete prior to rainy season
6