## Coversheet
CHANGE ORDER REQUEST
1. PROJECT: |  |  | 2. CONTRACTOR: |  | 3. PROJECT. |  |  | 4. REQUEST NO:
Sunnyvale Civic Center |  |  | Hensel Phelps |  | Sunnyvale City Hall |  |  | CE 0335
|  |  | CE 0335 - Turnstiles PCO 148 |  | 5. CONTRACT: |  |  | 6. PROPOSAL DATE
[5 empty] | RC2023 |  |  | 2023-01-31
COST SUMMARY
FOR CHANGE WORK DIRECTLY PERFORMED BY THE UNDERSIGNED CONTRACTOR
A | HPCC Direct Labor HP 21% Direct Labor Markup (Includes Bond) | [5 empty] | 0
B | HP 21% Direct Labor Markup (Includes Bond) | [5 empty] | 0
C | Material/Equipment Including Tax HP 16% Direct Material/Equipment Markup (Includes Bond) | [5 empty] | 0
D | HP 16% Direct Material/Equipment Markup (Includes Bond) | [5 empty] | 0
E | Direct Labor/Material/Equipment TOTAL Markup on Direct Labor/Material/Equipment TOTAL Total | [5 empty] | 0
F | Markup on Direct Labor/Material/Equipment TOTAL | [5 empty] | 0
G | Total | [5 empty] | 0
FOR CHANGE WORK TO BE PERFORMED BY OTHERS, PER PROPOSALS AND DETAILED BREAKDOWNS ATTACHED:
Company Name |  |  |  | TRADE/SCOPE OF WORK |  |  |  |  | AMOUNT
1 | Acoustical Cielings |  |  | Remove and reinstall ceiling tiles in lobby for fire alarm/electrical access (labor only) |  |  |  |  | 2515.2
2 | Painting |  |  | Sand, prime and repaint ceiling patches for fire alarm/electrical access. |  |  |  |  | 2200.9831
3 | Framing |  |  | Drywall Patch and Repair Level 4 Ceiling after overhead electrical work |  |  |  |  | 0
4 | Hensel Phelps |  |  | Deck Scanning for Glass Railing Installation Intermittent and Final Clean Protection of exisiting finishes |  |  |  |  | 20654.9476
5 | Millwork |  |  | North Side - Remove/Modify/Re-Install Exisiting Wood Slat Wall Paneling South Side - Remove/Re-Install Exisiting Wood Slat Wall Paneling |  |  |  |  | 0
6 | Electrical w/ 2nd Tier Telecommunication |  |  | Provide raceway for security inputs to Turnstiles Provide 120vac standby power for (2) Turnstiles Raceway and cable for fire alarm inputs to Turnstiles Install (2) fire alarm relays and program fire alarm system (programming by EMS) |  |  |  |  | 0
| Electical (2nd Tier Audio Visuals Only) | [7 empty] | 0
| Electrical (2nd Tier Fire Alarm Only) | [7 empty] | 0
7 | Security Electronics w/ 2nd Tier Specialties |  |  | Install (2) card readers on the 4th floor to control access from lobby |  |  |  |  | 15339.4091
| Security Electronics (2nd Tier Programming) | [7 empty] | 3931.2
8 | Glazing w/ 2nd Tier Turnstile Installer |  |  | Provide and Install turnstiles and glass guardrail per PCO 148 Turnstile Protection Handling, Transporiting and Delivery of Turnstile |  |  |  |  | 0
Trade Partner TOTAL - Lines 1 - 11 (WITH MARK-UP; 20% Labor, 15% Materials & Equipment, 6% on tier) | [9 empty] | 44641.7398
SUBTOTAL AMOUNT - Lines A - D & 1 - 11 (Includes all Trade Partner and self work with markups) | [9 empty] | 44641.7398
CONTRACTOR MARK-UP (6% on Trade Partner(s)) | [9 empty] | 0
TOTAL INCREASE OR DECREASE OF CONTRACT PRICE | [9 empty] | 44641.7398
TOTAL INCREASE OR DECREASE OF CONTRACT SHCEDULE | [9 empty] | 0
Hensel Phelps
SUBMITTED BY: |  | TEAM NAME HERE
2023-01-31
SIGNATURE / DATE

## Framing
Fill in highlighted fields ONLY
COST BREAKDOWN FORM FOR CONTRACT MODIFICATIONS
THIS FORM SHALL BE USED FOR ALL CHANGES TO THE CONTRACT
One separate form shall be used by each first tier Trade Partner and each lower tier Trade Partner.
PCO/CO Number: |  | PCO 148 | Date: | 2023-01-31 |  | Contract Number 26637
Name of Trade Partner: |  | Framing
Description of Change:
Drywall Patch and Repair Level 4 Ceiling after overhead electrical work
Trade Partner AND TIER SUNCONTRACTOR WORK TOTALS | [7 empty] | Revisions/Comments
1. Labor Costs (see attached summary sheet ) |  |  |  |  | Line A + E | 0
2. Equipment (see attached summary sheet) |  |  |  |  | Line B + F | 0
3. Materials (see attached summary sheet) |  |  |  |  | Line (C + G) 9.00% | 0
4. Trade Partner and Tier Trade Partner Overhead |  |  |  |  | 20% of Line 1 15% of Line 2 & 3 | 0
5. Other Costs (no markup allowed) |  |  |  |  | Line D + H | 0
6. Trade Partner Mark-up on Tier Trade Partner |  |  |  |  | 6% of Tier Sub Direct Costs | 0
7. SUBTOTAL (ADD LINES 1 - 6) | [6 empty] | 0
8. Contractor Markup |  |  |  |  | 6% of All Subs Direct Costs | 0
9. Total Cost of Work |  |  |  |  | Line 7 + 8 |  | 0
Trade Partner
DESCRIPTION | [7 empty] | COST
A) Labor | [7 empty] | 0
20% Markup on Direct Labor | [7 empty] | 0
B) Equipment | [7 empty] | 0
15% Markup on Direct Equipment | [7 empty] | 0
C) Material | [7 empty] | 0
9% | Tax on Material | [6 empty] | 0
15% Markup on Direct Material | [7 empty] | 0
D) Other Costs (no markup allowed) | [7 empty] | 0
6% Markup on Tier Sub | [7 empty] | 0
Subtotal (without markups) | [7 empty] | 0
Markup Total | [7 empty] | 0
TOTAL Trade Partner COSTS | [7 empty] | 0
LOWER TIER Trade Partner
DESCRIPTION | [7 empty] | COST
E) Labor | [7 empty] | 0
20% Markup on Direct Labor | [7 empty] | 0
F) Equipment | [7 empty] | 0
15% Markup on Direct Equipment | [7 empty] | 0
G) Material | [7 empty] | 0
9% | Tax on Material | [6 empty] | 0
15% Markup on Direct Material | [7 empty] | 0
H) Other Costs (no markup allowed) | [7 empty] | 0
Subtotal (without markups) | [7 empty] | 0
Markup Total | [7 empty] | 0
TOTAL TIER Trade Partner COSTS | [7 empty] | 0
USE ADDITIONAL SHEETS AS NECESSARY

## Millwork
Fill in highlighted fields ONLY
COST BREAKDOWN FORM FOR CONTRACT MODIFICATIONS
THIS FORM SHALL BE USED FOR ALL CHANGES TO THE CONTRACT
One separate form shall be used by each first tier Trade Partner and each lower tier Trade Partner.
PCO/CO Number: |  | XX.XX | Date: | XX/XX/XXX |  | Contract Number 26637
Name of Trade Partner: |  | Millwork
Description of Change:
North Side - Remove/Modify/Re-Install Exisiting Wood Slat Wall Paneling South Side - Remove/Re-Install Exisiting Wood Slat Wall Paneling
Trade Partner AND TIER SUNCONTRACTOR WORK TOTALS | [7 empty] | Revisions/Comments
1. Labor Costs (see attached summary sheet ) |  |  |  |  | Line A + E | 0
2. Equipment (see attached summary sheet) |  |  |  |  | Line B + F | 0
3. Materials (see attached summary sheet) |  |  |  |  | Line (C + G) 9.00% | 0
4. Trade Partner and Tier Trade Partner Overhead |  |  |  |  | 20% of Line 1 15% of Line 2 & 3 | 0
5. Other Costs (no markup allowed) |  |  |  |  | Line D + H | 0
6. Trade Partner Mark-up on Tier Trade Partner |  |  |  |  | 6% of Tier Sub Direct Costs | 0
7. SUBTOTAL (ADD LINES 1 - 6) | [6 empty] | 0
8. Contractor Markup |  |  |  |  | 6% of All Subs Direct Costs | 0
9. Total Cost of Work |  |  |  |  | Line 7 + 8 |  | 0
Trade Partner
DESCRIPTION | [7 empty] | COST
A) Labor | [7 empty] | 0
20% Markup on Direct Labor | [7 empty] | 0
B) Equipment | [7 empty] | 0
15% Markup on Direct Equipment | [7 empty] | 0
C) Material | [7 empty] | 0
9% | Tax on Material | [6 empty] | 0
15% Markup on Direct Material | [7 empty] | 0
D) Other Costs (no markup allowed) | [7 empty] | 0
6% Markup on Tier Sub | [7 empty] | 0
Subtotal (without markups) | [7 empty] | 0
Markup Total | [7 empty] | 0
TOTAL Trade Partner COSTS | [7 empty] | 0
LOWER TIER Trade Partner
DESCRIPTION | [7 empty] | COST
E) Labor | [7 empty] | 0
20% Markup on Direct Labor | [7 empty] | 0
F) Equipment | [7 empty] | 0
15% Markup on Direct Equipment | [7 empty] | 0
G) Material | [7 empty] | 0
9% | Tax on Material | [6 empty] | 0
15% Markup on Direct Material | [7 empty] | 0
H) Other Costs (no markup allowed) | [7 empty] | 0
Subtotal (without markups) | [7 empty] | 0
Markup Total | [7 empty] | 0
TOTAL TIER Trade Partner COSTS | [7 empty] | 0
USE ADDITIONAL SHEETS AS NECESSARY

## Elec w. TelCom
Fill in highlighted fields ONLY
COST BREAKDOWN FORM FOR CONTRACT MODIFICATIONS
THIS FORM SHALL BE USED FOR ALL CHANGES TO THE CONTRACT
One separate form shall be used by each first tier Trade Partner and each lower tier Trade Partner.
PCO/CO Number: |  | XX.XX | Date: | XX/XX/XXX |  | Contract Number 26637
Name of Trade Partner: |  | Electrician with 2nd Tier Telecommunications Trade Partner
Description of Change:
REI: Provide 120vac standby power, raceway for security inputs and fire alarm. Install (2) alarm relays T&R: Provide security and low voltage conections for card reader functionality
Trade Partner AND TIER SUNCONTRACTOR WORK TOTALS | [7 empty] | Revisions/Comments
1. Labor Costs (see attached summary sheet ) |  |  |  |  | Line A + E | 0
2. Equipment (see attached summary sheet) |  |  |  |  | Line B + F | 0
3. Materials (see attached summary sheet) |  |  |  |  | Line (C + G) 9.00% | 0
4. Trade Partner and Tier Trade Partner Overhead |  |  |  |  | 20% of Line 1 15% of Line 2 & 3 | 0
5. Other Costs (no markup allowed) |  |  |  |  | Line D + H | 0
6. Trade Partner Mark-up on Tier Trade Partner |  |  |  |  | 6% of Tier Sub Direct Costs | 0
7. SUBTOTAL (ADD LINES 1 - 6) | [6 empty] | 0
8. Contractor Markup |  |  |  |  | 6% of All Subs Direct Costs | 0
9. Total Cost of Work |  |  |  |  | Line 7 + 8 |  | 0
Trade Partner
DESCRIPTION | [7 empty] | COST
A) Labor | [7 empty] | 0
20% Markup on Direct Labor | [7 empty] | 0
B) Equipment | [7 empty] | 0
15% Markup on Direct Equipment | [7 empty] | 0
C) Material | [7 empty] | 0
9% | Tax on Material | [6 empty] | 0
15% Markup on Direct Material | [7 empty] | 0
D) Other Costs (no markup allowed) | [7 empty] | 0
6% Markup on Tier Sub | [7 empty] | 0
Subtotal (without markups) | [7 empty] | 0
Markup Total | [7 empty] | 0
TOTAL Trade Partner COSTS | [7 empty] | 0
LOWER TIER Trade Partner
DESCRIPTION | [7 empty] | COST
E) Labor | [7 empty] | 0
20% Markup on Direct Labor | [7 empty] | 0
F) Equipment | [7 empty] | 0
15% Markup on Direct Equipment | [7 empty] | 0
G) Material | [7 empty] | 0
9% | Tax on Material | [6 empty] | 0
15% Markup on Direct Material | [7 empty] | 0
H) Other Costs (no markup allowed) | [7 empty] | 0
Subtotal (without markups) | [7 empty] | 0
Markup Total | [7 empty] | 0
TOTAL TIER Trade Partner COSTS | [7 empty] | 0
USE ADDITIONAL SHEETS AS NECESSARY

## AV Only
Fill in highlighted fields ONLY
COST BREAKDOWN FORM FOR CONTRACT MODIFICATIONS
THIS FORM SHALL BE USED FOR ALL CHANGES TO THE CONTRACT
One separate form shall be used by each first tier Trade Partner and each lower tier Trade Partner.
PCO/CO Number: |  | XX.XX | Date: | XX/XX/XXX |  | Contract Number 26637
Name of Trade Partner: |  | Electrician (2nd Tier Audio Visual Trade Partner Only)
Description of Change:
Remove and reinstall TVs
Trade Partner AND TIER SUNCONTRACTOR WORK TOTALS | [7 empty] | Revisions/Comments
1. Labor Costs (see attached summary sheet ) |  |  |  |  | Line A + E | 0
2. Equipment (see attached summary sheet) |  |  |  |  | Line B + F | 0
3. Materials (see attached summary sheet) |  |  |  |  | Line (C + G) 9.00% | 0
4. Trade Partner and Tier Trade Partner Overhead |  |  |  |  | 20% of Line 1 15% of Line 2 & 3 | 0
5. Other Costs (no markup allowed) |  |  |  |  | Line D + H | 0
6. Trade Partner Mark-up on Tier Trade Partner |  |  |  |  | 6% of Tier Sub Direct Costs | 0
7. SUBTOTAL (ADD LINES 1 - 6) | [6 empty] | 0
8. Contractor Markup |  |  |  |  | 6% of All Subs Direct Costs | 0
9. Total Cost of Work |  |  |  |  | Line 7 + 8 |  | 0
Trade Partner
DESCRIPTION | [7 empty] | COST
A) Labor | [7 empty] | 0
20% Markup on Direct Labor | [7 empty] | 0
B) Equipment | [7 empty] | 0
15% Markup on Direct Equipment | [7 empty] | 0
C) Material | [7 empty] | 0
9% | Tax on Material | [6 empty] | 0
15% Markup on Direct Material | [7 empty] | 0
D) Other Costs (no markup allowed) | [7 empty] | 0
6% Markup on Tier Sub | [7 empty] | 0
Subtotal (without markups) | [7 empty] | 0
Markup Total | [7 empty] | 0
TOTAL Trade Partner COSTS | [7 empty] | 0
LOWER TIER Trade Partner
DESCRIPTION | [7 empty] | COST
E) Labor | [7 empty] | 0
20% Markup on Direct Labor | [7 empty] | 0
F) Equipment | [7 empty] | 0
15% Markup on Direct Equipment | [7 empty] | 0
G) Material | [7 empty] | 0
9% | Tax on Material | [6 empty] | 0
15% Markup on Direct Material | [7 empty] | 0
H) Other Costs (no markup allowed) | [7 empty] | 0
Subtotal (without markups) | [7 empty] | 0
Markup Total | [7 empty] | 0
TOTAL TIER Trade Partner COSTS | [7 empty] | 0
USE ADDITIONAL SHEETS AS NECESSARY

## FA Only
Fill in highlighted fields ONLY
COST BREAKDOWN FORM FOR CONTRACT MODIFICATIONS
THIS FORM SHALL BE USED FOR ALL CHANGES TO THE CONTRACT
One separate form shall be used by each first tier Trade Partner and each lower tier Trade Partner.
PCO/CO Number: |  | XX.XX | Date: | XX/XX/XXX |  | Contract Number 26637
Name of Trade Partner: |  | Electrician (2nd Tier Fire Alarm Trade Partner Only)
Description of Change:
Design, program and commission fire alarm system
Trade Partner AND TIER SUNCONTRACTOR WORK TOTALS | [7 empty] | Revisions/Comments
1. Labor Costs (see attached summary sheet ) |  |  |  |  | Line A + E | 0
2. Equipment (see attached summary sheet) |  |  |  |  | Line B + F | 0
3. Materials (see attached summary sheet) |  |  |  |  | Line (C + G) 9.00% | 0
4. Trade Partner and Tier Trade Partner Overhead |  |  |  |  | 20% of Line 1 15% of Line 2 & 3 | 0
5. Other Costs (no markup allowed) |  |  |  |  | Line D + H | 0
6. Trade Partner Mark-up on Tier Trade Partner |  |  |  |  | 6% of Tier Sub Direct Costs | 0
7. SUBTOTAL (ADD LINES 1 - 6) | [6 empty] | 0
8. Contractor Markup |  |  |  |  | 6% of All Subs Direct Costs | 0
9. Total Cost of Work |  |  |  |  | Line 7 + 8 |  | 0
Trade Partner
DESCRIPTION | [7 empty] | COST
A) Labor | [7 empty] | 0
20% Markup on Direct Labor | [7 empty] | 0
B) Equipment | [7 empty] | 0
15% Markup on Direct Equipment | [7 empty] | 0
C) Material | [7 empty] | 0
9% | Tax on Material | [6 empty] | 0
15% Markup on Direct Material | [7 empty] | 0
D) Other Costs (no markup allowed) | [7 empty] | 0
6% Markup on Tier Sub | [7 empty] | 0
Subtotal (without markups) | [7 empty] | 0
Markup Total | [7 empty] | 0
TOTAL Trade Partner COSTS | [7 empty] | 0
LOWER TIER Trade Partner
DESCRIPTION | [7 empty] | COST
E) Labor | [7 empty] | 0
20% Markup on Direct Labor | [7 empty] | 0
F) Equipment | [7 empty] | 0
15% Markup on Direct Equipment | [7 empty] | 0
G) Material | [7 empty] | 0
9% | Tax on Material | [6 empty] | 0
15% Markup on Direct Material | [7 empty] | 0
H) Other Costs (no markup allowed) | [7 empty] | 0
Subtotal (without markups) | [7 empty] | 0
Markup Total | [7 empty] | 0
TOTAL TIER Trade Partner COSTS | [7 empty] | 0
USE ADDITIONAL SHEETS AS NECESSARY

## Glazing
Fill in highlighted fields ONLY
COST BREAKDOWN FORM FOR CONTRACT MODIFICATIONS
THIS FORM SHALL BE USED FOR ALL CHANGES TO THE CONTRACT
One separate form shall be used by each first tier Trade Partner and each lower tier Trade Partner.
PCO/CO Number: |  | XX.XX | Date: | XX/XX/XXX |  | Contract Number 26637
Name of Trade Partner: |  | Glazing with 2nd Tier Turnstile Specialties Installer
Description of Change:
Provide and Install turnstiles and glass guardrail per PCO 148 Turnstile Protection Handling, Transporiting and Delivery of Turnstile
Trade Partner AND TIER SUNCONTRACTOR WORK TOTALS | [7 empty] | Revisions/Comments
1. Labor Costs (see attached summary sheet ) |  |  |  |  | Line A + E | 0
2. Equipment (see attached summary sheet) |  |  |  |  | Line B + F | 0
3. Materials (see attached summary sheet) |  |  |  |  | Line (C + G) 9.00% | 0
4. Trade Partner and Tier Trade Partner Overhead |  |  |  |  | 20% of Line 1 15% of Line 2 & 3 | 0
5. Other Costs (no markup allowed) |  |  |  |  | Line D + H | 0
6. Trade Partner Mark-up on Tier Trade Partner |  |  |  |  | 6% of Tier Sub Direct Costs | 0
7. SUBTOTAL (ADD LINES 1 - 6) | [6 empty] | 0
8. Contractor Markup |  |  |  |  | 6% of All Subs Direct Costs | 0
9. Total Cost of Work |  |  |  |  | Line 7 + 8 |  | 0
Trade Partner
DESCRIPTION | [7 empty] | COST
A) Labor | [7 empty] | 0
20% Markup on Direct Labor | [7 empty] | 0
B) Equipment | [7 empty] | 0
15% Markup on Direct Equipment | [7 empty] | 0
C) Material | [7 empty] | 0
9% | Tax on Material | [6 empty] | 0
15% Markup on Direct Material | [7 empty] | 0
D) Other Costs (no markup allowed) | [7 empty] | 0
6% Markup on Tier Sub | [7 empty] | 0
Subtotal (without markups) | [7 empty] | 0
Markup Total | [7 empty] | 0
TOTAL Trade Partner COSTS | [7 empty] | 0
LOWER TIER Trade Partner
DESCRIPTION | [7 empty] | COST
E) Labor | [7 empty] | 0
20% Markup on Direct Labor | [7 empty] | 0
F) Equipment | [7 empty] | 0
15% Markup on Direct Equipment | [7 empty] | 0
G) Material | [7 empty] | 0
9% | Tax on Material | [6 empty] | 0
15% Markup on Direct Material | [7 empty] | 0
H) Other Costs (no markup allowed) | [7 empty] | 0
Subtotal (without markups) | [7 empty] | 0
Markup Total | [7 empty] | 0
TOTAL TIER Trade Partner COSTS | [7 empty] | 0
USE ADDITIONAL SHEETS AS NECESSARY