## Scorescheet
Scoring Criteria and Weighting of Each Section
710 Wilshire Hotel Santa Monica, California
| II | PROJECT MANAGEMENT |  | 20%
Plan Reading
Accuracy / Correct Answers
Subcontractor Scope Writing
Critical Thinking
Quality of Content
Accuracy / Correct Answers
Photo Hunt
Accuracy / Correct Answers
Project Dilemmas
Crtical Thinking
| III | PROJECT SCHEDULING |  | 15%
Concrete Structure Detailed CPM Schedule
Accuracy and completeness of schedule activities
Correct and Logical schedule order
Accurate and realistic schedule durations
Exterior Façade Phasing Plan Detailed Schedule
Accuracy and completeness of schedule activities
Correct and Logical schedule order
Accurate and realistic schedule durations
Landmark Building Detailed Demolition & Structural Retrofit Upgrades CPM Schedule
Accuracy and completeness of schedule activities
Correct and Logical schedule order
Accurate and realistic schedule durations
Mock-up Detailed Schedule
Identification of pertinent information
Correctly identifying interrelated trades
Critical thinking
Accuracy and completeness
| IV | PROJECT ESTIMATING |  | 15%
Overall Project Schedule of Values
Accuracy of quantities
Accurate and realistic pricing
Level of detail included in backup
Full Size Mock-up
Accuracy and completeness
Format of Change Order
| V | Field Management |  | 15%
Site Logistics
Accuracy and completeness
Locations of equipment is logical
Overall presentation
Constructability Issues
Logical Approach to Solution
Accuracy and completeness
Embed Plan
Accuracy and completeness
Mock-up Coordination Meeting
Critical Thinking and Reasoning
Preparation for Meeting
| VI | Project Execution Plan |  | 15%
Accurate and effective approach
Logical Approach to Solution
Creativity
Project Specific (not "canned" material)
Overall presentation (neatness, quality, etc.)
| TEAM PRESENTATION |  |  | 20%
Demonstrated knowledge of the project and requested subject matter
(presentation not "canned")
Response to questions and ability to think on your feet
Presentation Skills
Participation by all team members
PENALTY
Penalty for late Problem Turn-in
Deduct 10%